## VOWD (2) (hidden)
Contractor | Scope | M/S | PO Number | Description |  |  | Amt | % Progress | VOWD | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
STEVE INTEGRATED | BASE SCOPE | 1. DPA - BASE SCOPE |  |  | NGN | USD | FUSD
A (onshore procurement, fabrication, and offshore pre-drill and post drill installation)
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 7251375 | 23775 | 75% | 17831.25
|  | 1.2 |  | Onshore demobilisation | 0 | 1712523.15 | 5614.83 | 75% | 4211.1225
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 9629688.75 | 31572.75 | 75% | 23679.5625
|  | 1.4 |  | Offshore demobilisation | 0 | 3845160.9476 | 12607.0851 | 75% | 9455.3138
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 18273858 | 59914.2885 | 75% | 44935.7164
|  | 2 |  | Project Management | 13382.04 | 2729936.16 | 22332.6504 | 80% | 17866.1203
|  | 3 |  | Procurement |  |  |  |  | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 102084.7142 | 20825250.8465 | 170364.2252 | 100% | 170364.2252
|  |  |  | Piping & Accessories (Deliver) | 102084.7142 | 20825250.8465 | 170364.2252 | 100% | 170364.2252
|  | 3.2 |  | Instrument (FOB) | 290182.4417 | 45461348.0024 | 439236.0418 | 100% | 439236.0418
|  |  |  | Instrument (Deliver) | 290182.4417 | 45461348.0024 | 439236.0418 | 100% | 439236.0418
|  | 3.3 |  | Civil/Structural | 1327.003 | 269823.9409 | 2211.6716 | 100% | 2211.6716
|  | 3.4 |  | Mechanical/HVAC | 5722.093 | 2559700 | 14114.552 | 100% | 14114.552
|  | 3.5 |  | Electrical | 18323.872 | 4242138.8385 | 32232.5239 | 100% | 32232.5239
|  | 3.6 |  | Painting | 2971.1066 | 604125 | 4951.8443 | 100% | 4951.8443
|  | 4 |  | Onshore Fabrication |  |  | 0 |  | 0
|  | 4.1 |  | Production of shop drawing | 9439.1004 | 1919283.7467 | 15731.834 | 100% | 15731.834
|  | 4.2 |  | Fabrication of piping spools | 160464.7067 | 32627823.6934 | 267441.1778 | 100% | 267441.1778
|  | 4.3 |  | NDT | 18878.2008 | 3838567.4933 | 31463.668 | 100% | 31463.668
|  | 5 |  | Installation/ Commissioning |  |  | 0 |  | 0
|  | 5.1 |  | Advance tie-in | 44945.73 | 9138965.1094 | 74909.5501 | 85% | 63673.1176
|  | 5.2 |  | Pre-drill installation | 104873.3701 | 21324251.922 | 174788.9502 | 85% | 148570.6077
|  | 5.3 |  | Hook-up | 119855.2801 | 24370573.6251 | 199758.8002 | 85% | 169794.9802
|  | 5.4 |  | Commissioning | 29963.82 | 6092643.4063 | 49939.7001 | 85% | 42448.745
|  | BASE SCOPE SUB-TOTAL |  |  | 1314680.6347 | 283003636.4811 | 2242561.41 |  | 2129814.3415
|  | B. OPTIONAL LOGISTICS (Vessels) | [6 empty] | 0
|  | 1 |  | Logistics (Land & Offshore) |  |  |  |  | 0
|  |  |  | Marine Logistics |  |  |  |  | 0
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 days for predrill, 6 days for precomissioning/wellhead tie-in) | 224190.6264 | 45585427.368 | 373651.044
|  |  |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System).)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 246328.2907 | 50086752.4376 | 410547.1511
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 0 | 0 | 0
|  |  |  | Land Logistics | 0 | 0 | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 days for material movement) | 572.8 | 137472 | 1023.5279
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) | 859.2 | 206208 | 1535.2918
|  | 2 |  | Habitat |  |  | 0 |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5705.088 | 1160034.56 | 9508.48 | 100% | 9508.48
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 |  | 0
|  |  |  | Instruments/valves on spare flowlines | 278191.6471 | 56565634.9144 | 463652.7452 |  | 0
|  | OPTIONAL VESELS SUB-TOTAL |  |  | 755847.6522 | 153741529.28 | 1259918.24 |  | 9508.48
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION | [6 empty] | 0
|  | 1 |  | Removal of Boat Catcher & Crane | 916214.1908 | 214678934.5661 | 1620079.55 | 100% | 1620079.55
|  | 2 |  | Re-installation of Boat Catcher & Crane | 182595.3074 | 39707328.5839 | 312783.27 | 0% | 0
|  | BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SUB-TOTAL |  |  | 1098809.4982 | 254386263.15 | 1932862.82 |  | 1620079.55
|  | DPA BASE SCOPE TOTAL |  |  | 3169337.785 | 691131428.9112 | 5435342.47 |  | 3759402.3715
|  | A. DPJ - BASE SCOPE | [6 empty] | 0
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 7670312.4168 | 25148.5653 | 60% | 15089.1392
|  | 1.2 |  | Onshore demobilisation | 0 | 1811461.6306 | 5939.2185 | 60% | 3563.5311
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 10186029.7101 | 33396.8187 | 60% | 20038.0912
|  | 1.4 |  | Offshore demobilisation | 0 | 4067309.4084 | 13335.4407 | 60% | 8001.2644
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 19329602.9953 | 63375.7475 | 60% | 38025.4485
|  | 2 |  | Project Management | 34888.89 | 7117333.56 | 58224.4099 | 60% | 34934.6459
|  | 3 |  | Procurement |  |  | 0 |  | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 192891.949 | 39349895.6653 | 321908.0003 | 100% | 321908.0003
|  |  |  | Piping & Accessories (Deliver) | 192891.949 | 39349895.6653 | 321908.0003 | 100% | 321908.0003
|  | 3.2 |  | Instrument (FOB) | 521677.8075 | 64881676.1177 | 734404.6144 | 100% | 734404.6144
|  |  |  | Instrument (Deliver) | 521677.8075 | 64881676.1177 | 734404.6144 | 100% | 734404.6144
|  | 3.3 |  | Civil/Structural | 5281.1622 | 1073836.3107 | 8801.937 | 100% | 8801.937
|  | 3.4 |  | Mechanical/HVAC | 2136.186 | 930800 | 5187.9893 | 100% | 5187.9893
|  | 3.5 |  | Electrical |  |  | 0 | 100% | 0
|  | 3.6 |  | Painting | 5460.8939 | 1110381.75 | 9101.4898 | 100% | 9101.4898
|  | 4 |  | Onshore Fabrication |  |  | 0 |  | 0
|  | 4.1 |  | Production of shop drawing | 18878.2008 | 3838567.4933 | 31463.668 | 100% | 31463.668
|  | 4.2 |  | Fabrication of piping spools | 320929.4134 | 65255647.3868 | 534882.3556 | 100% | 534882.3556
|  | 4.3 |  | NDT | 37756.4016 | 7677134.9867 | 62927.336 | 100% | 62927.336
|  | 5 |  | Installation/ Commissioning |  |  | 0 |  | 0
|  | 5.1 |  | Advance tie-in | 76570.9033 | 15569417.0026 | 127618.1722 | 70% | 89332.7205
|  | 5.2 |  | Pre-drill installation | 178665.441 | 36328639.6728 | 297775.735 | 70% | 208443.0145
|  | 5.3 |  | Hook-up | 204189.0754 | 41518445.3403 | 340315.1257 | 70% | 238220.588
|  | 5.4 |  | Commissioning | 51047.2689 | 10379611.3351 | 85078.7814 | 70% | 59555.147
|  | HOOKUP SCOPE DPJ SUB-TOTAL |  |  | 2364943.3493 | 442327674.5654 | 3815198.02 |  | 3480193.5955
B. DPJ - XXXXX SCOPE
|  | 1 |  | Logistics (Land & Offshore)
Marine Logistics
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 for predrill, 6 days for precomissioning/wellhead tie-in) | 224190.6264 | 45585427.368 | 373651.044
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 0 | 0 | 0
|  |  |  | Provision of Crewboat (Hookup of Last Well post Rigmove)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 410547.1511 | 83477920.7293 | 684245.2519
|  |  |  | Land Logistics | 0 | 0 | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 for material movement) | 572.8 | 137472 | 1023.5279
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) | 859.2 | 206208 | 1535.2918
0
|  | 3 |  | Habitat |  |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5705.088 | 1160034.56 | 9508.48 | 100% | 9508.48
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0
|  |  |  | Instruments/valves on spare flowlines | 296948.4027 | 60379508.5427 | 494914.0044 | 0%
|  | OPTIONAL SCOPE DPJ SUB-TOTAL |  |  | 938823.2682 | 190946571.2 | 1564877.6 |  | 9508.48
|  | DPJ BASE SCOPE TOTAL |  |  | 3303766.6175 | 633274245.7654 | 5380075.62 |  | 3489702.0755
|  | TOTAL BASE SCOPE (PLATFORMS A & J) |  |  | 6473104.4025 | 1324405674.6766 | 10815418.09 |  | 7249104.4469
| OPTIONAL SCOPE | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPA | [6 empty] | 0
|  | 1 |  | DPA - MARINE LOGISTICS |  |  |  |  | 0
|  | 1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPA WELL HOOKUP) |  |  |  |  | 0
|  | 1.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days. | 310875.12 | 63211274.4 | 518125.2
|  | 1.1.4 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 145200 | 29524000 | 242000
|  | 1.1.5 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 477000 | 96990000 | 795000
|  | 1.1.6 |  | Provision of SEWOP Support Vessel | 180000 | 36600000 | 300000
|  | 1.1.7 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 180000 | 36600000 | 300000
|  | 1.1.8 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 72000 | 14640000 | 120000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1365075.12 | 277565274.4 | 2275125.2 |  | 0
|  | 1.2 |  | Boat Catcher/Crane Removal & Debris Survey (ALL DPA WELL HOOKUP) |  |  |  |  | 0
|  | 1.2.1 |  | Provision of DP2 PSV boat – For Medevac/ERP –(Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (In addition to Contractor Crew, allow for 3 Diving crew,6NOV Crew, 5 SPDC) & Debris Survey | 362687.64 | 73746486.8 | 604479.4
|  | 1.2.5 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 556500 | 113155000 | 927500
|  | 1.2.5 |  | Provision of SEWOP Support Vessel | 210000 | 42700000 | 350000
|  | 1.2.6 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 210000 | 42700000 | 350000
|  | 1.2.5 |  | Provision of a Diving Spread comprising: | 0 | 0 | 0
|  | 1.2.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 84000 | 17080000 | 140000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1523508.84 | 309780130.8 | 2539181.4 |  | 0
|  | 1.3 |  | DPA Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 1.3.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days. | 227975.088 | 46354934.56 | 379958.48 |  | 0
|  |  |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 145200 | 29524000 | 242000 |  | 0
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 349800 | 71126000 | 583000 |  | 0
|  | 1.3.4 |  | Provision of SEWOP Support Vessel | 132000 | 26840000 | 220000 |  | 0
|  | 1.3.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 132000 | 26840000 | 220000 |  | 0
|  | 1.3.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 52800 | 10736000 | 88000 |  | 0
|  |  |  | Sub-total (With Class 230 SEWOP) | 1039775.088 | 211420934.56 | 1732958.48 |  | 0
|  | 1.4 |  | Boat Catcher Reinstallation |  |  |  |  | 0
|  | 1.4.1 |  | Provision of DP2 PSV boat for Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position | 186525.072 | 37926764.64 | 310875.12 |  | 0
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 286200 | 58194000 | 477000 |  | 0
|  | 1.4.3 |  | Provision of SEWOP Support Vessel | 108000 | 21960000 | 180000 |  | 0
|  | 1.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 108000 | 21960000 | 180000 |  | 0
|  | 1.4.5 |  | Provision of a Diving Spread comprising: | 0 | 0 | 0 |  | 0
|  | 1.4.6.1 |  | Two LARS systems (for working diver and standby diver resp.) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.6.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.6.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.6.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.6.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.7 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 43200 | 8784000 | 72000 |  | 0
|  |  |  | Sub-total (With Class 230 SEWOP) | 783518.832 | 159315495.84 | 1305864.72 |  | 0
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPA TOTAL |  |  | 4711877.88 | 958081835.6 | 7853129.8 | 0% | 0
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPJ | [6 empty] | 0
|  | 3.1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPJ WELL HOOKUP) |  |  |  |  | 0
|  | 3.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 310875.12 | 63211274.4 | 518125.2 |  | 0
|  | 3.1.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 200 SEWOP with a crane capacity as 5tons@20 m radius Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 128400 | 26108000 | 214000 |  | 0
|  | 3.1.3 |  | Provision of Class 200 SEWOP with a crane capacity as 5tons@20 m radius. Crane must be manriding certified. | 417600 | 84912000 | 696000 |  | 0
|  | 3.1.4 |  | Provision of SEWOP Support Vessel | 180000 | 36600000 | 300000 |  | 0
|  | 3.1.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 180000 | 36600000 | 300000 |  | 0
|  | 3.1.6 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 72000 | 14640000 | 120000 |  | 0
|  |  |  | Sub-total | 1288875.12 | 262071274.4 | 2148125.2 |  | 0
|  | 3.2 |  | DPJ Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 3.2.1 |  | Provision of DP2 PSV boat - (option to MV Bello) – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 227975.088 | 46354934.56 | 379958.48 |  | 0
|  | 3.2.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 200 SEWOP with a crane capacity as 5tons@20 m radius. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 128400 | 26108000 | 214000 |  | 0
|  | 3.2.3 |  | Provision of Class 200 SEWOP with a crane capacity as 5tons@20 m radius for both boat catcher and crane dismantling . Crane must be manriding certified. | 306240 | 62268800 | 510400 |  | 0
|  | 3.2.4 |  | Provision of SEWOP Support Vessel | 132000 | 26840000 | 220000 |  | 0
|  | 3.2.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 132000 | 26840000 | 220000 |  | 0
|  | 3.2.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 52800 | 10736000 | 88000 |  | 0
|  |  |  | Sub-total | 979415.088 | 199147734.56 | 1632358.48 |  | 0
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPJ |  |  | 2268290.208 | 461219008.96 | 3780483.68 |  | 0
|  | TOTAL ADDITIONAL VESSELS |  |  | 6980168.088 | 1419300844.56 | 11633613.48 |  | 0
0
|  |  |  | Crane Services |  |  |  |  | 0
|  | 1 |  | Crane removal |  |  |  |  | 0
|  | 2 |  | Reinstallation of crane | 355816.4344 | 10408657.415 | 389943.18 | 50% | 194971.59
|  |  |  | Telecoms Relocation |  |  |  |  | 0
|  | 1 |  | Mobilisation and 50% relocation works | 59869.6069 | 6086743.3681 | 79826.1425 | 100% | 79826.1425
|  | 2 |  | Complete telecoms works 100% | 59869.6069 | 6086743.3681 | 79826.1425 | 100% | 79826.1425
|  |  |  | Instrumentation (Invesys) |  |  |  |  | 0
|  | 1 |  | 50% Instrumentation works | 205548.054 | 41794770.98 | 342580.09 | 20% | 68516.018
|  | 2 |  | Complete Instrumentation works | 205548.054 | 41794770.98 | 342580.09 | 20% | 68516.018
|  |  |  | Gas Lift Modification |  |  |  |  | 0
|  | 1 |  | Project Management | 77.538 | 15817.745 | 129.3994 | 100% | 129.3994
|  | 2 |  | Procurement | 1300.6952 | 0 | 1300.6952 |  | 0
|  | 3 |  | Onshore Fabrication | 1506.9909 | 306421.4925 | 2511.6516 |  | 0
|  | 4 |  | Installation/Commissioning | 4209.0261 | 564014.4476 | 6058.2538 |  | 0
|  | CRANE SERVICES TELE COM GASLIFT TOTAL |  |  | 893746.0064 | 107057939.7964 | 1244755.6451 |  | 491785.3105
|  | TOTAL OPTIONAL SCOPE (PLATFORMS A AND J) |  |  | 7873914.0944 | 1526358784.3564 | 12878369.1251 |  | 491785.3105
DORMALONG | BASE SCOPE | A.HOOKUP SCOPE DPB | [6 empty] | 0
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 6366052.1022 | 20872.302 | 10% | 2087.2302
|  | 1.2 |  | Onshore demobilisation | 0 | 1503440.6025 | 4929.3135 | 10% | 492.9313
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 8453996.6986 | 27718.022 | 10% | 2771.8022
|  | 1.4 |  | Offshore demobilisation | 0 | 3375703.9091 | 11067.8817 | 10% | 1106.7882
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 16042796.3161 | 52599.3322 | 10% | 5259.9332
|  | 2 |  | Project Management | 26177.0838 | 5340125.1038 | 43685.6907 | 2% | 873.7138
|  | 3 |  | Procurement | 0 | 0 | 0 |  | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 81214.7716 | 16513670.2254 | 135357.9527 |  | 0
|  |  |  | Piping & Accessories (Deliver) | 81214.7716 | 16513670.2254 | 135357.9527 |  | 0
|  | 3.2 |  | Instrument (FOB) | 202329.0868 | 41140247.6511 | 337215.1447 |  | 0
|  |  |  | Instrument (Deliver) | 202329.0868 | 41140247.6511 | 337215.1447 |  | 0
|  | 3.3 |  | Civil/Structural | 1054.3317 | 214380.7844 | 1757.2195 |  | 0
|  | 3.4 |  | Mechanical/HVAC | 6728.5847 | 1368145.5548 | 11214.3078 |  | 0
|  | 3.5 |  | Electrical | 15365.6501 | 3124348.848 | 25609.4168 |  | 0
|  | 3.6 |  | Painting | 2360.6065 | 479989.9924 | 3934.3442 |  | 0
|  | 4 |  | Onshore Fabrication | 0 | 0 | 0 |  | 0
|  | 4.1 |  | Production of shop drawing | 12005.6099 | 2441140.6811 | 20009.3498 |  | 0
|  | 4.2 |  | Fabrication of piping spools | 204095.3684 | 41499391.5793 | 340158.9474 |  | 0
|  | 4.3 |  | NDT | 24011.2198 | 4882281.3623 | 40018.6997 |  | 0
|  | 5 |  | Installation/ Commissioning | 0 | 0 |  |  | 0
|  | 5.1 |  | Advance tie-in | 47698.0018 | 9698593.7044 | 79496.6697 |  | 0
|  | 5.2 |  | Pre-drill installation | 111295.3376 | 22630051.977 | 185492.2293 |  | 0
|  | 5.3 |  | Hook-up | 127194.6715 | 25862916.5452 | 211991.1192 |  | 0
|  | 5.4 |  | Commissioning | 31798.6679 | 6465729.1363 | 52997.7798 |  | 0
|  | HOOKUP SCOPE DPB SUB-TOTAL |  |  | 1176872.8507 | 275056920.6507 | 2078698.82 |  | 12592.3989
|  | B. OPTIONAL SCOPE DPB | [6 empty] | 0
|  | 1 |  | Logistics (Land & Offshore) |  |  |  |  | 0
|  |  |  | Marine Logistics | 217198.048 | 44163603.1002 | 361996.7467 |  | 0
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 for predrill, 6 days for precomissioning/wellhead tie-in) | 0 | 0 | 0 |  | 0
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 397742.0523 | 80874217.301 | 662903.4205 |  | 0
|  |  |  | Provision of Crewboat (Hookup of Last Well post Rigmove)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 0 | 0 | 0 |  | 0
|  |  |  | Land Logistics | 554.9342 | 133184.2037 | 991.6037 |  | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 for material movement) | 832.4013 | 199776.3056 | 1487.4056 |  | 0
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) |  |  | 0 |  | 0
|  | 2 |  | Habitat |  |  | 0 |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5527.1445 | 1123852.7058 | 9211.9074 |  | 0
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 |  | 0
|  | 4 |  | Instruments/valves on spare flowlines | 287686.4857 | 58496252.0837 | 479477.4761 |  | 0
|  | OPTIONAL SCOPE DPB SUB-TOTAL |  |  | 909541.0659 | 184990885.7 | 1516068.56 |  | 0
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | 1 |  | Removal of Boat Catcher & Crane | 1319619.5832 | 12447957.924 | 1360432.56 |  | 0
|  | 2 |  | Re-installation of Boat Catcher & Crane | 1043395.492 | 226897658.1421 | 1787322.24 |  | 0
|  | BOAT CATCHER SUB-TOTAL |  |  | 2363015.0752 | 239345616.0661 | 3147754.8 |  | 0
|  | DORMANLONG DPA | [6 empty] | 0
|  | B. OPTIONAL SCOPE | [6 empty] | 0
|  | Logistics (Land & Offshore) | [6 empty] | 0
|  |  |  | Marine Logistics |  |  |  |  | 0
|  |  |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System).)(Max 16 days for precomissioning/wellhead tie-in) | 177531.168 | 36098004.16 | 295885.28 |  | 0
|  | SUB-TOTAL |  |  | 177531.168 | 36098004.16 | 295885.28 |  | 0
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | Re-installation of Boat Catcher & Crane | [6 empty] | 0
|  |  |  | Cost for DP-2 Construction & Diving Support Vessel | 330642.9598 | 67230735.1624 | 551071.5997 |  | 0
|  |  |  | Cost for diving services | 135647.3017 | 27581618.0192 | 226078.8362 |  | 0
|  |  |  | Cost of meals& bunks | 32112.4225 | 6529525.8984 | 53520.7041 |  | 0
|  | SUB-TOTAL |  |  | 498402.684 | 101341879.08 | 830671.14 |  | 0
|  | TOTAL BASE SCOPE PLATFORM B |  |  | 5125362.8437 | 836833305.6568 | 7869078.6 |  | 12592.3989
| OPTIONAL SCOPE | 2 |  | DPB - MARINE LOGISTICS |  |  |  |  | 0
|  | 2.1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPB WELL HOOKUP) |  |  |  |  | 0
|  | 2.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 248700.096 | 50569019.52 | 414500.16 |  | 0
|  | 2.1.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.1.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 381600 | 77592000 | 636000 |  | 0
|  | 2.1.4 |  | Provision of SEWOP Support Vessel | 144000 | 29280000 | 240000 |  | 0
|  | 2.1.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 144000 | 29280000 | 240000 |  | 0
|  | 2.1.6 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 57600 | 11712000 | 96000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 1134900.096 | 230763019.52 | 1891500.16 |  | 0
|  | 2.2 |  | Boat Catcher/Crane Removal & Debris Survey (ALL DPB WELL HOOKUP) |  |  |  |  | 0
|  | 2.2.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) & Debris Survey | 248700.096 | 50569019.52 | 414500.16 |  | 0
|  | 2.2.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.2.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 381600 | 77592000 | 636000 |  | 0
|  | 2.2.4 |  | Provision of SEWOP Support Vessel | 144000 | 29280000 | 240000 |  | 0
|  | 2.2.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 144000 | 29280000 | 240000 |  | 0
|  | 2.2.6 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0
|  | 2.2.6.1 |  | Two LARS systems (for working diver and standby diver resp.) | 27516.672 | 5595056.64 | 45861.12 |  | 0
|  | 2.2.6.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.7 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 57600 | 11712000 | 96000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 1217450.112 | 247548189.44 | 2029083.52 |  | 0
0
|  | 2.3 |  | DPB Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 2.3.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 196887.576 | 40033807.12 | 328145.96 |  | 0
|  | 2.3.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.3.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0
|  | 2.3.4 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0
|  | 2.3.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0
|  | 2.3.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 45600 | 9272000 | 76000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 931587.576 | 189422807.12 | 1552645.96 |  | 0
|  | 2.4 |  | Boat Catcher Reinstallation |  |  |  |  | 0
|  | 2.4.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) | 196887.576 | 40033807.12 | 328145.96 |  | 0
|  | 2.4.2 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0
|  | 2.4.3 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) |  |  | 0 |  | 0
|  | 2.4.3 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.5 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0
|  | 2.4.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 21784.032 | 4429419.84 | 36306.72 |  | 0
|  | 2.4.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 45600 | 9272000 | 76000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 837939.672 | 170381066.64 | 1396566.12 |  | 0
0
|  |  |  | Crane Services |  |  |  |  | 0
|  | 1 |  | Crane Services | 355816.4344 | 10408657.415 | 389943.18 |  | 0
|  |  |  | Gas Lift Modification |  |  |  |  | 0
|  | 1 |  | Project Management | 88.9406 | 18143.8875 | 148.4288 |  | 0
|  | 2 |  | Procurement | 1491.9742 |  | 1491.9742 |  | 0
|  | 3 |  | Onshore Fabrication | 1728.6076 | 351483.5446 | 2881.0127 |  | 0
|  | 4 |  | Installation/Commissioning | 4828.0014 | 646957.8737 | 6949.1748 |  | 0
|  | Sub-Total |  |  | 363953.9583 | 11425242.7208 | 401413.7705 |  | 0
0
|  | 2.4 |  | Boat Catcher Reinstallation (DPA) |  |  |  |  | 0
|  | 2.4.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) | 196887.576 | 40033807.12 | 328145.96 |  | 0
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0
|  | 2.4.3 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.5 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0
|  | 2.4.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 21784.032 | 4429419.84 | 36306.72 |  | 0
|  | 2.4.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 45600 | 9272000 | 76000 |  | 0
|  |  |  | Sub-total with SEWOP 200 | 837939.672 | 170381066.64 | 1396566.12 |  | 0
|  | TOTAL OPTIONAL SCOPE PLATFORM B |  |  | 5323771.0863 | 1019921392.0808 | 8667775.6505 |  | 0
[7 empty] | 40230641.4655 |  | 7753482.1564
0
Marine Logisitics | [6 empty] | 3826539.34 |  | 3826539.34
DED | [6 empty] | 632656.64 |  | 632656.64
Technical Support service/QA QC | [6 empty] | 641362.18 |  | 641362.18
OTHERS (Catering, Hotel,travels, logistics) | [6 empty] | 66811.42 |  | 66811.42
5167369.58
PMT/OTHERS | [8 empty] | 0
SALARIES | [6 empty] | 2038937.73 |  | 2038937.73
TP OVERHEAD | [6 empty] | 3187943.41 |  | 744596.97
OTHERS (Catering, Hotel,Aviation,Travels, Government Levies) | [6 empty] | 404408.71 |  | 404408.71
3187943.41
16108795.1464

## Summary (2) (hidden)
EA FOD FACILITIES CONTRACT COST PERFORMANCE SUMMARY
CONTRACTOR | SCOPE | PLAT FORM | WORKSCOPE | CONTRACT | BUDGET (CONTRACT) per PLATFORM | EAC | VOWD ITD | VOWD | ESTIMATE TO COMPLETE | ESTIMATE AT COMPLETION | ETC | TARGET SAVINGS
0
|  |  |  | 0 |  |  | 0 | 0 | 0 | 0
SI | BASE SCOPE | DPA | Onshore Fabrication, predrills, post drills, Boatcatcher/Crane removal + Tel Mast relocation (DPA) | 10815418.09 | 5435342.47 | 10815418.09 | 3814418.9098 | 5576419.68 | 1515598.7222 | 7092018.4022 | 3343794.8925 | 0
|  | DPJ |  |  | 5380075.62 |  | 3657204.2877
| MODIFICATION SCOPE | DA | Travel to Site, Spud & Pre-drill Offshore Logistics | 12878369.1251 | 7853129.8 | 12878369.13 | 0 | 2622106.64 | 2058835.0546 | 4680941.6946 | 3000000 | 8386583.8146 | 5031950.2887
|  | DPJ |  |  | 5025239.3251 |  | 491785.3105
| VARIATION ORDER |  | Additional Flow Lines from DPB to DPA (SHALLOW GAS); Cables; omitted materials for EI installation: MCB Approved, Negotiation held with NAPIMs. |  |  | 2900000 | 2900000 | 2900000 | 0 | 2900000 | -2900000 | 0 |  | TRANSFER LINES FROM dpb TO dpa (SHALLOW GAS) + ; Cables: mcb Approved, NAPIMS review planned
DL | BASE SCOPE | DPB | On shore Fabrication, predrills, post drills, Boatcatcher/Crane removal + Tel Mast relocation (DPA) | 7869078.6 | 6742522.18 | 7869078.6 | 750096.9961 | 750096.9961 | 4651754.4596 | 5401851.4557 |  | 0
|  | DPA |  |  | 1126556.42 |  | 0
| MODIFICATION SCOPE | DPB | Travel to Site, Spud & Pre-drill Offshore Logistics | 8667775.6505 | 7271209.5305 | 8667775.65 | 0 | 0 | 1396566.12 | 1396566.12 |  | -600000
|  | DPA | Re-installation of Boat Catcher & Crane |  | 1396566.12 |  | 0
|  | DPB | If Frigg drills DPB, Boatcatcher/Crane will no longer be removed |  |  | -6000000 |  |  |  | 0
| EMERGING VO (To be reconciled) |  | Potential Reduction based on reduction from 5nos. To 3Nos. Wells (Reconcilliation ongoing with Dorman Long) |  |  | -700000 | 0 |  | -700000 | -700000 |  |  |  | TRANSFER LINES FROM dpb TO dpa (SHALLOW GAS) + ; Cables: mcb Approved, NAPIMS review planned
SI & DL Contract Total |  |  |  | 40230641.4655 | 40230641.4655 | 36430641.47 | 11613505.5041 | 11848623.3161 | 8922754.3563 | 20771377.6724 | 3443794.8925
Corporate Marine | Marine Logisitics | DPA/DPJ | Marine Logisitics |  |  | 4620982.0959 | 4620982.0959 | 4382111.4 | 4179596.4 | 8561707.8
Technical Support/Others | Technical Support/Others | DPA/DPB/DPJ | QA/QC Tech Support/others |  |  | 1000496.85 | 1000496.85 | 1000496.85 | 850000 | 1850496.85
DED | DED | DP A,DPB & DP J | Detail Engineering Design | 680000 |  |  |  | 632656.64 | 0 | 632656.64
Marine/Technical Support Total |  |  |  | 680000 | 0 | 5621478.9459 | 5621478.9459 | 6015264.89 | 5029596.4 | 11044861.29 | 3543794.8925
Grand Total |  |  |  | 41590641.4655 |  | 42052120.4159 | 17234984.45 | 17863888.2061 | 13952350.7563 | 31816238.9624
|  |  |  | VOWD |  |  |  | ETC
OTHERS
OTHERS | Marine Logisitics | DPA/DPJ | Marine Logisitics
| Marine Logisitics | DPB | Marine Logisitics
| Technical Support service/QA QC |  | Technical Support service/QA QC
| Catering, Hotel,travels, logistics |  | Catering, Hotel,travels, logistics
PMT JV line
PMT | SALARIES | #REF! | SALARIES
| TP OVERHEAD |  | TP OVERHEAD
| OTHERS (Catering, Hotel,Aviation,Travels, Government Levies) |  | OTHERS (Catering, Hotel,Aviation,Travels, Government Levies)
Total ITD VOWD
|  |  | SI Base Scope | 8476419.68 |  |  |  | 1515598.7222
|  |  | DLE Base Scope | 750096.9961 |  |  |  | 4651754.4596
|  |  | Marine Logisitics | 4250648.058 | 4054208.508 | 8304856.566 | 0 | 0
|  |  | DED | 421771.0933 |  |  |  | 0
|  |  | QA/QC Tech Support/others | 1000496.85 |  |  |  | 170000
|  |  |  | 14899432.6774 | 4054208.508 | 8304856.566 | 0 | 6337353.1817
|  |  | SI Mod Scope | 2622106.64 |  |  |  | 2058835.0546
|  |  | DLE Mod Scope | 0 |  |  |  | 1396566.12
|  |  | Marine Logisitics | 131463.342 |  |  |  | 4179596.4
|  |  | DED | 210885.5467 |  |  |  | 0
|  |  | QA/QC Tech Support/others | 0 |  |  |  | 680000
|  |  | EMERGING VO (To be reconciled) | 0 |  |  |  | -700000
|  |  |  | 2964455.5287 | 8314997.5746 | 8314997.5746 | 8314997.5746 | 7614997.5746
|  |  |  | 17863888.2061 | 12369206.0826 | 16619854.1406 | 8314997.5746 | 13952350.7563

## Summary (hidden)
SUMMARY
CONTRACT
CONTRACTOR | SCOPE | PLAT FORM | BUDGET | BUDGET per PLATFORM | VOWD ITD per PLATFORM | VOWD per SCOPE | PERCENTAGE
SI | BASE SCOPE | DPA | 10815418.09 | 5435342.47 | 3814418.9098 | 7471623.1975 | 69.08%
|  | DPJ |  | 5380075.62 | 3657204.2877
| OPTIONAL SCOPE | DA | 12878369.1251 | 7853129.8 | 0 | 491785.3105 | 3.819%
|  | DPJ |  | 5025239.3251 | 491785.3105
DL | BASE SCOPE | DPB | 7869078.6 | 6742522.18 | 750096.9961 | 750096.9961 | 9.532%
|  | DPA |  | 1126556.42 | 0
| OPTIONAL SCOPE | DPB | 8667775.6505 | 7271209.5305 | 0 | 0 | 0%
|  | DPA |  | 1396566.12 | 0
|  |  | 40230641.4655 | 40230641.4655 | 8713505.5041 | 8713505.5041
OTHERS |  | VOWD
OTHERS | Marine Logisitics | 3826539.34
| DED | 632656.64
| Technical Support service/QA QC | 641362.18
| Catering, Hotel,travels, logistics | 66811.42
5167369.58
PMT JV line |  | VOWD
PMT | SALARIES | 2038937.73
| TP OVERHEAD | 744596.97
| OTHERS (Catering, Hotel,Aviation,Travels, Government Levies) | 404408.71
3187943.41
Total ITD VOWD |  | 17068818.4941
Marine Logistics VOWD per Contract |  | 8274497.2512
Marine Logistics VOWD Per |  | 3826539.34
Savings |  | 4447957.9112
Draft Cost Savings Summary

## VOWD (hidden)
Contractor | Scope | M/S | PO Number | Description |  |  | Amt | % Progress | VOWD | ETC |  | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
STEVE INTEGRATED | BASE SCOPE | A. HOOKUP SCOPE DPA |  |  | NGN | USD | FUSD
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 7251375 | 23775 | 95% | 22586.25 | 1188.75
|  | 1.2 |  | Onshore demobilisation | 0 | 1712523.15 | 5614.83 | 95% | 5334.0885 | 280.7415
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 9629688.75 | 31572.75 | 95% | 29994.1125 | 1578.6375
|  | 1.4 |  | Offshore demobilisation | 0 | 3845160.9476 | 12607.0851 | 95% | 11976.7308 | 630.3543
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 18273858 | 59914.2885 | 95% | 56918.5741 | 2995.7144
|  | 2 |  | Project Management | 13382.04 | 2729936.16 | 22332.6504 | 95% | 21216.0178 | 1116.6325
|  | 3 |  | Procurement |  |  |  |  | 0 | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 102084.7142 | 20825250.8465 | 170364.2252 | 100% | 170364.2252 | 0
|  |  |  | Piping & Accessories (Deliver) | 102084.7142 | 20825250.8465 | 170364.2252 | 100% | 170364.2252 | 0
|  | 3.2 |  | Instrument (FOB) | 290182.4417 | 45461348.0024 | 439236.0418 | 100% | 439236.0418 | 0
|  |  |  | Instrument (Deliver) | 290182.4417 | 45461348.0024 | 439236.0418 | 100% | 439236.0418 | 0
|  | 3.3 |  | Civil/Structural | 1327.003 | 269823.9409 | 2211.6716 | 100% | 2211.6716 | 0
|  | 3.4 |  | Mechanical/HVAC | 5722.093 | 2559700 | 14114.552 | 100% | 14114.552 | 0
|  | 3.5 |  | Electrical | 18323.872 | 4242138.8385 | 32232.5239 | 100% | 32232.5239 | 0
|  | 3.6 |  | Painting | 2971.1066 | 604125 | 4951.8443 | 100% | 4951.8443 | 0
|  | 4 |  | Onshore Fabrication |  |  | 0 |  | 0 | 0
|  | 4.1 |  | Production of shop drawing | 9439.1004 | 1919283.7467 | 15731.834 | 100% | 15731.834 | 0
|  | 4.2 |  | Fabrication of piping spools | 160464.7067 | 32627823.6934 | 267441.1778 | 100% | 267441.1778 | 0
|  | 4.3 |  | NDT | 18878.2008 | 3838567.4933 | 31463.668 | 100% | 31463.668 | 0
|  | 5 |  | Installation/ Commissioning |  |  | 0 |  | 0 | 0
|  | 5.1 |  | Advance tie-in | 44945.73 | 9138965.1094 | 74909.5501 | 90% | 67418.5951 | 7490.955
|  | 5.2 |  | Pre-drill installation | 104873.3701 | 21324251.922 | 174788.9502 | 90% | 157310.0552 | 17478.895
|  | 5.3 |  | Hook-up | 119855.2801 | 24370573.6251 | 199758.8002 | 90% | 179782.9202 | 19975.88
|  | 5.4 |  | Commissioning | 29963.82 | 6092643.4063 | 49939.7001 | 90% | 44945.73 | 4993.97
|  | HOOKUP SCOPE DPA SUB-TOTAL |  |  | 1314680.6347 | 283003636.4811 | 2242561.41 |  | 2184830.8798 | 57730.5302
|  | B. OPTIONAL SCOPE DPA | [6 empty] | 0
|  | 1 |  | Logistics (Land & Offshore) |  |  |  | 0% | 0 | 0
|  |  |  | Marine Logistics |  |  |  | 0% | 0 | 0
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 days for predrill, 6 days for precomissioning/wellhead tie-in) | 224190.6264 | 45585427.368 | 373651.044 | 0% |  | 0
|  |  |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System).)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 246328.2907 | 50086752.4376 | 410547.1511 | 0% |  | 0
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 0 | 0 | 0 | 0% |  | 0
|  |  |  | Land Logistics | 0 | 0 | 0 | 0% |  | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 days for material movement) | 572.8 | 137472 | 1023.5279 | 0% |  | 0
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) | 859.2 | 206208 | 1535.2918 | 0% |  | 0
|  | 2 |  | Habitat |  |  | 0 | 0% | 0 | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5705.088 | 1160034.56 | 9508.48 | 100% | 9508.48 | 9508.48
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 | 0% | 0 | 0
|  |  |  | Instruments/valves on spare flowlines | 278191.6471 | 56565634.9144 | 463652.7452 |  | 0 | 463652.7452
|  | OPTIONAL SCOPE DPA SUB-TOTAL |  |  | 755847.6522 | 153741529.28 | 1259918.24 |  | 9508.48 | 473161.2252
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | 1 |  | Removal of Boat Catcher & Crane | 916214.1908 | 214678934.5661 | 1620079.55 | 100% | 1620079.55 | 0
|  | 2 |  | Re-installation of Boat Catcher & Crane | 182595.3074 | 39707328.5839 | 312783.27 | 0% | 0 | 312783.27
|  | BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE SUB-TOTAL |  |  | 1098809.4982 | 254386263.15 | 1932862.82 |  | 1620079.55 | 312783.27
|  | DPA BASE SCOPE TOTAL |  |  | 3169337.785 | 691131428.9112 | 5435342.47 |  | 3814418.9098 | 843675.0254
|  | A.HOOKUP SCOPE DPJ | [6 empty] | 0
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 7670312.4168 | 25148.5653 | 80% | 20118.8522 | 5029.7131 | 51185.05
|  | 1.2 |  | Onshore demobilisation | 0 | 1811461.6306 | 5939.2185 | 80% | 4751.3748 | 1187.8437
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 10186029.7101 | 33396.8187 | 80% | 26717.455 | 6679.3637
|  | 1.4 |  | Offshore demobilisation | 0 | 4067309.4084 | 13335.4407 | 80% | 10668.3525 | 2667.0881
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 19329602.9953 | 63375.7475 | 80% | 50700.598 | 12675.1495
|  | 2 |  | Project Management | 34888.89 | 7117333.56 | 58224.4099 | 80% | 46579.5279 | 11644.882
|  | 3 |  | Procurement |  |  | 0 |  | 0 | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 192891.949 | 39349895.6653 | 321908.0003 | 100% | 321908.0003 | 0
|  |  |  | Piping & Accessories (Deliver) | 192891.949 | 39349895.6653 | 321908.0003 | 100% | 321908.0003 | 0
|  | 3.2 |  | Instrument (FOB) | 521677.8075 | 64881676.1177 | 734404.6144 | 100% | 734404.6144 | 0
|  |  |  | Instrument (Deliver) | 521677.8075 | 64881676.1177 | 734404.6144 | 100% | 734404.6144 | 0
|  | 3.3 |  | Civil/Structural | 5281.1622 | 1073836.3107 | 8801.937 | 100% | 8801.937 | 0
|  | 3.4 |  | Mechanical/HVAC | 2136.186 | 930800 | 5187.9893 | 100% | 5187.9893 | 0
|  | 3.5 |  | Electrical |  |  | 0 | 100% | 0 | 0
|  | 3.6 |  | Painting | 5460.8939 | 1110381.75 | 9101.4898 | 100% | 9101.4898 | 0
|  | 4 |  | Onshore Fabrication |  |  | 0 |  | 0 | 0
|  | 4.1 |  | Production of shop drawing | 18878.2008 | 3838567.4933 | 31463.668 | 100% | 31463.668 | 0
|  | 4.2 |  | Fabrication of piping spools | 320929.4134 | 65255647.3868 | 534882.3556 | 100% | 534882.3556 | 0
|  | 4.3 |  | NDT | 37756.4016 | 7677134.9867 | 62927.336 | 100% | 62927.336 | 0
|  | 5 |  | Installation/ Commissioning |  |  | 0 |  | 0 | 0
|  | 5.1 |  | Advance tie-in | 76570.9033 | 15569417.0026 | 127618.1722 | 85% | 108475.4463 | 19142.7258
|  | 5.2 |  | Pre-drill installation | 178665.441 | 36328639.6728 | 297775.735 | 85% | 253109.3748 | 44666.3603
|  | 5.3 |  | Hook-up | 204189.0754 | 41518445.3403 | 340315.1257 | 85% | 289267.8569 | 51047.2689
|  | 5.4 |  | Commissioning | 51047.2689 | 10379611.3351 | 85078.7814 | 85% | 72316.9642 | 12761.8172
|  | HOOKUP SCOPE DPJ SUB-TOTAL |  |  | 2364943.3493 | 442327674.5654 | 3815198.02 |  | 3647695.8077 | 167502.2123
B. OPTIONAL SCOPE DPJ
|  | 1 |  | Logistics (Land & Offshore)
Marine Logistics
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 for predrill, 6 days for precomissioning/wellhead tie-in) | 224190.6264 | 45585427.368 | 373651.044
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 0 | 0 | 0
|  |  |  | Provision of Crewboat (Hookup of Last Well post Rigmove)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 410547.1511 | 83477920.7293 | 684245.2519
|  |  |  | Land Logistics | 0 | 0 | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 for material movement) | 572.8 | 137472 | 1023.5279
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) | 859.2 | 206208 | 1535.2918
0
|  | 3 |  | Habitat |  |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5705.088 | 1160034.56 | 9508.48 | 100% | 9508.48 | 9507.48
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 |  |  | 0
|  |  |  | Instruments/valves on spare flowlines | 296948.4027 | 60379508.5427 | 494914.0044 | 0% |  | 494914.0044
|  | OPTIONAL SCOPE DPJ SUB-TOTAL |  |  | 938823.2682 | 190946571.2 | 1564877.6 |  | 9508.48 | 504421.4844
|  | DPJ BASE SCOPE TOTAL |  |  | 3303766.6175 | 633274245.7654 | 5380075.62 |  | 3657204.2877 | 671923.6967
|  | TOTAL BASE SCOPE |  |  | 6473104.4025 | 1324405674.6766 | 10815418.09 |  | 7471623.1975 | 1515598.7222
| OPTIONAL SCOPE | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPA | [6 empty] | 0
|  | 1 |  | DPA - MARINE LOGISTICS |  |  |  |  | 0
|  | 1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPA WELL HOOKUP) |  |  |  |  | 0
|  | 1.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days. | 310875.12 | 63211274.4 | 518125.2
|  | 1.1.4 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 145200 | 29524000 | 242000
|  | 1.1.5 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 477000 | 96990000 | 795000
|  | 1.1.6 |  | Provision of SEWOP Support Vessel | 180000 | 36600000 | 300000
|  | 1.1.7 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 180000 | 36600000 | 300000
|  | 1.1.8 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 72000 | 14640000 | 120000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1365075.12 | 277565274.4 | 2275125.2 |  | 0 | 0
|  | 1.2 |  | Boat Catcher/Crane Removal & Debris Survey (ALL DPA WELL HOOKUP) |  |  |  |  | 0
|  | 1.2.1 |  | Provision of DP2 PSV boat – For Medevac/ERP –(Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (In addition to Contractor Crew, allow for 3 Diving crew,6NOV Crew, 5 SPDC) & Debris Survey | 362687.64 | 73746486.8 | 604479.4
|  | 1.2.5 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 556500 | 113155000 | 927500
|  | 1.2.5 |  | Provision of SEWOP Support Vessel | 210000 | 42700000 | 350000
|  | 1.2.6 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 210000 | 42700000 | 350000
|  | 1.2.5 |  | Provision of a Diving Spread comprising: | 0 | 0 | 0
|  | 1.2.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 84000 | 17080000 | 140000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1523508.84 | 309780130.8 | 2539181.4 |  | 0 | 0
|  | 1.3 |  | DPA Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 1.3.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days. | 227975.088 | 46354934.56 | 379958.48 |  | 0
|  |  |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 145200 | 29524000 | 242000 |  | 0
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 349800 | 71126000 | 583000 |  | 0
|  | 1.3.4 |  | Provision of SEWOP Support Vessel | 132000 | 26840000 | 220000 |  | 0
|  | 1.3.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 132000 | 26840000 | 220000 |  | 0
|  | 1.3.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 52800 | 10736000 | 88000 |  | 0
|  |  |  | Sub-total (With Class 230 SEWOP) | 1039775.088 | 211420934.56 | 1732958.48 |  | 0 | 0
|  | 1.4 |  | Boat Catcher Reinstallation |  |  |  |  | 0
|  | 1.4.1 |  | Provision of DP2 PSV boat for Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position | 186525.072 | 37926764.64 | 310875.12 |  | 0 | 310875.12
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 286200 | 58194000 | 477000 |  | 0 | 477000
|  | 1.4.3 |  | Provision of SEWOP Support Vessel | 108000 | 21960000 | 180000 |  | 0 | 180000
|  | 1.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 108000 | 21960000 | 180000 |  | 0 | 180000
|  | 1.4.5 |  | Provision of a Diving Spread comprising: | 0 | 0 | 0 |  | 0 | 0
|  | 1.4.6.1 |  | Two LARS systems (for working diver and standby diver resp.) | 10318.752 | 2098146.24 | 17197.92 |  | 0 | 17197.92
|  | 1.4.6.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10318.752 | 2098146.24 | 17197.92 |  | 0 | 17197.92
|  | 1.4.6.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10318.752 | 2098146.24 | 17197.92 |  | 0 | 17197.92
|  | 1.4.6.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10318.752 | 2098146.24 | 17197.92 |  | 0 | 17197.92
|  | 1.4.6.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10318.752 | 2098146.24 | 17197.92 |  | 0 | 17197.92
|  | 1.4.7 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 43200 | 8784000 | 72000 |  | 0 | 72000
|  |  |  | Sub-total (With Class 230 SEWOP) | 783518.832 | 159315495.84 | 1305864.72 |  | 0 | 1305864.72
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPA TOTAL |  |  | 4711877.88 | 958081835.6 | 7853129.8 | 0% | 0 | 1305864.72
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPJ | [6 empty] | 0
|  | 3.1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPJ WELL HOOKUP) |  |  |  |  | 0
|  | 3.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 310875.12 | 63211274.4 | 518125.2 |  | 0
|  | 3.1.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 200 SEWOP with a crane capacity as 5tons@20 m radius Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 128400 | 26108000 | 214000 |  | 0
|  | 3.1.3 |  | Provision of Class 200 SEWOP with a crane capacity as 5tons@20 m radius. Crane must be manriding certified. | 417600 | 84912000 | 696000 |  | 0
|  | 3.1.4 |  | Provision of SEWOP Support Vessel | 180000 | 36600000 | 300000 |  | 0
|  | 3.1.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 180000 | 36600000 | 300000 |  | 0
|  | 3.1.6 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 72000 | 14640000 | 120000 |  | 0
|  |  |  | Sub-total | 1288875.12 | 262071274.4 | 2148125.2 |  | 0
|  | 3.2 |  | DPJ Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 3.2.1 |  | Provision of DP2 PSV boat - (option to MV Bello) – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 227975.088 | 46354934.56 | 379958.48 |  | 0
|  | 3.2.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 200 SEWOP with a crane capacity as 5tons@20 m radius. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 128400 | 26108000 | 214000 |  | 0
|  | 3.2.3 |  | Provision of Class 200 SEWOP with a crane capacity as 5tons@20 m radius for both boat catcher and crane dismantling . Crane must be manriding certified. | 306240 | 62268800 | 510400 |  | 0
|  | 3.2.4 |  | Provision of SEWOP Support Vessel | 132000 | 26840000 | 220000 |  | 0
|  | 3.2.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 132000 | 26840000 | 220000 |  | 0
|  | 3.2.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 52800 | 10736000 | 88000 |  | 0
|  |  |  | Sub-total | 979415.088 | 199147734.56 | 1632358.48 |  | 0
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPJ |  |  | 2268290.208 | 461219008.96 | 3780483.68 |  | 0 | 0
|  | TOTAL ADDITIONAL VESSELS |  |  | 6980168.088 | 1419300844.56 | 11633613.48 |  | 0 | 1305864.72
0
|  |  |  | Crane Services |  |  |  |  | 0
|  | 1 |  | Crane removal |  |  |  |  | 0 | 0
|  | 2 |  | Reinstallation of crane | 355816.4344 | 10408657.415 | 389943.18 | 50% | 194971.59 | 194971.59
|  |  |  | Telecoms Relocation |  |  |  |  | 0 | 0
|  | 1 |  | Mobilisation and 50% relocation works | 59869.6069 | 6086743.3681 | 79826.1425 | 100% | 79826.1425 | 0
|  | 2 |  | Complete telecoms works 100% | 59869.6069 | 6086743.3681 | 79826.1425 | 100% | 79826.1425 | 0
|  |  |  | Instrumentation (Invesys) |  |  |  |  | 0 | 0
|  | 1 |  | 50% Instrumentation works | 205548.054 | 41794770.98 | 342580.09 | 20% | 68516.018 | 274064.072
|  | 2 |  | Complete Instrumentation works | 205548.054 | 41794770.98 | 342580.09 | 20% | 68516.018 | 274064.072
|  |  |  | Gas Lift Modification |  |  |  |  | 0 | 0
|  | 1 |  | Project Management | 77.538 | 15817.745 | 129.3994 | 100% | 129.3994 | 0
|  | 2 |  | Procurement | 1300.6952 | 0 | 1300.6952 |  | 0 | 1300.6952
|  | 3 |  | Onshore Fabrication | 1506.9909 | 306421.4925 | 2511.6516 |  | 0 | 2511.6516
|  | 4 |  | Installation/Commissioning | 4209.0261 | 564014.4476 | 6058.2538 |  | 0 | 6058.2538
|  | CRANE SERVICES TELE COM GASLIFT TOTAL |  |  | 893746.0064 | 107057939.7964 | 1244755.6451 |  | 491785.3105 | 752970.3346
|  | TOTAL OPTIONAL SCOPE |  |  | 7873914.0944 | 1526358784.3564 | 12878369.1251 |  | 491785.3105 | 2058835.0546
DORMALONG | BASE SCOPE | A.HOOKUP SCOPE DPB | [6 empty] | 0
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0 | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 6366052.1022 | 20872.302 | 10% | 20872.302 | 7.2466e-06
|  | 1.2 |  | Onshore demobilisation | 0 | 1503440.6025 | 4929.3135 | 10% | 2453.39 | 2475.9235
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 8453996.6986 | 27718.022 | 10% | 2771.8022 | 24946.2198 | 23325.692
|  | 1.4 |  | Offshore demobilisation | 0 | 3375703.9091 | 11067.8817 | 10% | 1106.7882 | 9961.0935
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 16042796.3161 | 52599.3322 | 10% | 5259.9332 | 47339.399
|  | 2 |  | Project Management | 26177.0838 | 5340125.1038 | 43685.6907 | 2% | 8721.13 | 34964.5607
|  | 3 |  | Procurement | 0 | 0 | 0 |  | 0 | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 81214.7716 | 16513670.2254 | 135357.9527 |  | 155367.301 | 0 | 329429.2006
|  |  |  | Piping & Accessories (Deliver) | 81214.7716 | 16513670.2254 | 135357.9527 |  | 135110.44 | 0
|  | 3.2 |  | Instrument (FOB) | 202329.0868 | 41140247.6511 | 337215.1447 |  | 33659.85 | 303555.2947
|  |  |  | Instrument (Deliver) | 202329.0868 | 41140247.6511 | 337215.1447 |  |  | 337215.1447
|  | 3.3 |  | Civil/Structural | 1054.3317 | 214380.7844 | 1757.2195 |  | 1757.2195 | 0
|  | 3.4 |  | Mechanical/HVAC | 6728.5847 | 1368145.5548 | 11214.3078 |  | 0 | 11214.3078
|  | 3.5 |  | Electrical | 15365.6501 | 3124348.848 | 25609.4168 |  | 0 | 25609.4168
|  | 3.6 |  | Painting | 2360.6065 | 479989.9924 | 3934.3442 |  | 3534.39 | 399.9542
|  | 4 |  | Onshore Fabrication | 0 | 0 | 0 |  | 0 | 0
|  | 4.1 |  | Production of shop drawing | 12005.6099 | 2441140.6811 | 20009.3498 |  | 0 | 20009.3498
|  | 4.2 |  | Fabrication of piping spools | 204095.3684 | 41499391.5793 | 340158.9474 |  | 339536.93 | 622.0174 | 379482.45
|  | 4.3 |  | NDT | 24011.2198 | 4882281.3623 | 40018.6997 |  | 39945.52 | 73.1797
|  | 5 |  | Installation/ Commissioning | 0 | 0 |  |  | 0 | 0
|  | 5.1 |  | Advance tie-in | 47698.0018 | 9698593.7044 | 79496.6697 |  | 0 | 79496.6697
|  | 5.2 |  | Pre-drill installation | 111295.3376 | 22630051.977 | 185492.2293 |  | 0 | 185492.2293
|  | 5.3 |  | Hook-up | 127194.6715 | 25862916.5452 | 211991.1192 |  | 0 | 211991.1192
|  | 5.4 |  | Commissioning | 31798.6679 | 6465729.1363 | 52997.7798 |  | 0 | 52997.7798
|  | HOOKUP SCOPE DPB SUB-TOTAL |  |  | 1176872.8507 | 275056920.6507 | 2078698.82 |  | 750096.9961 | 1348363.6596
|  | B. OPTIONAL SCOPE DPB | [6 empty] | 0
|  | 1 |  | Logistics (Land & Offshore) |  |  |  |  | 0
|  |  |  | Marine Logistics | 217198.048 | 44163603.1002 | 361996.7467 |  | 0 | 361996.7467
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 for predrill, 6 days for precomissioning/wellhead tie-in) | 0 | 0 | 0 |  | 0 | 0
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 397742.0523 | 80874217.301 | 662903.4205 |  | 0 | 662903.4205
|  |  |  | Provision of Crewboat (Hookup of Last Well post Rigmove)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 0 | 0 | 0 |  | 0 | 0
|  |  |  | Land Logistics | 554.9342 | 133184.2037 | 991.6037 |  | 0 | 991.6037
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 for material movement) | 832.4013 | 199776.3056 | 1487.4056 |  | 0 | 1487.4056
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) |  |  | 0 |  | 0 | 0
|  | 2 |  | Habitat |  |  | 0 |  | 0 | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5527.1445 | 1123852.7058 | 9211.9074 |  | 0 | 9211.9074
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 |  | 0 | 0
|  | 4 |  | Instruments/valves on spare flowlines | 287686.4857 | 58496252.0837 | 479477.4761 |  | 0 | 479477.4761
|  | OPTIONAL SCOPE DPB SUB-TOTAL |  |  | 909541.0659 | 184990885.7 | 1516068.56 |  | 0 | 1516068.56
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | 1 |  | Removal of Boat Catcher & Crane | 1319619.5832 | 12447957.924 | 1360432.56 |  | 0
|  | 2 |  | Re-installation of Boat Catcher & Crane | 1043395.492 | 226897658.1421 | 1787322.24 |  | 0 | 1787322.24
|  | BOAT CATCHER SUB-TOTAL |  |  | 2363015.0752 | 239345616.0661 | 3147754.8 |  | 0 | 1787322.24
|  | DORMANLONG DPA | [6 empty] | 0
|  | B. OPTIONAL SCOPE | [6 empty] | 0
|  | Logistics (Land & Offshore) | [6 empty] | 0
|  |  |  | Marine Logistics |  |  |  |  | 0
|  |  |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System).)(Max 16 days for precomissioning/wellhead tie-in) | 177531.168 | 36098004.16 | 295885.28 |  | 0
|  | SUB-TOTAL |  |  | 177531.168 | 36098004.16 | 295885.28 |  | 0 | 0
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | Re-installation of Boat Catcher & Crane | [6 empty] | 0
|  |  |  | Cost for DP-2 Construction & Diving Support Vessel | 330642.9598 | 67230735.1624 | 551071.5997 |  | 0
|  |  |  | Cost for diving services | 135647.3017 | 27581618.0192 | 226078.8362 |  | 0
|  |  |  | Cost of meals& bunks | 32112.4225 | 6529525.8984 | 53520.7041 |  | 0
|  | SUB-TOTAL |  |  | 498402.684 | 101341879.08 | 830671.14 |  | 0 | 0
|  | TOTAL |  |  | 5125362.8437 | 836833305.6568 | 7869078.6 |  | 750096.9961 | 4651754.4596
| OPTIONAL SCOPE | 2 |  | DPB - MARINE LOGISTICS |  |  |  |  | 0
|  | 2.1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPB WELL HOOKUP) |  |  |  |  | 0
|  | 2.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 248700.096 | 50569019.52 | 414500.16 |  | 0
|  | 2.1.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.1.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 381600 | 77592000 | 636000 |  | 0
|  | 2.1.4 |  | Provision of SEWOP Support Vessel | 144000 | 29280000 | 240000 |  | 0
|  | 2.1.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 144000 | 29280000 | 240000 |  | 0
|  | 2.1.6 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 57600 | 11712000 | 96000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 1134900.096 | 230763019.52 | 1891500.16 |  | 0 | 0
|  | 2.2 |  | Boat Catcher/Crane Removal & Debris Survey (ALL DPB WELL HOOKUP) |  |  |  |  | 0
|  | 2.2.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) & Debris Survey | 248700.096 | 50569019.52 | 414500.16 |  | 0
|  | 2.2.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.2.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 381600 | 77592000 | 636000 |  | 0
|  | 2.2.4 |  | Provision of SEWOP Support Vessel | 144000 | 29280000 | 240000 |  | 0
|  | 2.2.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 144000 | 29280000 | 240000 |  | 0
|  | 2.2.6 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0
|  | 2.2.6.1 |  | Two LARS systems (for working diver and standby diver resp.) | 27516.672 | 5595056.64 | 45861.12 |  | 0
|  | 2.2.6.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.7 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 57600 | 11712000 | 96000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 1217450.112 | 247548189.44 | 2029083.52 |  | 0
0
|  | 2.3 |  | DPB Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 2.3.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 196887.576 | 40033807.12 | 328145.96 |  | 0
|  | 2.3.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.3.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0
|  | 2.3.4 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0
|  | 2.3.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0
|  | 2.3.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 45600 | 9272000 | 76000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 931587.576 | 189422807.12 | 1552645.96 |  | 0
|  | 2.4 |  | Boat Catcher Reinstallation |  |  |  |  | 0
|  | 2.4.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) | 196887.576 | 40033807.12 | 328145.96 |  | 0
|  | 2.4.2 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0
|  | 2.4.3 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) |  |  | 0 |  | 0
|  | 2.4.3 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.5 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0
|  | 2.4.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 21784.032 | 4429419.84 | 36306.72 |  | 0
|  | 2.4.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 45600 | 9272000 | 76000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 837939.672 | 170381066.64 | 1396566.12 |  | 0
0
|  |  |  | Crane Services |  |  |  |  | 0
|  | 1 |  | Crane Services | 355816.4344 | 10408657.415 | 389943.18 |  | 0
|  |  |  | Gas Lift Modification |  |  |  |  | 0
|  | 1 |  | Project Management | 88.9406 | 18143.8875 | 148.4288 |  | 0
|  | 2 |  | Procurement | 1491.9742 |  | 1491.9742 |  | 0
|  | 3 |  | Onshore Fabrication | 1728.6076 | 351483.5446 | 2881.0127 |  | 0
|  | 4 |  | Installation/Commissioning | 4828.0014 | 646957.8737 | 6949.1748 |  | 0
|  | Sub-Total |  |  | 363953.9583 | 11425242.7208 | 401413.7705 |  | 0
0
|  | 2.4 |  | Boat Catcher Reinstallation (DPA) |  |  |  |  | 0
|  | 2.4.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) | 196887.576 | 40033807.12 | 328145.96 |  | 0 | 328145.96
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0 | 503500
|  | 2.4.3 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0 | 190000
|  | 2.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0 | 190000
|  | 2.4.5 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0 | 0
|  | 2.4.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 21784.032 | 4429419.84 | 36306.72 |  | 0 | 36306.72
|  | 2.4.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 45600 | 9272000 | 76000 |  | 0 | 76000
|  |  |  | Sub-total with SEWOP 200 | 837939.672 | 170381066.64 | 1396566.12 |  | 0 | 1396566.12
|  | TOTAL |  |  | 5323771.0863 | 1019921392.0808 | 8667775.6505 |  | 0 | 1396566.12
[7 empty] | 40230641.4655 |  | 8713505.5041 | 9622754.3563
0
Marine Logisitics | [6 empty] | 3826539.34 |  | 3826539.34
DED | [6 empty] | 632656.64 |  | 632656.64
Technical Support service/QA QC | [6 empty] | 641362.18 |  | 641362.18
OTHERS (Catering, Hotel,travels, logistics) | [6 empty] | 66811.42 |  | 66811.42
[9 empty] | 5167369.58 | 0
PMT/OTHERS | [8 empty] | 0
SALARIES | [6 empty] | 2038937.73 |  | 2038937.73
TP OVERHEAD | [6 empty] | 3187943.41 |  | 744596.97
OTHERS (Catering, Hotel,Aviation,Travels, Government Levies) | [6 empty] | 404408.71 |  | 404408.71
[9 empty] | 3187943.41 | 0
17068818.4941
7458630.5463
1254874.9578

## Summary (3)
EA FOD FACILITIES CONTRACT COST PERFORMANCE SUMMARY
CONTRACTOR | SCOPE | PLAT FORM | WORKSCOPE | CONTRACT | BUDGET (CONTRACT) per PLATFORM | EAC | VOWD ITD | VARIATION TO CONTRACT | VARIATION TO CONTRACT | VARIATION TO CONTRACT | VOWD | ESTIMATE TO COMPLETE (2020 LE) | ESTIMATE AT COMPLETION | OP19 | 2020 Potential Savings | TARGET SAVINGS | Remarks
0
|  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
SI | BASE SCOPE | DPA | Package 1 -Main Facilities Hook up (DPJ/DPA) | 10815418.09 | 5435342.47 | 10815418.09 | 3814418.9098 |  |  | 0 | 5576419.68 | 1515598.7222 | 7092018.4022 | 897684.4957 | -617914.2265 | 3723399.6878 | AF Budget $10.62mln AF Contract (Facilities hookup+Additional Vessel) DPA/DPJ $23.69mln Cost Saving result from the use of DP2 Vessel (MV Bello) and Crew Boat on the EA Field to be used/shared during the project execution with the EA Asset for emergency medivac and personnel movement respectively as against drawing from the AF Contract | Onshore Fabrication, predrills, post drills, Boatcatcher/Crane removal + Tel Mast relocation (DPA)
|  | DPJ |  |  | 5380075.62 |  | 3657204.2877 |  |  | 0 |  |  |  |  | 0
| MODIFICATION SCOPE | DA | Package 1 - Additional Vessels (DPJ/DPA) | 12878369.1251 | 7853129.8 | 12878369.13 | 0 |  |  | 0 | 2882226.64 | 2058835.0546 | 4941061.6946 | 6227331.9531 | 4168496.8985 | 7937307.4305 |  | Travel to Site, Spud & Pre-drill Offshore Logistics
|  | DPJ |  |  | 5025239.3251 |  | 491785.3105 | [7 empty] | 0
| VARIATION ORDER |  | Additional Flow Lines from DPB to DPA (SHALLOW GAS); Cables; omitted materials for EI installation: MCB Approved, Negotiation held with NAPIMs. |  |  | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 0 | 2900000 |  | 0 | -2900000 | VO for additional Flow Lines from DPB to DPA (SHALLOW GAS); Cables; omitted materials for EI installation: MCB Approved, Negotiation held with NAPIMs. | Additional Flow Lines from DPB to DPA (SHALLOW GAS); Cables; omitted materials for EI installation: MCB Approved, Negotiation held with NAPIMs.
|  |  | Marine Logisitics/Technical Support services | [6 empty] | 0 | 5382608.25 | 754439.46 | 6137047.71 |  | -754439.46 | -6137047.71 | Cost of deploying Vessels with the Coprate Marine team and Technical Support service | Marine Logisitics/Technical Support services
|  |  | Modification of EJA8/9/10 | [6 empty] | 0 | 0 | 200000 | 200000 |  | -200000 | -200000 | Additional scope for Maditification of EJA8/9/10 | Modification of EJA8/6/10
|  |  |  | 23693787.2151 |  |  |  | 2900000 | 2900000 | 2900000 | 16741254.57 | 4528873.2367 | 21270127.8067 | 7125016.4488 | 2596143.212 | 2423659.4083
DL | BASE SCOPE | DPB | Package 2 -Main Facilities Hook up (DPB)) | 7869078.6 | 6742522.18 | 7869078.6 | 750096.9961 |  | \ | 0 | 827000 | 4651754.4596 | 5478754.4596 | 7592992.1977 | 2941237.7381 | 2390324.1404 | AF Budget $10.62mln AF Contract (Facilities hookup+Additional Vessel) DPB $16.54mln $3.6Mln saving due to the fact that Frigg is drilling DPB, Boatcatcher/Crane will no longer be removed.
|  | DPA |  |  | 1126556.42 |  | 0 | [7 empty] | 0 |  |  | On shore Fabrication, predrills, post drills, Boatcatcher/Crane removal + Tel Mast relocation (DPA)
| MODIFICATION SCOPE | DPB | Package 2 -Main Facilities Hook up (DPB) | 8667775.6505 | 7271209.5305 | 8667775.65 | 0 |  |  | 0 | 0 | 1396566.12 | 1396566.12 | 8667775.6505 | 7271209.5305 | 7271209.5305
|  | DPA | Re-installation of Boat Catcher & Crane |  | 1396566.12 |  | 0 | [7 empty] | 0 |  |  | Travel to Site, Spud & Pre-drill Offshore Logistics
|  | DPB | If Frigg drills DPB, Boatcatcher/Crane will no longer be removed |  |  | -6000000 | [6 empty] | 0 |  | 0 | 700000 |  | Re-installation of Boat Catcher & Crane
| EMERGING VO (To be reconciled) |  | Potential Reduction based on reduction from 5nos. To 3Nos. Wells (Reconcilliation ongoing with Dorman Long) | 0 |  | -700000 | 0 |  |  | 0 | 0 | -700000 | -700000 |  | 700000 |  | Potential Reduction based on reduction from 5nos. To 3Nos. Wells (Reconcilliation ongoing with Dorman Long) | If Frigg drills DPB, Boatcatcher/Crane will no longer be removed
|  |  | Marine Logisitics/Technical Support services | 0 | [5 empty] | 0 | 0 | 4023677.12 | 4023677.12 |  | -4023677.12 | -4023677.12 | Forecasted Cost f deploying Coparated Marine Vessel+Technical Support | Potential Reduction based on reduction from 5nos. To 3Nos. Wells (Reconcilliation ongoing with Dorman Long)
|  |  | Project management services | [10 empty] | 225701.5624 | 225701.5624
|  |  | Salaries | [10 empty] | 2038937.73 | 2038937.73
|  |  | OTHERS (Catering, Hotel,Aviation,Travels, Government Levies) | [10 empty] | 404408.71 | 404408.71
|  |  |  | 16536854.2505 |  |  |  | 0 |  | 0 | 827000 | 9371997.6996 | 10198997.6996 | 18929815.8505 | 9557818.1509 | 6337856.5509 |  | Marine Logisitics/Technical Support services
|  |  |  | 40230641.4655 |  |  |  | 2900000 |  | 2900000 | 17568254.57 | 13900870.9363 | 31469125.5063 | 26054832.2993 | 12153961.363 | 8761515.9592
Corporate Marine | Marine Logisitics | DPA/DPJ | Marine Logisitics |  |  | 4620982.0959 | 4620982.0959 |  |  |  | 4382111.4 | 4179596.4 | 8561707.8
Technical Support/Others | Technical Support/Others | DPA/DPB/DPJ | QA/QC Tech Support/others |  |  | 1000496.85 | 1000496.85 |  |  |  | 1000496.85 | 850000 | 1850496.85
DED | DED | DP A,DPB & DP J | Detail Engineering Design | 680000 | [6 empty] | 632656.64 | 0 | 632656.64
Marine/Technical Support Total |  |  |  | 680000 | 0 | 5621478.9459 | 5621478.9459 |  |  |  | 6015264.89 | 5029596.4 | 11044861.29
Grand Total |  |  |  | 17896854.2505 |  | 5621478.9459 | 5621478.9459 |  |  |  | 6842264.89 | 14401594.0996 | 21243858.9896
|  |  |  | VOWD | [6 empty] | ETC | 0.26
OTHERS
OTHERS | Marine Logisitics | DPA/DPJ | Marine Logisitics
| Marine Logisitics | DPB | Marine Logisitics
| Technical Support service/QA QC |  | Technical Support service/QA QC
| Catering, Hotel,travels, logistics |  | Catering, Hotel,travels, logistics
PMT JV line
PMT | SALARIES | #REF! | SALARIES
| TP OVERHEAD |  | TP OVERHEAD
| OTHERS (Catering, Hotel,Aviation,Travels, Government Levies) |  | OTHERS (Catering, Hotel,Aviation,Travels, Government Levies)
Total ITD VOWD
|  |  | SI Base Scope | 8476419.68 | [6 empty] | 1515598.7222
|  |  | DLE Base Scope | 827000 | [6 empty] | 4651754.4596
|  |  | Marine Logisitics | 4250648.058 | 4054208.508 | 8304856.566 | #REF! |  |  |  | 0
|  |  | DED | 421771.0933 | [6 empty] | 0
|  |  | QA/QC Tech Support/others | 1000496.85 | [6 empty] | 170000
|  |  |  | 14976335.6813 | 4054208.508 | 8304856.566 | #REF! |  |  |  | 6337353.1817
|  |  | SI Mod Scope | 2882226.64 | [6 empty] | 2058835.0546
|  |  | DLE Mod Scope | 0 | [6 empty] | 1396566.12
|  |  | Marine Logisitics | 131463.342 | [6 empty] | 4179596.4
|  |  | DED | 210885.5467 | [6 empty] | 0
|  |  | QA/QC Tech Support/others | 0 | [6 empty] | 680000
|  |  | EMERGING VO (To be reconciled) | 0 | [6 empty] | -700000
|  |  |  | 3224575.5287 | 8314997.5746 | 8314997.5746 | 8314997.5746 |  |  |  | 7614997.5746
|  |  | #REF! | [7 empty] | #REF!
|  |  |  | 18200911.21 | 12369206.0826 | 16619854.1406 | #REF! |  |  |  | #REF!

## Savings (hidden)
SI Contract
Contractor | Scope | M/S | PO Number | Description |  |  | Amt | % Progress | Marine VOWD |  | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
STEVE INTEGRATED | BASE SCOPE | A. HOOKUP SCOPE DPA |  |  | NGN | USD | FUSD
|  | 1 |  | Mobilisation / Demobilisation
|  | 1.1 |  | Onshore mobilisation | 0 | 7251375 | 23775 | 75%
|  | 1.2 |  | Onshore demobilisation | 0 | 1712523.15 | 5614.83 | 75%
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 9629688.75 | 31572.75 | 75%
|  | 1.4 |  | Offshore demobilisation | 0 | 3845160.9476 | 12607.0851 | 75%
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 18273858 | 59914.2885 | 75%
|  | 2 |  | Project Management | 13382.04 | 2729936.16 | 22332.6504 | 80%
|  | 3 |  | Procurement
|  | 3.1 |  | Piping & Accessories (FOB) | 102084.7142 | 20825250.8465 | 170364.2252 | 100%
|  |  |  | Piping & Accessories (Deliver) | 102084.7142 | 20825250.8465 | 170364.2252 | 100%
|  | 3.2 |  | Instrument (FOB) | 290182.4417 | 45461348.0024 | 439236.0418 | 100%
|  |  |  | Instrument (Deliver) | 290182.4417 | 45461348.0024 | 439236.0418 | 100%
|  | 3.3 |  | Civil/Structural | 1327.003 | 269823.9409 | 2211.6716 | 100%
|  | 3.4 |  | Mechanical/HVAC | 5722.093 | 2559700 | 14114.552 | 100%
|  | 3.5 |  | Electrical | 18323.872 | 4242138.8385 | 32232.5239 | 100%
|  | 3.6 |  | Painting | 2971.1066 | 604125 | 4951.8443 | 100%
|  | 4 |  | Onshore Fabrication |  |  | 0
|  | 4.1 |  | Production of shop drawing | 9439.1004 | 1919283.7467 | 15731.834 | 100%
|  | 4.2 |  | Fabrication of piping spools | 160464.7067 | 32627823.6934 | 267441.1778 | 100%
|  | 4.3 |  | NDT | 18878.2008 | 3838567.4933 | 31463.668 | 100%
|  | 5 |  | Installation/ Commissioning |  |  | 0
|  | 5.1 |  | Advance tie-in | 44945.73 | 9138965.1094 | 74909.5501 | 85%
|  | 5.2 |  | Pre-drill installation | 104873.3701 | 21324251.922 | 174788.9502 | 85%
|  | 5.3 |  | Hook-up | 119855.2801 | 24370573.6251 | 199758.8002 | 85%
|  | 5.4 |  | Commissioning | 29963.82 | 6092643.4063 | 49939.7001 | 85%
|  | HOOKUP SCOPE DPA SUB-TOTAL |  |  | 1314680.6347 | 283003636.4811 | 2242561.41 |  | 0 | 0
|  | B. OPTIONAL SCOPE DPA | [6 empty] | 0
|  | 1 |  | Logistics (Land & Offshore) |  |  |  |  | 0
|  |  |  | Marine Logistics |  |  |  |  | 0
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 days for predrill, 6 days for precomissioning/wellhead tie-in) | 224190.6264 | 45585427.368 | 373651.044 | 70% | 261555.7308 | 373651.044
|  |  |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System).)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 246328.2907 | 50086752.4376 | 410547.1511 | 70% | 287383.0058 | 410547.1511
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 0 | 0 | 0 | 70% | 0 | 0
|  |  |  | Land Logistics | 0 | 0 | 0 | 70% | 0 | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 days for material movement) | 572.8 | 137472 | 1023.5279 | 70% | 716.4695 | 1023.5279
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) | 859.2 | 206208 | 1535.2918 | 70% | 1074.7043 | 1535.2918
|  | 2 |  | Habitat |  |  | 0 |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5705.088 | 1160034.56 | 9508.48 | 100% | 9508.48 | 9508.48
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 |  | 0
|  |  |  | Instruments/valves on spare flowlines | 278191.6471 | 56565634.9144 | 463652.7452 | 0% | 0 | 463652.7452
|  | OPTIONAL SCOPE DPA SUB-TOTAL |  |  | 755847.6522 | 153741529.28 | 1259918.24 |  | 560238.3904 | 1259918.24
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | 1 |  | Removal of Boat Catcher & Crane | 916214.1908 | 214678934.5661 | 1620079.55 | 100%
|  | 2 |  | Re-installation of Boat Catcher & Crane | 182595.3074 | 39707328.5839 | 312783.27 | 0% | 0
|  | BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE SUB-TOTAL |  |  | 1098809.4982 | 254386263.15 | 1932862.82 |  | 0 | 0
|  | DPA BASE SCOPE TOTAL |  |  | 3169337.785 | 691131428.9112 | 5435342.47 |  | 560238.3904 | 1259918.24
|  | A.HOOKUP SCOPE DPJ | [6 empty] | 0
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 7670312.4168 | 25148.5653 | 60%
|  | 1.2 |  | Onshore demobilisation | 0 | 1811461.6306 | 5939.2185 | 60%
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 10186029.7101 | 33396.8187 | 60%
|  | 1.4 |  | Offshore demobilisation | 0 | 4067309.4084 | 13335.4407 | 60%
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 19329602.9953 | 63375.7475 | 60%
|  | 2 |  | Project Management | 34888.89 | 7117333.56 | 58224.4099 | 60%
|  | 3 |  | Procurement |  |  | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 192891.949 | 39349895.6653 | 321908.0003 | 100%
|  |  |  | Piping & Accessories (Deliver) | 192891.949 | 39349895.6653 | 321908.0003 | 100%
|  | 3.2 |  | Instrument (FOB) | 521677.8075 | 64881676.1177 | 734404.6144 | 100%
|  |  |  | Instrument (Deliver) | 521677.8075 | 64881676.1177 | 734404.6144 | 100%
|  | 3.3 |  | Civil/Structural | 5281.1622 | 1073836.3107 | 8801.937 | 100%
|  | 3.4 |  | Mechanical/HVAC | 2136.186 | 930800 | 5187.9893 | 100%
|  | 3.5 |  | Electrical |  |  | 0 | 100%
|  | 3.6 |  | Painting | 5460.8939 | 1110381.75 | 9101.4898 | 100%
|  | 4 |  | Onshore Fabrication |  |  | 0
|  | 4.1 |  | Production of shop drawing | 18878.2008 | 3838567.4933 | 31463.668 | 100%
|  | 4.2 |  | Fabrication of piping spools | 320929.4134 | 65255647.3868 | 534882.3556 | 100%
|  | 4.3 |  | NDT | 37756.4016 | 7677134.9867 | 62927.336 | 100%
|  | 5 |  | Installation/ Commissioning |  |  | 0
|  | 5.1 |  | Advance tie-in | 76570.9033 | 15569417.0026 | 127618.1722 | 70%
|  | 5.2 |  | Pre-drill installation | 178665.441 | 36328639.6728 | 297775.735 | 70%
|  | 5.3 |  | Hook-up | 204189.0754 | 41518445.3403 | 340315.1257 | 70%
|  | 5.4 |  | Commissioning | 51047.2689 | 10379611.3351 | 85078.7814 | 70%
|  | HOOKUP SCOPE DPJ SUB-TOTAL |  |  | 2364943.3493 | 442327674.5654 | 3815198.02 |  | 0 | 0
B. OPTIONAL SCOPE DPJ
|  | 1 |  | Logistics (Land & Offshore)
Marine Logistics
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 for predrill, 6 days for precomissioning/wellhead tie-in) | 224190.6264 | 45585427.368 | 373651.044 | 70% | 261555.7308 | 373651.044
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 0 | 0 | 0 |  | 0 | 0
|  |  |  | Provision of Crewboat (Hookup of Last Well post Rigmove)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 410547.1511 | 83477920.7293 | 684245.2519 | 70% | 478971.6763 | 684245.2519
|  |  |  | Land Logistics | 0 | 0 | 0 |  | 0 | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 for material movement) | 572.8 | 137472 | 1023.5279 | 70% | 716.4695 | 1023.5279
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) | 859.2 | 206208 | 1535.2918 | 70% | 1074.7043 | 1535.2918
[7 empty] | 0 |  | 0 | 0
|  | 3 |  | Habitat |  |  | 0 |  | 0 | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5705.088 | 1160034.56 | 9508.48 | 100% | 9508.48 | 9508.48
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0
|  |  |  | Instruments/valves on spare flowlines | 296948.4027 | 60379508.5427 | 494914.0044 | 0% | 0 | 494914.0044
|  | OPTIONAL SCOPE DPJ SUB-TOTAL |  |  | 938823.2682 | 190946571.2 | 1564877.6 |  | 751827.0609 | 1564877.6
|  | DPJ BASE SCOPE TOTAL |  |  | 3303766.6175 | 633274245.7654 | 5380075.62 |  | 751827.0609 | 1564877.6
|  | TOTAL BASE SCOPE |  |  | 6473104.4025 | 1324405674.6766 | 10815418.09 |  | 1312065.4512 | 2824795.84
| OPTIONAL SCOPE | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPA | [6 empty] | 0
|  | 1 |  | DPA - MARINE LOGISTICS |  |  |  |  | 0
|  | 1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPA WELL HOOKUP) |  |  |  |  | 0
|  | 1.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days. | 310875.12 | 63211274.4 | 518125.2 | 100% | 518125.2 | 518125.2
|  | 1.1.4 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 145200 | 29524000 | 242000 | 100% | 242000 | 242000
|  | 1.1.5 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 477000 | 96990000 | 795000 | 100% | 795000 | 795000
|  | 1.1.6 |  | Provision of SEWOP Support Vessel | 180000 | 36600000 | 300000 | 100% | 300000 | 300000
|  | 1.1.7 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 180000 | 36600000 | 300000 | 100% | 300000 | 300000
|  | 1.1.8 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 72000 | 14640000 | 120000 | 100% | 120000 | 120000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1365075.12 | 277565274.4 | 2275125.2 |  | 2275125.2 | 2275125.2
|  | 1.2 |  | Boat Catcher/Crane Removal & Debris Survey (ALL DPA WELL HOOKUP) |  |  |  |  | 0 | 0
|  | 1.2.1 |  | Provision of DP2 PSV boat – For Medevac/ERP –(Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (In addition to Contractor Crew, allow for 3 Diving crew,6NOV Crew, 5 SPDC) & Debris Survey | 362687.64 | 73746486.8 | 604479.4 | 100% | 604479.4 | 604479.4
|  | 1.2.5 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 556500 | 113155000 | 927500 | 100% | 927500 | 927500
|  | 1.2.5 |  | Provision of SEWOP Support Vessel | 210000 | 42700000 | 350000 | 100% | 350000 | 350000
|  | 1.2.6 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 210000 | 42700000 | 350000 | 100% | 350000 | 350000
|  | 1.2.5 |  | Provision of a Diving Spread comprising: | 0 | 0 | 0 | 100% | 0 | 0
|  | 1.2.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 20064.24 | 4079728.8 | 33440.4 | 100% | 33440.4 | 33440.4
|  | 1.2.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 20064.24 | 4079728.8 | 33440.4 | 100% | 33440.4 | 33440.4
|  | 1.2.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 20064.24 | 4079728.8 | 33440.4 | 100% | 33440.4 | 33440.4
|  | 1.2.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 20064.24 | 4079728.8 | 33440.4 | 100% | 33440.4 | 33440.4
|  | 1.2.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 20064.24 | 4079728.8 | 33440.4 | 100% | 33440.4 | 33440.4
|  | 1.2.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 84000 | 17080000 | 140000 | 100% | 140000 | 140000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1523508.84 | 309780130.8 | 2539181.4 |  | 2539181.4 | 2539181.4
|  | 1.3 |  | DPA Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 1.3.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days. | 227975.088 | 46354934.56 | 379958.48 | 0% | 0 | 379958.48
|  |  |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 145200 | 29524000 | 242000 | 0% | 0 | 242000
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 349800 | 71126000 | 583000 | 0% | 0 | 583000
|  | 1.3.4 |  | Provision of SEWOP Support Vessel | 132000 | 26840000 | 220000 | 0% | 0 | 220000
|  | 1.3.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 132000 | 26840000 | 220000 | 0% | 0 | 220000
|  | 1.3.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 52800 | 10736000 | 88000 | 0% | 0 | 88000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1039775.088 | 211420934.56 | 1732958.48 |  | 0 | 1732958.48
|  | 1.4 |  | Boat Catcher Reinstallation |  |  |  |  | 0
|  | 1.4.1 |  | Provision of DP2 PSV boat for Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position | 186525.072 | 37926764.64 | 310875.12 | 0% | 0 | 310875.12
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 286200 | 58194000 | 477000 | 0% | 0 | 477000
|  | 1.4.3 |  | Provision of SEWOP Support Vessel | 108000 | 21960000 | 180000 | 0% | 0 | 180000
|  | 1.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 108000 | 21960000 | 180000 | 0% | 0 | 180000
|  | 1.4.5 |  | Provision of a Diving Spread comprising: | 0 | 0 | 0 | 0% | 0 | 0
|  | 1.4.6.1 |  | Two LARS systems (for working diver and standby diver resp.) | 10318.752 | 2098146.24 | 17197.92 | 0% | 0 | 17197.92
|  | 1.4.6.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10318.752 | 2098146.24 | 17197.92 | 0% | 0 | 17197.92
|  | 1.4.6.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10318.752 | 2098146.24 | 17197.92 | 0% | 0 | 17197.92
|  | 1.4.6.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10318.752 | 2098146.24 | 17197.92 | 0% | 0 | 17197.92
|  | 1.4.6.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10318.752 | 2098146.24 | 17197.92 | 0% | 0 | 17197.92
|  | 1.4.7 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 43200 | 8784000 | 72000 | 0% | 0 | 72000
|  |  |  | Sub-total (With Class 230 SEWOP) | 783518.832 | 159315495.84 | 1305864.72 |  | 0 | 1305864.72
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPA TOTAL |  |  | 4711877.88 | 958081835.6 | 7853129.8 | 0% | 4814306.6 | 7853129.8
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPJ | [6 empty] | 0
|  | 3.1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPJ WELL HOOKUP) |  |  |  |  | 0
|  | 3.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 310875.12 | 63211274.4 | 518125.2 | 100% | 518125.2 | 518125.2
|  | 3.1.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 200 SEWOP with a crane capacity as 5tons@20 m radius Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 128400 | 26108000 | 214000 | 100% | 214000 | 214000
|  | 3.1.3 |  | Provision of Class 200 SEWOP with a crane capacity as 5tons@20 m radius. Crane must be manriding certified. | 417600 | 84912000 | 696000 | 100% | 696000 | 696000
|  | 3.1.4 |  | Provision of SEWOP Support Vessel | 180000 | 36600000 | 300000 | 100% | 300000 | 300000
|  | 3.1.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 180000 | 36600000 | 300000 | 100% | 300000 | 300000
|  | 3.1.6 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 72000 | 14640000 | 120000 | 100% | 120000 | 120000
|  |  |  | Sub-total | 1288875.12 | 262071274.4 | 2148125.2 |  | 2148125.2 | 2148125.2
|  | 3.2 |  | DPJ Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 3.2.1 |  | Provision of DP2 PSV boat - (option to MV Bello) – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 227975.088 | 46354934.56 | 379958.48 | 0% | 0 | 379958.48
|  | 3.2.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 200 SEWOP with a crane capacity as 5tons@20 m radius. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 128400 | 26108000 | 214000 | 0% | 0 | 214000
|  | 3.2.3 |  | Provision of Class 200 SEWOP with a crane capacity as 5tons@20 m radius for both boat catcher and crane dismantling . Crane must be manriding certified. | 306240 | 62268800 | 510400 | 0% | 0 | 510400
|  | 3.2.4 |  | Provision of SEWOP Support Vessel | 132000 | 26840000 | 220000 | 0% | 0 | 220000
|  | 3.2.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 132000 | 26840000 | 220000 | 0% | 0 | 220000
|  | 3.2.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 52800 | 10736000 | 88000 | 0% | 0 | 88000
|  |  |  | Sub-total | 979415.088 | 199147734.56 | 1632358.48 |  | 0 | 1632358.48
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPJ |  |  | 2268290.208 | 461219008.96 | 3780483.68 |  | 2148125.2 | 3780483.68
|  | TOTAL ADDITIONAL VESSELS |  |  | 6980168.088 | 1419300844.56 | 11633613.48 |  | 6962431.8 | 11633613.48
0
|  |  |  | Crane Services |  |  |  |  | 0
|  | 1 |  | Crane removal |  |  |  |  | 0
|  | 2 |  | Reinstallation of crane | 355816.4344 | 10408657.415 | 389943.18 | 50%
Telecoms Relocation
|  | 1 |  | Mobilisation and 50% relocation works | 59869.6069 | 6086743.3681 | 79826.1425 | 100%
|  | 2 |  | Complete telecoms works 100% | 59869.6069 | 6086743.3681 | 79826.1425 | 100%
Instrumentation (Invesys)
|  | 1 |  | 50% Instrumentation works | 205548.054 | 41794770.98 | 342580.09 | 20%
|  | 2 |  | Complete Instrumentation works | 205548.054 | 41794770.98 | 342580.09 | 20%
|  |  |  | Gas Lift Modification |  |  |  |  | 0
|  | 1 |  | Project Management | 77.538 | 15817.745 | 129.3994 |  | 0
|  | 2 |  | Procurement | 1300.6952 | 0 | 1300.6952 |  | 0
|  | 3 |  | Onshore Fabrication | 1506.9909 | 306421.4925 | 2511.6516 |  | 0
|  | 4 |  | Installation/Commissioning | 4209.0261 | 564014.4476 | 6058.2538 |  | 0
|  | CRANE SERVICES TELE COM GASLIFT TOTAL |  |  | 893746.0064 | 107057939.7964 | 1244755.6451 |  | 0 | 0
|  | TOTAL OPTIONAL SCOPE |  |  | 7873914.0944 | 1526358784.3564 | 12878369.1251 |  | 6962431.8 | 11633613.48
DORMALONG | BASE SCOPE | A.HOOKUP SCOPE DPB | [6 empty] | 0
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 6366052.1022 | 20872.302 | 10%
|  | 1.2 |  | Onshore demobilisation | 0 | 1503440.6025 | 4929.3135 | 10%
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 8453996.6986 | 27718.022 | 10%
|  | 1.4 |  | Offshore demobilisation | 0 | 3375703.9091 | 11067.8817 | 10%
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 16042796.3161 | 52599.3322 | 10%
|  | 2 |  | Project Management | 26177.0838 | 5340125.1038 | 43685.6907 | 2%
|  | 3 |  | Procurement | 0 | 0 | 0 |  | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 81214.7716 | 16513670.2254 | 135357.9527 |  | 0
|  |  |  | Piping & Accessories (Deliver) | 81214.7716 | 16513670.2254 | 135357.9527 |  | 0
|  | 3.2 |  | Instrument (FOB) | 202329.0868 | 41140247.6511 | 337215.1447 |  | 0
|  |  |  | Instrument (Deliver) | 202329.0868 | 41140247.6511 | 337215.1447 |  | 0
|  | 3.3 |  | Civil/Structural | 1054.3317 | 214380.7844 | 1757.2195 |  | 0
|  | 3.4 |  | Mechanical/HVAC | 6728.5847 | 1368145.5548 | 11214.3078 |  | 0
|  | 3.5 |  | Electrical | 15365.6501 | 3124348.848 | 25609.4168 |  | 0
|  | 3.6 |  | Painting | 2360.6065 | 479989.9924 | 3934.3442 |  | 0
|  | 4 |  | Onshore Fabrication | 0 | 0 | 0 |  | 0
|  | 4.1 |  | Production of shop drawing | 12005.6099 | 2441140.6811 | 20009.3498 |  | 0
|  | 4.2 |  | Fabrication of piping spools | 204095.3684 | 41499391.5793 | 340158.9474 |  | 0
|  | 4.3 |  | NDT | 24011.2198 | 4882281.3623 | 40018.6997 |  | 0
|  | 5 |  | Installation/ Commissioning | 0 | 0 |  |  | 0
|  | 5.1 |  | Advance tie-in | 47698.0018 | 9698593.7044 | 79496.6697 |  | 0
|  | 5.2 |  | Pre-drill installation | 111295.3376 | 22630051.977 | 185492.2293 |  | 0
|  | 5.3 |  | Hook-up | 127194.6715 | 25862916.5452 | 211991.1192 |  | 0
|  | 5.4 |  | Commissioning | 31798.6679 | 6465729.1363 | 52997.7798 |  | 0
|  | HOOKUP SCOPE DPB SUB-TOTAL |  |  | 1176872.8507 | 275056920.6507 | 2078698.82 |  | 0 | 0
|  | B. OPTIONAL SCOPE DPB | [6 empty] | 0
|  | 1 |  | Logistics (Land & Offshore) |  |  |  |  | 0
|  |  |  | Marine Logistics | 217198.048 | 44163603.1002 | 361996.7467 |  | 0
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 for predrill, 6 days for precomissioning/wellhead tie-in) | 0 | 0 | 0 |  | 0
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 397742.0523 | 80874217.301 | 662903.4205 |  | 0
|  |  |  | Provision of Crewboat (Hookup of Last Well post Rigmove)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 0 | 0 | 0 |  | 0
|  |  |  | Land Logistics | 554.9342 | 133184.2037 | 991.6037 |  | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 for material movement) | 832.4013 | 199776.3056 | 1487.4056 |  | 0
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) |  |  | 0 |  | 0
|  | 2 |  | Habitat |  |  | 0 |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5527.1445 | 1123852.7058 | 9211.9074 |  | 0
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 |  | 0
|  | 4 |  | Instruments/valves on spare flowlines | 287686.4857 | 58496252.0837 | 479477.4761 |  | 0
|  | OPTIONAL SCOPE DPB SUB-TOTAL |  |  | 909541.0659 | 184990885.7 | 1516068.56 |  | 0 | 0
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | 1 |  | Removal of Boat Catcher & Crane | 1319619.5832 | 12447957.924 | 1360432.56 |  | 0
|  | 2 |  | Re-installation of Boat Catcher & Crane | 1043395.492 | 226897658.1421 | 1787322.24 |  | 0
|  | BOAT CATCHER SUB-TOTAL |  |  | 2363015.0752 | 239345616.0661 | 3147754.8 |  | 0 | 0
|  | DORMANLONG DPA | [6 empty] | 0
|  | B. OPTIONAL SCOPE | [6 empty] | 0
|  | Logistics (Land & Offshore) | [6 empty] | 0
|  |  |  | Marine Logistics |  |  |  |  | 0
|  |  |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System).)(Max 16 days for precomissioning/wellhead tie-in) | 177531.168 | 36098004.16 | 295885.28 |  | 0
|  | SUB-TOTAL |  |  | 177531.168 | 36098004.16 | 295885.28 |  | 0 | 0
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | Re-installation of Boat Catcher & Crane | [6 empty] | 0
|  |  |  | Cost for DP-2 Construction & Diving Support Vessel | 330642.9598 | 67230735.1624 | 551071.5997 |  | 0
|  |  |  | Cost for diving services | 135647.3017 | 27581618.0192 | 226078.8362 |  | 0
|  |  |  | Cost of meals& bunks | 32112.4225 | 6529525.8984 | 53520.7041 |  | 0
|  | SUB-TOTAL |  |  | 498402.684 | 101341879.08 | 830671.14 |  | 0 | 0
|  | TOTAL |  |  | 5125362.8437 | 836833305.6568 | 7869078.6 |  | 0 | 0
| OPTIONAL SCOPE | 2 |  | DPB - MARINE LOGISTICS |  |  |  |  | 0
|  | 2.1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPB WELL HOOKUP) |  |  |  |  | 0
|  | 2.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 248700.096 | 50569019.52 | 414500.16 |  | 0 | 414500.16
|  | 2.1.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0 | 265000
|  | 2.1.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 381600 | 77592000 | 636000 |  | 0 | 636000
|  | 2.1.4 |  | Provision of SEWOP Support Vessel | 144000 | 29280000 | 240000 |  | 0 | 240000
|  | 2.1.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 144000 | 29280000 | 240000 |  | 0 | 240000
|  | 2.1.6 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 57600 | 11712000 | 96000 |  | 0 | 96000
|  |  |  | Sub-total with SEWOP 230 | 1134900.096 | 230763019.52 | 1891500.16 |  | 0 | 1891500.16
|  | 2.2 |  | Boat Catcher/Crane Removal & Debris Survey (ALL DPB WELL HOOKUP) |  |  |  |  | 0 | 0
|  | 2.2.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) & Debris Survey | 248700.096 | 50569019.52 | 414500.16 |  | 0 | 414500.16
|  | 2.2.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0 | 265000
|  | 2.2.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 381600 | 77592000 | 636000 |  | 0 | 636000
|  | 2.2.4 |  | Provision of SEWOP Support Vessel | 144000 | 29280000 | 240000 |  | 0 | 240000
|  | 2.2.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 144000 | 29280000 | 240000 |  | 0 | 240000
|  | 2.2.6 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0 | 0
|  | 2.2.6.1 |  | Two LARS systems (for working diver and standby diver resp.) | 27516.672 | 5595056.64 | 45861.12 |  | 0 | 45861.12
|  | 2.2.6.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 13758.336 | 2797528.32 | 22930.56 |  | 0 | 22930.56
|  | 2.2.6.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 13758.336 | 2797528.32 | 22930.56 |  | 0 | 22930.56
|  | 2.2.6.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 13758.336 | 2797528.32 | 22930.56 |  | 0 | 22930.56
|  | 2.2.6.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 13758.336 | 2797528.32 | 22930.56 |  | 0 | 22930.56
|  | 2.2.7 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 57600 | 11712000 | 96000 |  | 0 | 96000
|  |  |  | Sub-total with SEWOP 230 | 1217450.112 | 247548189.44 | 2029083.52 |  | 0 | 2029083.52
0
|  | 2.3 |  | DPB Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 2.3.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 196887.576 | 40033807.12 | 328145.96 |  | 0 | 328145.96
|  | 2.3.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0 | 328145.96
|  | 2.3.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0 | 328145.96
|  | 2.3.4 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0 | 328145.96
|  | 2.3.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0 | 328145.96
|  | 2.3.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 45600 | 9272000 | 76000 |  | 0 | 328145.96
|  |  |  | Sub-total with SEWOP 230 | 931587.576 | 189422807.12 | 1552645.96 |  | 0 | 1968875.76
|  | 2.4 |  | Boat Catcher Reinstallation |  |  |  |  | 0
|  | 2.4.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) | 196887.576 | 40033807.12 | 328145.96 |  | 0 | 328145.96
|  | 2.4.2 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0 | 503500
|  | 2.4.3 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) |  |  | 0 |  | 0 | 0
|  | 2.4.3 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0 | 190000
|  | 2.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0 | 190000
|  | 2.4.5 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0 | 0
|  | 2.4.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 21784.032 | 4429419.84 | 36306.72 |  | 0 | 36306.72
|  | 2.4.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 45600 | 9272000 | 76000 |  | 0 | 76000
|  |  |  | Sub-total with SEWOP 230 | 837939.672 | 170381066.64 | 1396566.12 |  | 0 | 1396566.12
[9 empty] | 0 | 0
|  |  |  | Crane Services |  |  |  |  | 0 | 0
|  | 1 |  | Crane Services | 355816.4344 | 10408657.415 | 389943.18 |  | 0 | 389943.18
|  |  |  | Gas Lift Modification |  |  |  |  | 0 | 0
|  | 1 |  | Project Management | 88.9406 | 18143.8875 | 148.4288 |  | 0 | 148.4288
|  | 2 |  | Procurement | 1491.9742 |  | 1491.9742 |  | 0 | 1491.9742
|  | 3 |  | Onshore Fabrication | 1728.6076 | 351483.5446 | 2881.0127 |  | 0 | 2881.0127
|  | 4 |  | Installation/Commissioning | 4828.0014 | 646957.8737 | 6949.1748 |  | 0 | 6949.1748
|  | Sub-Total |  |  | 363953.9583 | 11425242.7208 | 401413.7705 |  | 0 | 401413.7705
0
|  | 2.4 |  | Boat Catcher Reinstallation (DPA) |  |  |  |  | 0
|  | 2.4.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) | 196887.576 | 40033807.12 | 328145.96 |  | 0 | 328145.96
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0 | 503500
|  | 2.4.3 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0 | 190000
|  | 2.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0 | 190000
|  | 2.4.5 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0 | 0
|  | 2.4.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 21784.032 | 4429419.84 | 36306.72 |  | 0 | 36306.72
|  | 2.4.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10892.016 | 2214709.92 | 18153.36 |  | 0 | 18153.36
|  | 2.4.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 45600 | 9272000 | 76000 |  | 0 | 76000
|  |  |  | Sub-total with SEWOP 200 | 837939.672 | 170381066.64 | 1396566.12 |  | 0 | 1396566.12
|  | TOTAL |  |  | 5323771.0863 | 1019921392.0808 | 8667775.6505 |  | 0 | 9084005.4505
[7 empty] | 40230641.4655 |  | 8274497.2512 | 23542414.7705
0
Marine Logisitics | [6 empty] | 3826539.34 |  | 3826539.34
DED | [6 empty] | 632656.64 |  | 632656.64
Technical Support service/QA QC | [6 empty] | 641362.18 |  | 641362.18
OTHERS (Catering, Hotel,travels, logistics) | [6 empty] | 66811.42 |  | 66811.42
5167369.58
PMT/OTHERS | [8 empty] | 0
SALARIES | [6 empty] | 2038937.73 |  | 2038937.73
TP OVERHEAD | [6 empty] | 3187943.41 |  | 744596.97
OTHERS (Catering, Hotel,Aviation,Travels, Government Levies) | [6 empty] | 404408.71 |  | 404408.71
3187943.41

## OTHERS (hidden)
OTHERS
Catering |  | AKOMA IKECHUKWU M WESTEND | 43.24
|  | AKOMA IKECHUKWU M WESTEND 15TH - 31ST MARCH 2019 I | 20.17
|  | AKPABIO JESSICA WESTEND 1ST -15TH APRIL 2019 I.A | 44.46
|  | David Joy ELVIMEX | 143.59
|  | David Joy MENAGE | 2946.62
|  | DAVID JOY WESTEND | 28.79
|  | Jonah Anthony ELVIMEX LTD | 32.69
|  | OBIAKOR OBIORA WESTEND 1ST -15TH APRIL 2019 I.A | 93.96
|  | Obinya Echezieuche ELVIMEX | 17.04
|  | Obinya Echezieuche ELVIMEX NIG LTD | 42.26
|  | Obinya Echezieuche MENAGE | 1410.29
|  | Uko Lydia WESTEND | 237.93
|  | UKO LYDIA WESTEND 15TH - 31ST MARCH 2019 I.A | 44.9
|  | UKO LYDIA WESTEND 1ST -15TH JUNE 2019 I.A | 319.23
|  | UKO LYDIA WESTEND 1ST -15TH MAY 2019 I.A | 43.22
COURTESY VISIT TO EA COMMUNITY TRADITIONAL RULERS |  | COURTESY VISIT TO EA COMMUNITY TRADITIONAL RULERS | 7688.79
Hotels |  | ADEKOYA ADEBANJI AYALLA HOTELS | 75.34
|  | ADESHOLA TELLA HOTEL PRESIDENTIAL | 153.91
|  | Adesola Ojesanmi Eko Suites Hotel | 1248.83
|  | Agha Johnson Kayriott Hotel & Suites | 94.98
|  | Amam Stanley SE Eko Suites Hotel | 206.92
|  | ARIAGBODE E. CHRISTIAN MATHO CRYSTAL HOTEL | 747.69
|  | Asalu Bunmi Eko Suites Hotel | 419.65
|  | Awe Oluwaseun O GOLDEN TULIP | 508.33
|  | Ayeni Paul PO Eko Suites Hotel | 445.47
|  | Bale Nurudeen GOLDEN TULIP | 143.07
|  | Bassey Essien EEko Suites Hotel | 260.15
|  | CHIDIEBERE CHIKWUMA AYALLA HOTELS | 68.78
|  | CONFERENCE HALL SEG LECTURE Eko Suites Hotel | 506.85
|  | CYRIL NDUDI EJOWOKOGHENE PH Guesthouse | 42.59
|  | Ebenuwah Andrew AC Eko Suites Hotel | 509.39
|  | Ebinum Olisemeka Regent Luxury Suites Ltd | 1399.05
|  | ELOHO ABU AYALLA HOTELS | 68.78
|  | ELUMEZE EBELE AYALLA HOTELS | 349.54
|  | EMAKPO EREWHATA PH Guesthouse | 98.25
|  | Emakpo Erewhata PH_RA HALL | 654.98
|  | EMMANUEL EKOBA AYALLA HOTELS | 115.48
|  | ETIM ASUQUO AYALLA HOTELS | 115.48
|  | Ikhureigbe Macdonald ME Eko Suites Hotel | 570.69
|  | Ikhureigbe Macdonald MEEko Suites Hotel | 574.04
|  | Ikpeme Philip Eko Suites Hotel | 193.83
|  | Ikpeme Philip Kayriott Hotel & Suites | 981.09
|  | Ikpewock Mudei GOLDEN TULIP | 235.88
|  | Kabiru Onisarotu GOLDEN TULIP | 506.44
|  | KINGSLEY CHINWO AYALLA HOTELS | 75.34
|  | Kura Mohammed Aisha GOLDEN TULIP | 117.36
|  | Micheal Richard Eko Suites Hotel | 186.68
|  | NTUK FABIAN AYALLA HOTELS | 115.48
|  | Nwabuoku Michael MU Eko Suites Hotel | 168.66
|  | Nwabuoku Michael MUEko Suites Hotel | 1720.65
|  | Nwabuoku Uche Eko Suites Hotel | 1042.29
|  | Obinya Echezieuche PH_RA HALL | 327.49
|  | Oboho Eteyen EE Kayriott Hotel & Suites | 73.5
|  | Ocho Uchechukwu UL Eko Suites Hotel | 769.34
|  | Ocho Uchechukwu ULEko Suites Hotel | 382.04
|  | Odokuma Lucky L Eko Suites Hotel | 154.7
|  | Okafor Nnanna Kayriott Hotel & Suites | 154.53
|  | OKOLI CHRIS AYALLA HOTELS | 95.28
|  | Okpo Abonne EtetimEko Suites Hotel | 233.61
|  | Olanipekun Bashiru Kayriott Hotel & Suites | 1413.57
|  | Ovokeronye Ejenavi GOLDEN TULIP | 253.42
|  | ROLAND ONYEJIUWA MATHO CRYSTAL HOTEL | 708.1
|  | Shariff Bashiru GOLDEN TULIP | 229.44
|  | Shehu Mohammed GOLDEN TULIP | 243.63
|  | SIMPLE OHALLEM HOTEL PRESIDENTIAL | 221.55
|  | STEPHEN OKIRI AYALLA HOTELS | 135.43
|  | SUNNY RICHARD MATHO CRYSTAL HOTEL | 688.87
|  | TAIWO MAFIMISEBI MATHO CRYSTAL HOTEL | 742.03
|  | TITAN ATILA MATHO CRYSTAL HOTEL | 690.38
|  | UKPE GODWIN AYALLA HOTELS | 115.48
|  | Umar El-Badawy GOLDEN TULIP | 255.52
|  | UNUIGBE CHRISTOPHER WARRI GUESTHOUSE | 43.61
HSE Services Generic |  | ABDULAZEEZNURUDEENOffshore Safety Permit cards | 680
|  | AyeniNikkiOffshore Safety Permit cards | 680
|  | AyeniPaulOffshore Safety Permit cards | 680
|  | BUKARAHMED ABDULLAHI Offshore Safety Permit cards | 680
|  | CHIOKEKELECHUKWUOffshore Safety Permit cards | 680
|  | EmakpoErewhata FataOffshore Safety Permit cards | 680
|  | KOLAJOOLADELE OLUWASEYIOffshore Safety Permit card | 680
|  | MAJAROAKINLOLU OLUBUSAYOOffshore Safety Permit car | 680
|  | MOHAMMEDMUKHTAROffshore Safety Permit cards | 680
|  | OBRESAHGODSPOWEROffshore Safety Permit cards | 680
|  | ODUDIMUAKINLOWO OLADAPOOffshore Safety Permit card | 680
|  | OkpoAbonneOffshore Safety Permit cards | 680
|  | ORODUMERCY OMENEBELEOffshore Safety Permit cards | 680
|  | TBOSIET TRAINING Ayeni Nikki A SPDC-PTEEUPE | 1000
|  | TBOSIET TRAINING Jaiyeola Rotimi O SPDC-UPOGPWT | 1000
|  | TBOSIET WITH CA-EBS Briggs Ibifubara SPDC-UPO/G/SC | 1000
|  | TBOSIET WITH CA-EBS Ogwe Ezenwa SPDC-PTP/O/NP | 1000
|  | TBOSIET WITH CA-EBS Unuigbe Christopher SPDC-UPO/G | 1000
Security Expenditure |  | NPA (JTF FUEL DELIVERY) CHIOMA OZOAGU | 91.4
|  | SEPTEMBER 2017 TBOSIET ChTBOSIET TRAINING Ayeni Ni | 1000
|  | SEPTEMBER 2017 TBOSIET ChTBOSIET TRAINING Jaiyeola | 1000
|  | WARRI ENVIRONS OBOHO ETEYEN | 274.11
Training, Internal |  | TBOSIET TRAINING WITH CA-EBSOnimowo Kayode O SPDC- | 1000
|  | TBOSIET WITH CA-EBS Jonah Anthony SPDC-PTP/O/NP | 1000
Logistics Airfreight Services Generic |  | Aviation East CB | -153032
|  | Aviation East CB for August 19 | 12455.5
|  | Aviation East CB for June 19 | 108161.64
|  | Aviation East CB for May 19 | 35593.67
|  | Aviation West CB for May 19 | 8597.51
|  | TWIN OTTA CHARGEBACK FOR NOV | 339.84
|  | Twin Otter CB for Mar19 | 509.34
|  | Twin Otter CB for May 19 | 169.77
66811.42
Technical Support service/QA QC
| 4510411034 |  | -1.81
|  | QA/QC SERV. 1 PERS 01 .M | 759.38
|  | QA/QC SERV. 1 PERS 01 .S | 2295.93
|  | QA/QC SERV. 1 PERS 02 .M | 675.13
|  | QA/QC SERV. 1 PERS 02 .S | 2041.2
|  | QA/QC SERV. 1 PERS 03 .M | 731.14
|  | QA/QC SERV. 1 PERS 03 .S | 2210.55
| 4510411037 |  | 0.51
|  | QA/QC SERV. 1 PERS 02 .M | 1243.21
|  | QA/QC SERV. 1 PERS 02 .S | 3758.74
|  | QA/QC SERV. 2 PERS 01 .M | 1398.56
|  | QA/QC SERV. 2 PERS 01 .S | 4228.45
|  | QA/QC SERV. 2 PERS 3 .M | 1346.56
|  | QA/QC SERV. 2 PERS 3 .S | 4071.22
| 4510411171 |  | 0.52
|  | DC Correction cost | 0
|  | QA/QC SERV. 4 PERS 01 .M | 2222.01
|  | QA/QC SERV. 4 PERS 01 .S | 6718.09
|  | QA/QC SERV. 4 PERS 02 .M | 1975.48
|  | QA/QC SERV. 4 PERS 02 .S | 5972.73
|  | QA/QC SERV. 4 PERS 03 .M | 2139.38
|  | QA/QC SERV. 4 PERS 03 .S | 6468.28
| 4510414853 |  | 5.27
|  | QA/QC SERV. 1 PERS 06 .M | 406.23
|  | QA/QC SERV. 1 PERS 06 .S | 1228.2
|  | QA/QC SERV. 3 PERS 04 .M | 2167.16
|  | QA/QC SERV. 3 PERS 06 .M | 1677.66
|  | QA/QC SERV. 3 PERS 06 .S | 5072.28
|  | QA/QC SERV. 4 PERS 04 .S | 6552.27
|  | QA/QC SERV. 4 PERS 05 .M | 2250.93
|  | QA/QC SERV. 4 PERS 05 .S | 6805.53
| 4510414859 |  | 1.07
|  | DC Correction cost | 0
|  | QA/QC SERV. 2 PERS 04 .M | 1278.58
|  | QA/QC SERV. 2 PERS 04 .S | 3866.41
|  | QA/QC SERV. 2 PERS 05 .M | 1328
|  | QA/QC SERV. 2 PERS 05 .S | 4015.12
| 4510414862 |  | 3.11
|  | QA/QC SERV. 1 PER 06 . M | 703.02
|  | QA/QC SERV. 1 PER 07 . M | 0
|  | QA/QC SERV. 1 PERS 06 .M | 591.55
|  | QA/QC SERV. 1 PERS 06 .S | 3914.03
|  | QA/QC SERV. 1 PERS 07 .S | 0
|  | QA/QC SERV. 2 PERS 04 .M | 1346.1
|  | QA/QC SERV. 2 PERS 04 .S | 4069.85
|  | QA/QC SERV. 2 PERS 05 .M | 1398.13
|  | QA/QC SERV. 2 PERS 05 .S | 4227.16
| 4510414868 |  | 2.42
|  | QA/QC SERV. 1 PERS 04 .M | 730.89
|  | QA/QC SERV. 1 PERS 04 .S | 2209.81
|  | QA/QC SERV. 1 PERS 05 .M | 759.15
|  | QA/QC SERV. 1 PERS 05 .S | 2295.22
|  | QA/QC SERV. 1 PERS 06 .M | 702.78
|  | QA/QC SERV. 1 PERS 06 .S | 2124.82
| 4510418403 |  | 1.67
|  | QA/QC SERV. 2 PERS 06 .M | 1229.4
|  | QA/QC SERV. 2 PERS 06 .S | 3717.02
| 4510420304 |  | -1.67
|  | QA/QC SERV. 4 PER M | 4502.21
|  | QA/QC SERV. 4 PERS 07 .S | 6805.53
|  | QA/QC SERV. 4 PERS 08 .S | 6806.57
|  | QA/QC SERV. 4 PERS 09.M | 2084.51
|  | QA/QC SERV. 4 PERS 09 . S | 6302.38
| 4510420308 |  | -0.43
|  | QA/QC SERV. 1 PER 08 . M | 568.94
|  | QA/QC SERV. 1 PERS 07 .M | 568.86
|  | QA/QC SERV. 1 PERS 07 .S | 1719.9
|  | QA/QC SERV. 1 PERS 08 .S | 1720.16
|  | QA/QC SERV. 1 PERS 09.M | 526.8
|  | QA/QC SERV. 1 PERS 09 . S | 1592.74
| 4510420309 |  | 0.49
|  | QA/QC SERV. 1 PER 07 . M | 639.08
|  | QA/QC SERV. 1 PER 08 . M | 639.08
|  | QA/QC SERV. 1 PER M | 759.15
|  | QA/QC SERV. 1 PERS 07 .S | 4227.45
|  | QA/QC SERV. 1 PERS 08 .M | 759.26
|  | QA/QC SERV. 1 PERS 08 .S | 4227.81
|  | QA/QC SERV. 2 PERS 09.M | 1294.77
|  | QA/QC SERV. 2 PERS 09.S | 3914.63
| 4510420314 |  | 0.47
|  | QA/QC SERV. 1 PER 08 . M | 759.26
|  | QA/QC SERV. 1 PER M | 759.15
|  | QA/QC SERV. 1 PERS 07 .S | 2295.22
|  | QA/QC SERV. 1 PERS 08 .S | 2295.58
|  | QA/QC SERV. 1 PERS 09.M | 703.02
|  | QA/QC SERV. 1 PERS 09 . S | 2125.53
| 4510422365 |  | -2.49
|  | QA/QC VEHICLE SERV. | 15883.65
|  | QA/QC VEHICLE SERV. M | 289.45
| 4510423421 | QA/QC SERV. 4x4 HiKUX M | 41.56
|  | QA/QC SERV. 4x4 HiKUX JUL - SEPT | 2280.59
| 4510423422 |  | 0.13
|  | QA/QC SERV. 1 PERS 07 .M | 224.93
|  | QA/QC SERV. 1 PERS 07 .S 2018 | 680.07
| 4510386111 |  | -907.81
|  | August2017 Planning Engr Ighagbon J | 3747.28
|  | DC Correction cost | 387.59
|  | July2017 Planning Engr Ighagbon J | 3747.28
|  | Sept2017 Planning Engr Ighagbon J | 3747.28
| 4510386113 |  | -447.63
|  | August2017 2No Service Positions | 5933.93
|  | DC Correction cost | 447.62
|  | July2017 2No Service Positions | 5933.93
|  | July2017 2No Service Positions 134873 | 4.5475e-13
|  | Sept2017 2No Service Positions | 5933.93
| 4510391546 |  | -0.16
|  | DC Correction cost | 0.16
|  | Dec2017 Planning Engr Ighagbon Joel | 3862.78
|  | Nov2017 Planning Engr Ighagbon Joel | 3862.78
|  | Oct2017 Planning Engr Ighagbon Joel | 3862.78
| 4510391547 |  | -4
|  | DC Correction cost | 4
|  | Dec2017 2No Service Positions | 5848.69
|  | Nov2017 2No Service Positions | 5848.69
|  | Oct2017 2No Service Positions | 5848.69
| 4510394418 |  | 6.38
|  | DC Correction cost | -6.38
|  | Feb 2018 Planning Engr Ighagbon Joel | 3862.09
|  | Feb 2018 Planning Engr Ighagbon Joel 134807 | 0
|  | Jan2018 Planning Engr Ighagbon Joel | 3862.09
|  | March 2018 Planning Engr Ighagbon Joel | 3862.09
| 4510394419 |  | 14.77
|  | DC Correction cost | -14.77
|  | Feb 2018 3No Service Positions | 9104.87
|  | Jan2018 3No Service Positions | 9104.87
|  | March 2018 3No Service Positions | 9104.87
| 4510398827 |  | -7.82
|  | April 2018 Planning Engr Ighagbon Joel | 4059.13
|  | DC Correction cost | 7.83
|  | June 2018 Planning Engr Ighagbon Joel | 4059.13
|  | May 2018 Planning Engr Ighagbon Joel | 4059.13
|  | May 2018 Planning Engr Ighagbon Joel 134807 | 0
| 4510398828 |  | -21.41
|  | April 2018 2No Service Positions | 5853.54
|  | DC Correction cost | 21.41
|  | June 2018 2No Service Positiions | 5853.54
|  | May 2018 2No Service Positiions | 5853.54
| 4510402862 |  | -16.05
|  | Aug 2018 Planning Engr Ighagbon Joel | 4172.55
|  | DC Correction cost | 16.04
|  | July 2018 Planning Engr Ighagbon Joel | 4172.55
|  | Sep 2018 Planning Engr Ighagbon Joel | 4172.55
| 4510402863 |  | -35.67
|  | Aug 2018 3No Service Positions | 9107.87
|  | DC Correction cost | 35.67
|  | July 2018 3No Service Positions | 9107.87
|  | Sep 2018 3No Service Positions | 9107.87
| 4510406047 |  | -38.13
|  | DC Correction cost | 38.12
|  | Dec 2018 2No Service Positions | 5842.92
|  | Nov 2018 2No Service Positions | 5842.92
|  | Oct 2018 2No Service Positions | 5842.92
| 4510410959 |  | 0.93
|  | DC Correction cost | -0.93
|  | Feb 2019 2No service Positions | 5828.59
|  | Jan 2019 2No service Positions | 5828.59
|  | Mar 2019 2No Service Positions | 5828.59
| 4510415103 |  | -0.39
|  | DC Correction cost | 0.39
|  | Feb 2019 Civil/Struc Engr Lawal Ademola | 3849.38
|  | Mar 2019 Civil/Struc Engr Lawal Ademola | 3849.38
| 4510415802 |  | -1.54
|  | Apr 2019 Civil/Struc Engr Lawal Ademola | 3958.88
|  | DC Correction cost | 1.53
|  | June 2019 Civil/Struc Engr Lawal Ademola | 3958.88
|  | May 2019 Civil/Struc Engr Lawal Ademola | 3958.88
| 4510415803 |  | -2.56
|  | Apr 2019 3No Service Positions | 12152.45
|  | DC Correction cost | 2.55
|  | June 2019 2No Service Positions | 9113.88
|  | May 2019 2No Service Positions | 9113.88
| 4510415804 |  | 0.27
|  | Apr 2019 Security Adviser Bature Paul | 6283.66
|  | DC Correction cost | -0.27
|  | June 2019 Security Adviser Bature Paul | 6283.66
|  | May 2019 Security Adviser Bature Paul | 6283.66
| 4510416052 |  | 3.3
|  | Apr 2019 Construc Engr Onyemaenu Obiora | 5496.88
|  | DC Correction cost | -3.3
|  | June 2019 Construc Engr Onyemaenu Obiora | 5496.88
|  | May 2019 Construc Engr Onyemaenu Obiora | 5496.88
| 4510419171 |  | 0.01
|  | DC Correction cost | -0.01
|  | June 2019 Logistics Coord Okafor Nnanna | 4927.46
| 4510419574 |  | 2.23
|  | Aug 2019 4No Service Positions | 22242.06
|  | DC Correction cost | -2.23
|  | July 2019 4No Service Positions | 22242.06
|  | Sep 2019 4No Service Positions | 22242.06
| 4510419576 |  | 1.53
|  | Aug 2019 Logist Coord Okafor Nnanna | 4927.46
|  | DC Correction cost | -1.53
|  | July 2019 Logist Coord Okafor Nnanna | 4927.46
|  | Sep 2019 Logist Coord Okafor Nnanna | 4927.46
| 4510419577 |  | 0.57
|  | Aug 2019 Civl/Struc Engr Lawal Ademola | 3958.88
|  | DC Correction cost | -0.55
|  | July 2019 Civl/Struc Engr Lawal Ademola | 3958.88
|  | Sep 2019 Civl/Struc Engr Lawal Ademola | 3958.88
| 4510419578 |  | 2.63
|  | Aug 2019 2No Service Positions | 9113.88
|  | DC Correction cost | -2.64
|  | July 2019 2No Service Positions | 9113.88
|  | Sep 2019 2No Service Positions | 9113.88
| 4510419579 |  | 2.1
|  | Aug 2019 Security Adviser Bature Paul | 6283.66
|  | DC Correction cost | -2.1
|  | July 2019 Security Adviser Bature Paul | 6283.66
|  | Sep 2019 Security Adviser Bature Paul | 6283.66
| 4510421837 |  | -2.59
|  | Aug 2019 Snr Planning Engr Bob-Manuel S | 5158.92
|  | DC Correction cost | 2.59
|  | July 2019 Snr Planning Engr Bob-Manuel S | 5158.92
|  | Sep 2019 Snr Planning Engr Bob-Manuel S | 5158.92
641362.18
DED
Design General
|  | SEDO chargeback_EA FOD Step 1 DED Additional Flowl | 84970.18
|  | SEDO Chargeback_Update of DED for EA FOD DPB based | 57826.68
|  | PO 4510385813 EA FOD Step 1 DED | 92287.52
|  | SEDO charge back -EA FOD Step 1 DED | 77212.8
|  | SEDO chargeback_EA FOD Step 1 DED | 24744.86
|  | SEDO chargeback_EA FOD Step 1 DED Additional Flowl | 83837.81
|  | SEDO chargeback-EA FOD Step 1 DED | 90314.78
| 4510400803 | 50% paymnt DED Sea Eagle FPSO Fut Dev W. | 51052.34
| 4510400803 | Bal 50% PM DED Sea Eagle FPSO Fut Dev W. | 51043.37
| 4510410461 | DED Sea Eagle FPSO Futur DW Change Order | 15018
| 4510397411 | Paymnt Sea Eagle Microwave link relocatn | 2310.42
| 4510397744 | Paymnt EA FODTelecoms site survey work-2 | 2037.88
632656.64
Marine Logisitics
Charter Barges
| 4510414994 | PROV.JUB(LEYAMAMUS)07-30/4/2019-MICHARRY | 399184.88
| 4510420155 | PROV.JUB(LEYAMAMUS)01-31/05/19-MICHARRY | 515613.81
| 4510420346 | PROV.JUB (LEYAMAMUS) 01-30/06/2019 | 498981.11
| 4510420353 | PROV.JUB (LEYAMAMUS) 01-31/07/2019 121207 | 515582.37
Fuel, Gasoline/Diesel/Vaporising | 4710138708 | Fuel, Gasoline/Diesel/Vaporising | 4388.35
| 4710138768 | Fuel, Gasoline/Diesel/Vaporising | 7191.29
| 4710139131 | Fuel, Gasoline/Diesel/Vaporising | 49097.68
| 4710139146 | Fuel, Gasoline/Diesel/Vaporising | 11753.35
| 4710139149 | Fuel, Gasoline/Diesel/Vaporising | 8812.05
| 4710139661 | Fuel, Gasoline/Diesel/Vaporising | 9403.59 | 28.8889
| 4710140206 | Fuel, Gasoline/Diesel/Vaporising | 5467.29 | 14.4444
| 4710140313 | Fuel, Gasoline/Diesel/Vaporising | 15631.65
| 4710140431 | Fuel, Gasoline/Diesel/Vaporising | 7850.57
| 4710140531 | Fuel, Gasoline/Diesel/Vaporising | 6248.33
| 4710140535 | Fuel, Gasoline/Diesel/Vaporising | 3126.33
|  | Fuel East CB for September 19 | 68.53
|  | Fuel West CB for August 19 | 655.78
|  | Fuel West CB for July 19 | 129.26
|  | JUB Layemamus at DP-J 20K litres of AGO for EA FOD | 12000
Stand-by Vessels | 4510418089 | MAY '19 PROV OF FFSV XXNNS EA FOD SEWOP 129878 | 208635.7
|  | PROV. OF SECURITY PATROL VESSELS- | 104317.8
|  | PROV. OF SECURITY PATROL VESSELS- 129878 | 0
| 4510422502 | PROV.OF VESSEL FOR EA FOD SEWOP | 353092.74
|  | PROV.OF VESSEL FOR EA FOD SEWOP-NNS EKO | 248769.89
|  | Prov.of Vessels @ EIA Project - FDG for 129878 | 88268.95
|  | Prov.of Vessels @Africa Worker -SEPTEMBR 129878 | 56171.15
Marine & Offshore Installations |  | RECEIVED BY EFUNBAJO ADEOLA 4/6/2019 DUR | 12646.66
Marine Service Vessels | 4510418922 | PROV.AHTS(GEDANDE)MTRL.MVT.EA-RPA -GREEN | 426489.21
| 4510420533 | PROV.AHTS(GEDANDE)MTRL.MVT.EA-RPA -GREEN | 241677.23
|  | Security for MV Layemamus 22nd - 23rd Apr Borrowed | 15283.79
3826539.34
5167369.58

## PMT (hidden)
|  |  | TP OVERHEADS |  |  | Salaries & Wages |  |  | OTHERS
Sum of Val/COArea Crcy |  |  | Sum of Val/COArea Crcy |  |  | Sum of Val/COArea Crcy |  |  | Sum of Val/COArea Crcy |  |  | Sum of Val/COArea Crcy | Total
Cost element descr. | Name | Total | Cost element descr. | Name | Total | Cost element descr. | Name | Total | Cost element descr. | Name | Total | Total | 3187943.41
|  |  | Cable & Accessories | TP-OVH TP OVERHEADS 20190430 | 5.9 | Salaries & Wages | Apr 2019 salary cap for SOTP (EA FOD Terminal & | 1331.52 | [5 empty] | OP19
Total |  |  |  | TP-OVH TP OVERHEADS 20190930 | 0 |  | Apr. 2018 salary cap for Pipeline Matrix & Civil | 3069.71 | Total | [5 empty] | Data | Y2019 | Y2020 | Y2021
Building Mat'S & Hardware, General |  | -13384.32 | Cable & Accessories Total |  | 5.9 |  | August 2018 salary cap for Pipeline Matrix & Civi | 4113.25 | Building Mat'S & Hardware, General |  | -13384.32 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Facilities | 6.33 | 23.6 | 1.1
| DC Correction cost | -0.44 | Catering | TP-OVH TP OVERHEADS 20190331 | 97.02 |  | Dec. 2018 salary cap for Pipeline Matrix & Civil | -680.43 |  | DC Correction cost | -0.44 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Facilities | 1.99 | 2 | 0.2
| SAGA2 FLOORING,GERFLOR,0012 | 6832.29 |  | TP-OVH TP OVERHEADS 20190430 | 23 |  | Jan & Feb 2019 salary cap for SOTP (EA FOD Termina | 4364.66 |  | SAGA2 FLOORING,GERFLOR,0012 | 6832.29 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Oncosts | 7.51 | 0
| SAGA2 FLOORING,GERFLOR,0022 | 6552.47 |  | TP-OVH TP OVERHEADS 20190531 | 733.18 |  | July 2018 salary cap for Pipeline Matrix & Civil | 4734.19 |  | SAGA2 FLOORING,GERFLOR,0022 | 6552.47 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Completion | 65.36 | 1.17
| WBS C.NG.EAF.DF.17.001.AC03 | 13384.75 |  | TP-OVH TP OVERHEADS 20190630 | 75.64 |  | July 2019 salary cap for SOTP (EA FOD Terminal & | 1406.92 |  | WBS C.NG.EAF.DF.17.001.AC03 | 13384.75 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Production Well Drilling | 139.82 | 53.62
Building Mat'S & Hardware, General Total |  | 13384.75 |  | TP-OVH TP OVERHEADS 20190731 | 74.04 |  | June 2018 salary cap for Pipeline Matrix & Civil | 3118.75 | Building Mat'S & Hardware, General Total |  | 13384.75 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1B | Dev. Oil Completion | 15.8 | 1.17
Cable & Accessories | Office and Building Maintenance | 7 |  | TP-OVH TP OVERHEADS 20190831 | 4.81 |  | June 2019 salary cap for SOTP (EA FOD Terminal & C | 1485.51 | Cable & Accessories | Office and Building Maintenance | 7 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1B | Dev. Oil Production Well Drilling | 25.15 | 34.6
| TP-OVH TP OVERHEADS 20190430 | 5.9 |  | TP-OVH TP OVERHEADS 20190930 | 727.25 |  | Mar 2019 salary cap for SOTP (EA FOD Terminal & Co | 1702.77 | Cable & Accessories Total |  | 7 |  |  |  |  | 261.96 | 116.16 | 1.3
| TP-OVH TP OVERHEADS 20190930 | 0 | Catering Total |  | 1734.94 |  | May 2018 salary cap for Pipeline Matrix & Civil P | 1916.87 | Catering | Ayeni Paul ELVIMEX LTD | 144.03
Cable & Accessories Total |  | 12.9 | Daily Allowance | TP-OVH TP OVERHEADS 20190331 | 906.99 |  | May 2019 salary cap for SOTP (EA FOD Terminal & | 789.47 |  | Catering | 3614.97 |  |  | OP19LE (Assumption: EJA13 & EJA11 dropped; No platform mod scope on DPB)
Catering | Ayeni Paul ELVIMEX LTD | 144.03 |  | TP-OVH TP OVERHEADS 20190531 | 164.1 |  | Nov. 2018 salary cap for Pipeline Matrix & Civil | 3152.98 |  | LYDIA UKO WESTEND 16TH - 31ST AUGUST 2019 I.A | 4.11 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Facilities
| Catering | 3614.97 |  | TP-OVH TP OVERHEADS 20190630 | 85.19 |  | Oct. 2018 salary cap for Pipeline Matrix & Civil | 5506.78 |  | OBOHO ETEYEN Homegate | 176.53 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Facilities
| LYDIA UKO WESTEND 16TH - 31ST AUGUST 2019 I.A | 4.11 |  | TP-OVH TP OVERHEADS 20190930 | 38.61 |  | Real of PT salaries | 1138659.76 |  | PHILIP IKPEME Homegate Catering | 126.11 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil On costs
| OBOHO ETEYEN Homegate | 176.53 | Daily Allowance Total |  | 1194.89 |  | Real of TP salaries | 569248.34 |  | UKO LYDIA WESTEND 15TH - 31ST MARCH 2019 I.A | 168.86 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Completion
| PHILIP IKPEME Homegate Catering | 126.11 | EPIC Projects | TP-OVH TP OVERHEADS 20190228 | 230167.26 |  | Sept. 2018 salary cap for Pipeline Matrix & Civil | 5984.53 |  | UKO LYDIA WESTEND 16TH - 31ST AUGUST 2019 I.A | 100.23 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1A | Dev. Oil Production Well Drilling
| TP-OVH TP OVERHEADS 20190331 | 97.02 |  | TP-OVH TP OVERHEADS 20190331 | 0 |  | September 2019 salary cap for SOTP (EA FOD Termin | 326.13 |  | UKO LYDIA WESTEND 1ST -15TH APRIL 2019 I.A | 141.11 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1B | Dev. Oil Completion
| TP-OVH TP OVERHEADS 20190430 | 23 |  | TP-OVH TP OVERHEADS 20190430 | 13793.23 |  | TP Mar 2018 Sal Real | 288706.02 | Catering Total |  | 4475.95 |  |  | EA FURTHER OIL DEVELOPMENT - STEP 1B | Dev. Oil Production Well Drilling
| TP-OVH TP OVERHEADS 20190531 | 733.18 |  | TP-OVH TP OVERHEADS 20190531 | 233173.64 | Salaries & Wages Total |  | 2038937.73 | Comm. Expenditure - Courtesy Call & Homa | Chrg for: CBN WDW CashLess Chrg & VAT | 310.48
| TP-OVH TP OVERHEADS 20190630 | 75.64 |  | TP-OVH TP OVERHEADS 20190630 | 4681.18 | Grand Total |  | 2038937.73 | Comm. Expenditure - Courtesy Call & Homa Total |  | 310.48
| TP-OVH TP OVERHEADS 20190731 | 74.04 |  | TP-OVH TP OVERHEADS 20190731 | 2779.26 |  |  |  | Facility Management Generic |  | -0.06 | [6 empty] | 48.5 | 98.88
| TP-OVH TP OVERHEADS 20190831 | 4.81 |  | TP-OVH TP OVERHEADS 20190831 | 218660.12 |  |  |  |  | Office and Building Maintenance | -187 | [6 empty] | 57.24 | 66.99
| TP-OVH TP OVERHEADS 20190930 | 727.25 |  | TP-OVH TP OVERHEADS 20190930 | 1622.92 |  |  |  |  | PROVIDE SMALL WHITE BOARDS-B2 38 | 0 | [6 empty] | 0.03 | 66.77
| UKO LYDIA WESTEND 15TH - 31ST MARCH 2019 I.A | 168.86 | EPIC Projects Total |  | 704877.61 |  |  |  |  | PROVIDE TWO WHITE BOARDS -B4 026 | 182.54 | [6 empty] | 105.77 | 232.64
| UKO LYDIA WESTEND 16TH - 31ST AUGUST 2019 I.A | 100.23 | Facility Management Generic | TP-OVH TP OVERHEADS 20190630 | -10.53 |  |  |  | Facility Management Generic Total |  | -4.52
| UKO LYDIA WESTEND 1ST -15TH APRIL 2019 I.A | 141.11 | Facility Management Generic Total |  | -10.53 |  |  |  | Fire/Safety/Envir. Eqpt | SHOELADIESBLACKUK7 | 184 | [6 empty] | 121.77
Catering Total |  | 6210.89 | Fasteners, General | TP-OVH TP OVERHEADS 20190930 | 8.62 |  |  |  | Fire/Safety/Envir. Eqpt Total |  | 184
Comm. Expenditure - Courtesy Call & Homa | Chrg for: CBN WDW CashLess Chrg & VAT | 310.48 | Fasteners, General Total |  | 8.62 |  |  |  | Geological Consultancy Services | Jack-up assessment for EA | 6720
Comm. Expenditure - Courtesy Call & Homa Total |  | 310.48 | Fuel, Gasoline/Diesel/Vaporising | TP-OVH TP OVERHEADS 20190331 | 2.13 |  |  |  | Geological Consultancy Services Total |  | 6720 | [7 empty] | 121.6
Daily Allowance | TP-OVH TP OVERHEADS 20190331 | 906.99 |  | TP-OVH TP OVERHEADS 20190430 | 5.38 |  |  |  | Government Fees | Taxes, levies_PYMNT TO DPR FOR THE SEA EAGLE Q1&Q | 115525.67
| TP-OVH TP OVERHEADS 20190531 | 164.1 |  | TP-OVH TP OVERHEADS 20190531 | 3.26 |  |  |  | Government Fees Total |  | 115525.67
| TP-OVH TP OVERHEADS 20190630 | 85.19 |  | TP-OVH TP OVERHEADS 20190630 | 4.85 |  |  |  | Hotels | Babatunde Olatuni GOLDEN TULIP | 250.49
| TP-OVH TP OVERHEADS 20190930 | 38.61 |  | TP-OVH TP OVERHEADS 20190731 | 6.78 |  |  |  |  | Batiswei Eyilade Rebatel Suites Limited | 78.21
Daily Allowance Total |  | 1194.89 |  | TP-OVH TP OVERHEADS 20190831 | 1.6 |  |  |  |  | Braemi Daniel Rebatel Suites Limited | 76.7
EPIC Projects | TP-OVH TP OVERHEADS 20190228 | 230167.26 |  | TP-OVH TP OVERHEADS 20190930 | 15.13 |  |  |  |  | CHIJIAKA RAPHAEL GENESIS HOTEL | 93
| TP-OVH TP OVERHEADS 20190331 | 0 | Fuel, Gasoline/Diesel/Vaporising Total |  | 39.13 |  |  |  |  | Decca Emma Rebatel Suites Limited | 76.7
| TP-OVH TP OVERHEADS 20190430 | 13793.23 | General Administration Costs | TP-OVH TP OVERHEADS 20190331 | 48.17 |  |  |  |  | DINNIA FRED .N GENESIS HOTEL | 91.49
| TP-OVH TP OVERHEADS 20190531 | 233173.64 |  | TP-OVH TP OVERHEADS 20190630 | 131.83 |  |  |  |  | Direabebe Ovuwo Rebatel Suites Limited | 76.7
| TP-OVH TP OVERHEADS 20190630 | 4681.18 |  | TP-OVH TP OVERHEADS 20190831 | -173.13 |  |  |  |  | DOKUBO OBONGO HOTEL PRESIDENTIAL | 419.8
| TP-OVH TP OVERHEADS 20190731 | 2779.26 |  | TP-OVH TP OVERHEADS 20190930 | 2.2 |  |  |  |  | Edi Emmanuel Rebatel Suites Limited | 76.7
| TP-OVH TP OVERHEADS 20190831 | 218660.12 | General Administration Costs Total |  | 9.07 |  |  |  |  | Egberibeleu Egeun Rebatel Suites Limited | 76.7
| TP-OVH TP OVERHEADS 20190930 | 1622.92 | Government Fees | TP-OVH TP OVERHEADS 20190331 | 1016 |  |  |  |  | EMAKPO EREWHATA FATA PH Guesthouse | 883.36
EPIC Projects Total |  | 704877.61 | Government Fees Total |  | 1016 |  |  |  |  | EREWHATA EMAKPO PH Guesthouse | 85.16
Facility Management Generic |  | -0.06 | Heavy Vehicles And Lifting Services | TP-OVH TP OVERHEADS 20190831 | 12.62 |  |  |  |  | FRANK IYOYO GENESIS HOTEL | 73.6
| Office and Building Maintenance | -187 | Heavy Vehicles And Lifting Services Total |  | 12.62 |  |  |  |  | FUNCTION MATHO CRYSTAL | 3056.9
| PROVIDE SMALL WHITE BOARDS-B2 38 | 0 | Hotels | TP-OVH TP OVERHEADS 20190228 | 93.71 |  |  |  |  | Giant Isiaye Rebatel Suites Limited | 76.7
| PROVIDE TWO WHITE BOARDS -B4 026 | 182.54 |  | TP-OVH TP OVERHEADS 20190331 | 834.77 |  |  |  |  | GIMBA FATIMA HOTEL PRESIDENTIAL | 309.57
| TP-OVH TP OVERHEADS 20190630 | -10.53 |  | TP-OVH TP OVERHEADS 20190430 | 721.69 |  |  |  |  | Gold kurabo Rebatel Suites Limited | 76.7
Facility Management Generic Total |  | -15.05 |  | TP-OVH TP OVERHEADS 20190531 | 373.42 |  |  |  |  | Hotels and travel | 11302
Fasteners, General | TP-OVH TP OVERHEADS 20190930 | 8.62 |  | TP-OVH TP OVERHEADS 20190630 | 1201.97 |  |  |  |  | Ibane Joel Rebatel Suites Limited | 76.7
Fasteners, General Total |  | 8.62 |  | TP-OVH TP OVERHEADS 20190731 | 694.42 |  |  |  |  | Igbosaibogha Clement Rebatel Suites Limited | 76.7
Fire/Safety/Envir. Eqpt | SHOELADIESBLACKUK7 | 184 |  | TP-OVH TP OVERHEADS 20190831 | 3183.73 |  |  |  |  | Igbosaibogha Patrick Rebatel Suites Limited | 76.7
Fire/Safety/Envir. Eqpt Total |  | 184 |  | TP-OVH TP OVERHEADS 20190930 | 1352.21 |  |  |  |  | Igbousai Israel Ngome Rebatel Suites Limited | 76.7
Fuel, Gasoline/Diesel/Vaporising | TP-OVH TP OVERHEADS 20190331 | 2.13 | Hotels Total |  | 8455.92 |  |  |  |  | JOSEPH PEREKEBINA EBIBOKEFIE HOTEL PRESIDENTIAL | 332.09
| TP-OVH TP OVERHEADS 20190430 | 5.38 | HSE Services Generic | TP-OVH TP OVERHEADS 20190430 | 0.77 |  |  |  |  | LUNCH PACKS MATHO CRYSTAL | 292.85
| TP-OVH TP OVERHEADS 20190531 | 3.26 | HSE Services Generic Total |  | 0.77 |  |  |  |  | Mar.18 PH Guest House Cha | 1959.29
| TP-OVH TP OVERHEADS 20190630 | 4.85 | Human Resources Consultancy Services | TP-OVH TP OVERHEADS 20190930 | 0 |  |  |  |  | Miebiogu Otidi Rebatel Suites Limited | 76.7
| TP-OVH TP OVERHEADS 20190731 | 6.78 | Human Resources Consultancy Services Total |  | 0 |  |  |  |  | Minna Fun F Rebatel Suites Limited | 76.7
| TP-OVH TP OVERHEADS 20190831 | 1.6 | IT General | TP-OVH TP OVERHEADS 20190531 | 3.62 |  |  |  |  | Nwabuoku Michael MU Eko Suites Hotel | 528.13
| TP-OVH TP OVERHEADS 20190930 | 15.13 |  | TP-OVH TP OVERHEADS 20190731 | -119.84 |  |  |  |  | Nwabuoku Uche Sheraton Hotel | 909.57
Fuel, Gasoline/Diesel/Vaporising Total |  | 39.13 |  | TP-OVH TP OVERHEADS 20190831 | -20.75 |  |  |  |  | NWANZE HENRY GENESIS HOTEL | 99.03
General Administration Costs | TP-OVH TP OVERHEADS 20190331 | 48.17 |  | TP-OVH TP OVERHEADS 20190930 | 2.04 |  |  |  |  | Oladipo Ogunbona GOLDEN TULIP | 235.63
| TP-OVH TP OVERHEADS 20190630 | 131.83 | IT General Total |  | -134.93 |  |  |  |  | Olamine Pius Rebatel Suites Limited | 76.7
| TP-OVH TP OVERHEADS 20190831 | -173.13 | Laboratory Requisites | TP-OVH TP OVERHEADS 20190430 | 13.82 |  |  |  |  | Orisunmbare Lateef Sheraton Hotel | 885.68
| TP-OVH TP OVERHEADS 20190930 | 2.2 |  | TP-OVH TP OVERHEADS 20190930 | 0 |  |  |  |  | Otiti David O Rebatel Suites Limited | 76.7
General Administration Costs Total |  | 9.07 | Laboratory Requisites Total |  | 13.82 |  |  |  |  | PH Guesthouse EMAKPO EREWHATA FATA | 2353.3
Geological Consultancy Services | Jack-up assessment for EA | 6720 | Light Vehicles Services | TP-OVH TP OVERHEADS 20190228 | 100.61 |  |  |  |  | Prima Marcus Rebatel Suites Limited | 76.7
Geological Consultancy Services Total |  | 6720 |  | TP-OVH TP OVERHEADS 20190331 | 2.81 |  |  |  |  | REMILEKUN MAKUN Elion House | 293.79
Government Fees | Taxes, levies_PYMNT TO DPR FOR THE SEA EAGLE Q1&Q | 115525.67 |  | TP-OVH TP OVERHEADS 20190531 | 137.5 |  |  |  |  | Seide Paul Rebatel Suites Limited | 76.7
| TP-OVH TP OVERHEADS 20190331 | 1016 |  | TP-OVH TP OVERHEADS 20190630 | 86.85 |  |  |  |  | Uchola Wilson GOLDEN TULIP | 203.89
Government Fees Total |  | 116541.67 |  | TP-OVH TP OVERHEADS 20190731 | 72.39 |  |  |  |  | Ugwa Sunday Eko Suites Hotel | 1040.63
Heavy Vehicles And Lifting Services | TP-OVH TP OVERHEADS 20190831 | 12.62 |  | TP-OVH TP OVERHEADS 20190930 | 93.71 |  |  |  |  | Ukponu Stellamaris Ngozi GOLDEN TULIP | 237.15
Heavy Vehicles And Lifting Services Total |  | 12.62 | Light Vehicles Services Total |  | 493.87 |  |  |  |  | Unuige Christopher Regent Luxury Suites Ltd | 142.71
Hotels | Babatunde Olatuni GOLDEN TULIP | 250.49 | Logistic Land Services Generic | TP-OVH TP OVERHEADS 20190228 | 4.52 |  |  |  |  | Zimobofawei James Rebatel Suites Limited | 76.7
| Batiswei Eyilade Rebatel Suites Limited | 78.21 |  | TP-OVH TP OVERHEADS 20190531 | 6.77 |  |  |  | Hotels Total |  | 27537.92
| Braemi Daniel Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190731 | 7.23 |  |  |  | HSE Services Generic | Accident Prevention & Investigation | 3000
| CHIJIAKA RAPHAEL GENESIS HOTEL | 93 | Logistic Land Services Generic Total |  | 18.52 |  |  |  |  | PTW REFRESHERADEBAYOSEBIOTIMO | 65.25
| Decca Emma Rebatel Suites Limited | 76.7 | Logistics Airfreight Services Generic | TP-OVH TP OVERHEADS 20190331 | 13.58 |  |  |  |  | PTW REFRESHEROLANIPEKUNBASHIR | 65.25
| DINNIA FRED .N GENESIS HOTEL | 91.49 |  | TP-OVH TP OVERHEADS 20190531 | 40.74 |  |  |  |  | TBOSIET WITH CA-EBS Daniyan Babatunde M | 1000
| Direabebe Ovuwo Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190831 | 74.69 |  |  |  | HSE Services Generic Total |  | 4130.5
| DOKUBO OBONGO HOTEL PRESIDENTIAL | 419.8 |  | TP-OVH TP OVERHEADS 20190930 | 13.58 |  |  |  | IT General |  | -39.13
| Edi Emmanuel Rebatel Suites Limited | 76.7 | Logistics Airfreight Services Generic Total |  | 142.59 |  |  |  |  | DC Correction cost | -0.01
| Egberibeleu Egeun Rebatel Suites Limited | 76.7 | Logistics General Services Generic | TP-OVH TP OVERHEADS 20190731 | 0.59 |  |  |  |  | Feb19 Non Payroll GSM Contractor bills | 6.67
| EMAKPO EREWHATA FATA PH Guesthouse | 883.36 | Logistics General Services Generic Total |  | 0.59 |  |  |  |  | Jan. to Mar. 2018 STM costs | 249.09
| EREWHATA EMAKPO PH Guesthouse | 85.16 | Manpower Services Generic | TP-OVH TP OVERHEADS 20190228 | 0 |  |  |  |  | July'19 Contractor lines | 35.35
| FRANK IYOYO GENESIS HOTEL | 73.6 |  | TP-OVH TP OVERHEADS 20190331 | 0 |  |  |  |  | June2019 Contractor lines | 19.72
| FUNCTION MATHO CRYSTAL | 3056.9 |  | TP-OVH TP OVERHEADS 20190831 | 0 |  |  |  |  | Mar19 Non Payroll GSM Contractor bills | 16.94
| Giant Isiaye Rebatel Suites Limited | 76.7 | Manpower Services Generic Total |  | 0 |  |  |  |  | May 2019 Contractor lines | 37.32
| GIMBA FATIMA HOTEL PRESIDENTIAL | 309.57 | Media Advertising, Including Radio. Tv, | TP-OVH TP OVERHEADS 20190228 | 7.4 |  |  |  |  | PAYMENT-OSP & BOSIET TRAINING EA-FOD PER | 39.14
| Gold kurabo Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190630 | 7.55 |  |  |  |  | WBS C.NG.EAF.DF.17.001.AC03 | 39.14
| Hotels and travel | 11302 |  | TP-OVH TP OVERHEADS 20190731 | 2.6 |  |  |  | IT General Total |  | 404.23
| Ibane Joel Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190930 | 2.6 |  |  |  | IT Maintenance Services |  | -11473.92
| Igbosaibogha Clement Rebatel Suites Limited | 76.7 | Media Advertising, Including Radio. Tv, Total |  | 20.15 |  |  |  |  | DC Correction cost | 0.42
| Igbosaibogha Patrick Rebatel Suites Limited | 76.7 | Mobile Phone Airtime Services | TP-OVH TP OVERHEADS 20190331 | 3.23 |  |  |  |  | OSP payment for EA-FOD-2 | 3405.02
| Igbousai Israel Ngome Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190630 | 4.82 |  |  |  |  | Payment on Markup for training | 1712.9
| JOSEPH PEREKEBINA EBIBOKEFIE HOTEL PRESIDENTIAL | 332.09 | Mobile Phone Airtime Services Total |  | 8.05 |  |  |  |  | Payment on Markup for training 120449 | 0
| LUNCH PACKS MATHO CRYSTAL | 292.85 | Office Equipment Services | TP-OVH TP OVERHEADS 20190630 | 2.25 |  |  |  |  | Pymt for BOSIET training for EA-FOD-2 | 6355.58
| Mar.18 PH Guest House Cha | 1959.29 | Office Equipment Services Total |  | 2.25 |  |  |  |  | WBS C.NG.EAF.DF.17.001.AC03 | 11473.51
| Miebiogu Otidi Rebatel Suites Limited | 76.7 | Packing/Jointing/Gaskets, General | TP-OVH TP OVERHEADS 20190430 | 1.96 |  |  |  | IT Maintenance Services Total |  | 11473.51
| Minna Fun F Rebatel Suites Limited | 76.7 | Packing/Jointing/Gaskets, General Total |  | 1.96 |  |  |  | Laboratory Requisites | Medical Cost | -14
| Nwabuoku Michael MU Eko Suites Hotel | 528.13 | Production Testing/Operation Services | TP-OVH TP OVERHEADS 20190228 | 1076.58 |  |  |  | Laboratory Requisites Total |  | -14
| Nwabuoku Uche Sheraton Hotel | 909.57 |  | TP-OVH TP OVERHEADS 20190331 | 1076.58 |  |  |  | Light Vehicles Services | Land Transport | 470
| NWANZE HENRY GENESIS HOTEL | 99.03 |  | TP-OVH TP OVERHEADS 20190430 | 1438.52 |  |  |  |  | Taxi Services LF West CB for Apr 19 | 326.22
| Oladipo Ogunbona GOLDEN TULIP | 235.63 |  | TP-OVH TP OVERHEADS 20190531 | 1271.14 |  |  |  | Light Vehicles Services Total |  | 796.22
| Olamine Pius Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190630 | 1296.67 |  |  |  | Logistics Airfreight Services Generic | Aviation East CB | 153032
| Orisunmbare Lateef Sheraton Hotel | 885.68 |  | TP-OVH TP OVERHEADS 20190731 | 1285.5 |  |  |  |  | Aviation East CB for August 19 | 11856.68
| Otiti David O Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190831 | 1285.55 |  |  |  |  | Aviation East CB for July 19 | 23957.58
| PH Guesthouse EMAKPO EREWHATA FATA | 2353.3 |  | TP-OVH TP OVERHEADS 20190930 | 1921.8 |  |  |  |  | Twin Otter Sep '19- AGBAH JULIUS OSUBIPHCNAF | 169.77
| Prima Marcus Rebatel Suites Limited | 76.7 | Production Testing/Operation Services Total |  | 10652.34 |  |  |  |  | Twin Otter Sep '19- AGBONSALOR OGBEBOR OSUBIPHCNAF | 169.77
| REMILEKUN MAKUN Elion House | 293.79 | Project Management Services Generic | TP-OVH TP OVERHEADS 20190228 | 1208.23 |  |  |  |  | Twin Otter Sep '19- EBIBOKEFIE JOSEPH PHCNAFOSUBI | 169.77
| Seide Paul Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190331 | 940.66 |  |  |  |  | Twin Otter Sep '19- IGE MICHAEL ADEBISI OSUBIPHCNA | 169.77
| TP-OVH TP OVERHEADS 20190228 | 93.71 |  | TP-OVH TP OVERHEADS 20190430 | 764.18 |  |  |  | Logistics Airfreight Services Generic Total |  | 189525.34
| TP-OVH TP OVERHEADS 20190331 | 834.77 |  | TP-OVH TP OVERHEADS 20190531 | 1003.89 |  |  |  | Logistics General Services Generic | Land Pre-Mob Chargeback for March 2102 | 14.69
| TP-OVH TP OVERHEADS 20190430 | 721.69 |  | TP-OVH TP OVERHEADS 20190630 | 1095.14 |  |  |  |  | Land Pre-Mob Chargeback for March 2103 | 14.69
| TP-OVH TP OVERHEADS 20190531 | 373.42 |  | TP-OVH TP OVERHEADS 20190731 | 775.75 |  |  |  |  | Land Pre-Mob Chargeback for March 2104 | 14.69
| TP-OVH TP OVERHEADS 20190630 | 1201.97 |  | TP-OVH TP OVERHEADS 20190831 | 1120.37 |  |  |  |  | Land Pre-Mob Chargeback for March 2105 | 14.69
| TP-OVH TP OVERHEADS 20190731 | 694.42 |  | TP-OVH TP OVERHEADS 20190930 | 947.3 |  |  |  |  | Land Pre-Mob Chargeback for March 2106 | 14.69
| TP-OVH TP OVERHEADS 20190831 | 3183.73 | Project Management Services Generic Total |  | 7855.52 |  |  |  |  | Land Pre-Mob Chargeback for March 2107 | 14.69
| TP-OVH TP OVERHEADS 20190930 | 1352.21 | Realised Trading DIE Gain (Internally Re | TP-OVH TP OVERHEADS 20190930 | 75.43 |  |  |  |  | Land Pre-Mob Chargeback for September 2019 | 88.08
| Uchola Wilson GOLDEN TULIP | 203.89 | Realised Trading DIE Gain (Internally Re Total |  | 75.43 |  |  |  |  | Land Transport | 178
| Ugwa Sunday Eko Suites Hotel | 1040.63 | Realised Trading DIE Loss (Internally Re | TP-OVH TP OVERHEADS 20190930 | 0.03 |  |  |  | Logistics General Services Generic Total |  | 354.22
| Ukponu Stellamaris Ngozi GOLDEN TULIP | 237.15 | Realised Trading DIE Loss (Internally Re Total |  | 0.03 |  |  |  | Media Advertising, Including Radio. Tv, | 2019 EA TRADITIONAL RULERS ENGAGEMENT | 156.24
| Unuige Christopher Regent Luxury Suites Ltd | 142.71 | Reprographics | TP-OVH TP OVERHEADS 20190228 | 8.35 |  |  |  | Media Advertising, Including Radio. Tv, Total |  | 156.24
| Zimobofawei James Rebatel Suites Limited | 76.7 |  | TP-OVH TP OVERHEADS 20190531 | 16.2 |  |  |  | Mobile Phone Airtime Services | APR 2019 CONTRACTOR LINES | 9.19
Hotels Total |  | 35993.84 |  | TP-OVH TP OVERHEADS 20190731 | 3.56 |  |  |  |  | AUG 2018 CONTRACTOR LINES | 9.02
HSE Services Generic | Accident Prevention & Investigation | 3000 |  | TP-OVH TP OVERHEADS 20190831 | 17.17 |  |  |  |  | JAN 2019 CONTRACTOR LINES | 5.58
| PTW REFRESHERADEBAYOSEBIOTIMO | 65.25 |  | TP-OVH TP OVERHEADS 20190930 | 17.17 |  |  |  |  | JULY 2018 CONTRACTOR LINES | 11.52
| PTW REFRESHEROLANIPEKUNBASHIR | 65.25 | Reprographics Total |  | 62.45 |  |  |  |  | NOV 2018 CONTRACTOR LINES | 10.67
| TBOSIET WITH CA-EBS Daniyan Babatunde M | 1000 | Security Expenditure Generic | TP-OVH TP OVERHEADS 20190228 | 85.27 |  |  |  |  | OCT 2018 CONTRACTOR LINES | 13.2
| TP-OVH TP OVERHEADS 20190430 | 0.77 |  | TP-OVH TP OVERHEADS 20190331 | 69.01 |  |  |  |  | SEP 2018 CONTRACTOR LINES | 14.16
HSE Services Generic Total |  | 4131.27 |  | TP-OVH TP OVERHEADS 20190531 | 186.73 |  |  |  | Mobile Phone Airtime Services Total |  | 73.34
Human Resources Consultancy Services | TP-OVH TP OVERHEADS 20190930 | 0 |  | TP-OVH TP OVERHEADS 20190630 | 85.26 |  |  |  | Project Management Services Generic | Catering | 144.03
Human Resources Consultancy Services Total |  | 0 |  | TP-OVH TP OVERHEADS 20190731 | 89.33 |  |  |  |  | Medical Cost | 14
IT General |  | -39.13 |  | TP-OVH TP OVERHEADS 20190831 | 81.17 |  |  |  |  | Office and Building Maintenance | 180
| DC Correction cost | -0.01 |  | TP-OVH TP OVERHEADS 20190930 | 89.31 |  |  |  | Project Management Services Generic Total |  | 338.03
| Feb19 Non Payroll GSM Contractor bills | 6.67 | Security Expenditure Generic Total |  | 686.08 |  |  |  | Realised Trading DIE Gain (Internally Re |  | -0.48
| Jan. to Mar. 2018 STM costs | 249.09 | Shop & Welding Eqpt, General | TP-OVH TP OVERHEADS 20190930 | 10.68 |  |  |  |  | PERDIEE0Z Performance DIE (411001E0Z) 20190531 | 0.05
| July'19 Contractor lines | 35.35 | Shop & Welding Eqpt, General Total |  | 10.68 |  |  |  |  | PERDIEE0Z Performance DIE (411001E0Z) 20190630 | 0.1
| June2019 Contractor lines | 19.72 | Subscription Fees, Institutes/Assoc.s | TP-OVH TP OVERHEADS 20190630 | 41.85 |  |  |  |  | PERDIEE0Z Performance DIE (411001E0Z) 20190731 | 0.33
| Mar19 Non Payroll GSM Contractor bills | 16.94 |  | TP-OVH TP OVERHEADS 20190831 | 290.98 |  |  |  | Realised Trading DIE Gain (Internally Re Total |  | -5.5511e-17
| May 2019 Contractor lines | 37.32 | Subscription Fees, Institutes/Assoc.s Total |  | 332.83 |  |  |  | Realised Trading DIE Loss (Internally Re |  | 0.01
| PAYMENT-OSP & BOSIET TRAINING EA-FOD PER | 39.14 | Travel Services / Agents | TP-OVH TP OVERHEADS 20190331 | 3.54 |  |  |  |  | PERDIEE0Z Performance DIE (411001E0Z) 20190630 | -0.01
| TP-OVH TP OVERHEADS 20190531 | 3.62 | Travel Services / Agents Total |  | 3.54 |  |  |  |  | PERDIEE0Z Performance DIE (411001E0Z) 20190731 | 0
| TP-OVH TP OVERHEADS 20190731 | -119.84 | Travel, Air | TP-OVH TP OVERHEADS 20190228 | 627.07 |  |  |  |  | PERDIEE0Z Performance DIE (411001E0Z) 20190831 | 0
| TP-OVH TP OVERHEADS 20190831 | -20.75 |  | TP-OVH TP OVERHEADS 20190331 | 177.95 |  |  |  | Realised Trading DIE Loss (Internally Re Total |  | 0
| TP-OVH TP OVERHEADS 20190930 | 2.04 |  | TP-OVH TP OVERHEADS 20190430 | 1057.5 |  |  |  | Reprographics | FEB 2019 Reprographics bills | 851.08
| WBS C.NG.EAF.DF.17.001.AC03 | 39.14 |  | TP-OVH TP OVERHEADS 20190531 | 1913.68 |  |  |  | Reprographics Total |  | 851.08
IT General Total |  | 269.3 |  | TP-OVH TP OVERHEADS 20190630 | 367.27 |  |  |  | Security Expenditure Generic | ESCORT REQUEST BY LYDIAUKO FOR ASALU BUNMI FROM | 202.97
IT Maintenance Services |  | -11473.92 |  | TP-OVH TP OVERHEADS 20190731 | 334.97 |  |  |  |  | OGUNU/MICHARRY JETTY LYDIA UKO | 91.37
| DC Correction cost | 0.42 |  | TP-OVH TP OVERHEADS 20190831 | 967.62 |  |  |  |  | WARRI ENVIRONS LYDIA UKO | 456.85
| OSP payment for EA-FOD-2 | 3405.02 |  | TP-OVH TP OVERHEADS 20190930 | 462.27 |  |  |  | Security Expenditure Generic Total |  | 751.19
| Payment on Markup for training | 1712.9 | Travel, Air Total |  | 5908.33 |  |  |  | Telephone & Accessories, Messaging Eqpt | January 2018 reallocation | 28.79
| Payment on Markup for training 120449 | 0 | Travel, Road, Incl. Taxi, Vehicle Hire | TP-OVH TP OVERHEADS 20190228 | 28.28 |  |  |  | Telephone & Accessories, Messaging Eqpt Total |  | 28.79
| Pymt for BOSIET training for EA-FOD-2 | 6355.58 |  | TP-OVH TP OVERHEADS 20190331 | 200.6 |  |  |  | Travel, Air | Erewhata Fata Emakpo BRISTOW AIRLINE | 442.12
| WBS C.NG.EAF.DF.17.001.AC03 | 11473.51 |  | TP-OVH TP OVERHEADS 20190430 | 79.1 |  |  |  |  | Erewhata Fata Emakpo BRISTOW AIRLINE | 1603.32
IT Maintenance Services Total |  | 11473.51 |  | TP-OVH TP OVERHEADS 20190531 | 81.54 |  |  |  |  | Hotels and travel | 20201
Laboratory Requisites | Medical Cost | -14 |  | TP-OVH TP OVERHEADS 20190630 | 268.91 |  |  |  |  | Mar.18 Bristow Airline C | 1816.44
| TP-OVH TP OVERHEADS 20190430 | 13.82 |  | TP-OVH TP OVERHEADS 20190731 | 182.7 |  |  |  |  | Mr Aniekan Udo-Etuk BRISTOW AIRLINE | 250.08
| TP-OVH TP OVERHEADS 20190930 | 0 |  | TP-OVH TP OVERHEADS 20190831 | 226.42 |  |  |  |  | Mr O.G Ogunbona Bristow Airline | 496.97
Laboratory Requisites Total |  | -0.18 |  | TP-OVH TP OVERHEADS 20190930 | 30.38 |  |  |  |  | Mr Christopher Unuigbe BRISTOW AIRLINE | 250.08
Light Vehicles Services | Land Transport | 470 | Travel, Road, Incl. Taxi, Vehicle Hire Total |  | 1097.93 |  |  |  |  | Mr Gimba Fatima BRISTOW AIRLINE | 496.82
| Taxi Services LF West CB for Apr 19 | 326.22 | Unrealised Foreign Currency Loss-Cash/Ca | TP-OVH TP OVERHEADS 20190930 | 0 |  |  |  |  | Mr Lateef Orisunmbare BRISTOW AIRLINE | 250.08
| TP-OVH TP OVERHEADS 20190228 | 100.61 | Unrealised Foreign Currency Loss-Cash/Ca Total |  | 0 |  |  |  |  | Mr Mohammed Siraj Bristow Airline | 496.97
| TP-OVH TP OVERHEADS 20190331 | 2.81 | Grand Total |  | 744596.97 |  |  |  |  | Mr Uche Nwabuoku BRISTOW AIRLINE | 250.08
| TP-OVH TP OVERHEADS 20190531 | 137.5 | [7 empty] | Mrs Stellamrin Ngozi Ukponu Bristow Airline | 496.97
| TP-OVH TP OVERHEADS 20190630 | 86.85 | [7 empty] | NWABUOKU UCHE Comm Airline | 139.65
| TP-OVH TP OVERHEADS 20190731 | 72.39 | [7 empty] | ORISUNMBARE LATEEF Comm Airline | 139.65
| TP-OVH TP OVERHEADS 20190930 | 93.71 | [6 empty] | Travel, Air Total |  | 27330.23
Light Vehicles Services Total |  | 1290.09 | [6 empty] | Waste Disposal Services | Waste Mgt West CB for June 2019 | 68.54
Logistic Land Services Generic | TP-OVH TP OVERHEADS 20190228 | 4.52 | [6 empty] | Waste Disposal Services Total |  | 68.54
| TP-OVH TP OVERHEADS 20190531 | 6.77 | [6 empty] | Grand Total |  | 404408.71
| TP-OVH TP OVERHEADS 20190731 | 7.23
Logistic Land Services Generic Total |  | 18.52
Logistics Airfreight Services Generic | Aviation East CB | 153032
| Aviation East CB for August 19 | 11856.68
| Aviation East CB for July 19 | 23957.58
| TP-OVH TP OVERHEADS 20190331 | 13.58
| TP-OVH TP OVERHEADS 20190531 | 40.74
| TP-OVH TP OVERHEADS 20190831 | 74.69
| TP-OVH TP OVERHEADS 20190930 | 13.58
| Twin Otter Sep '19- AGBAH JULIUS OSUBIPHCNAF | 169.77
| Twin Otter Sep '19- AGBONSALOR OGBEBOR OSUBIPHCNAF | 169.77
| Twin Otter Sep '19- EBIBOKEFIE JOSEPH PHCNAFOSUBI | 169.77
| Twin Otter Sep '19- IGE MICHAEL ADEBISI OSUBIPHCNA | 169.77
Logistics Airfreight Services Generic Total |  | 189667.93
Logistics General Services Generic | Land Pre-Mob Chargeback for March 2102 | 14.69
| Land Pre-Mob Chargeback for March 2103 | 14.69
| Land Pre-Mob Chargeback for March 2104 | 14.69
| Land Pre-Mob Chargeback for March 2105 | 14.69
| Land Pre-Mob Chargeback for March 2106 | 14.69
| Land Pre-Mob Chargeback for March 2107 | 14.69
| Land Pre-Mob Chargeback for September 2019 | 88.08
| Land Transport | 178
| TP-OVH TP OVERHEADS 20190731 | 0.59
Logistics General Services Generic Total |  | 354.81
Manpower Services Generic | TP-OVH TP OVERHEADS 20190228 | 0
| TP-OVH TP OVERHEADS 20190331 | 0
| TP-OVH TP OVERHEADS 20190831 | 0
Manpower Services Generic Total |  | 0
Media Advertising, Including Radio. Tv, | 2019 EA TRADITIONAL RULERS ENGAGEMENT | 156.24
| TP-OVH TP OVERHEADS 20190228 | 7.4
| TP-OVH TP OVERHEADS 20190630 | 7.55
| TP-OVH TP OVERHEADS 20190731 | 2.6
| TP-OVH TP OVERHEADS 20190930 | 2.6
Media Advertising, Including Radio. Tv, Total |  | 176.39
Mobile Phone Airtime Services | APR 2019 CONTRACTOR LINES | 9.19
| AUG 2018 CONTRACTOR LINES | 9.02
| JAN 2019 CONTRACTOR LINES | 5.58
| JULY 2018 CONTRACTOR LINES | 11.52
| NOV 2018 CONTRACTOR LINES | 10.67
| OCT 2018 CONTRACTOR LINES | 13.2
| SEP 2018 CONTRACTOR LINES | 14.16
| TP-OVH TP OVERHEADS 20190331 | 3.23
| TP-OVH TP OVERHEADS 20190630 | 4.82
Mobile Phone Airtime Services Total |  | 81.39
Office Equipment Services | TP-OVH TP OVERHEADS 20190630 | 2.25
Office Equipment Services Total |  | 2.25
Packing/Jointing/Gaskets, General | TP-OVH TP OVERHEADS 20190430 | 1.96
Packing/Jointing/Gaskets, General Total |  | 1.96
Production Testing/Operation Services | TP-OVH TP OVERHEADS 20190228 | 1076.58
| TP-OVH TP OVERHEADS 20190331 | 1076.58
| TP-OVH TP OVERHEADS 20190430 | 1438.52
| TP-OVH TP OVERHEADS 20190531 | 1271.14
| TP-OVH TP OVERHEADS 20190630 | 1296.67
| TP-OVH TP OVERHEADS 20190731 | 1285.5
| TP-OVH TP OVERHEADS 20190831 | 1285.55
| TP-OVH TP OVERHEADS 20190930 | 1921.8
Production Testing/Operation Services Total |  | 10652.34
Project Management Services Generic | Catering | 144.03
| Medical Cost | 14
| Office and Building Maintenance | 180
| TP-OVH TP OVERHEADS 20190228 | 1208.23
| TP-OVH TP OVERHEADS 20190331 | 940.66
| TP-OVH TP OVERHEADS 20190430 | 764.18
| TP-OVH TP OVERHEADS 20190531 | 1003.89
| TP-OVH TP OVERHEADS 20190630 | 1095.14
| TP-OVH TP OVERHEADS 20190731 | 775.75
| TP-OVH TP OVERHEADS 20190831 | 1120.37
| TP-OVH TP OVERHEADS 20190930 | 947.3
Project Management Services Generic Total |  | 8193.55
Realised Trading DIE Gain (Internally Re |  | -0.48
| PERDIEE0Z Performance DIE (411001E0Z) 20190531 | 0.05
| PERDIEE0Z Performance DIE (411001E0Z) 20190630 | 0.1
| PERDIEE0Z Performance DIE (411001E0Z) 20190731 | 0.33
| TP-OVH TP OVERHEADS 20190930 | 75.43
Realised Trading DIE Gain (Internally Re Total |  | 75.43
Realised Trading DIE Loss (Internally Re |  | 0.01
| PERDIEE0Z Performance DIE (411001E0Z) 20190630 | -0.01
| PERDIEE0Z Performance DIE (411001E0Z) 20190731 | 0
| PERDIEE0Z Performance DIE (411001E0Z) 20190831 | 0
| TP-OVH TP OVERHEADS 20190930 | 0.03
Realised Trading DIE Loss (Internally Re Total |  | 0.03
Reprographics | FEB 2019 Reprographics bills | 851.08
| TP-OVH TP OVERHEADS 20190228 | 8.35
| TP-OVH TP OVERHEADS 20190531 | 16.2
| TP-OVH TP OVERHEADS 20190731 | 3.56
| TP-OVH TP OVERHEADS 20190831 | 17.17
| TP-OVH TP OVERHEADS 20190930 | 17.17
Reprographics Total |  | 913.53
Salaries & Wages | Apr 2019 salary cap for SOTP (EA FOD Terminal & | 1331.52
| Apr. 2018 salary cap for Pipeline Matrix & Civil | 3069.71
| August 2018 salary cap for Pipeline Matrix & Civi | 4113.25
| Dec. 2018 salary cap for Pipeline Matrix & Civil | -680.43
| Jan & Feb 2019 salary cap for SOTP (EA FOD Termina | 4364.66
| July 2018 salary cap for Pipeline Matrix & Civil | 4734.19
| July 2019 salary cap for SOTP (EA FOD Terminal & | 1406.92
| June 2018 salary cap for Pipeline Matrix & Civil | 3118.75
| June 2019 salary cap for SOTP (EA FOD Terminal & C | 1485.51
| Mar 2019 salary cap for SOTP (EA FOD Terminal & Co | 1702.77
| May 2018 salary cap for Pipeline Matrix & Civil P | 1916.87
| May 2019 salary cap for SOTP (EA FOD Terminal & | 789.47
| Nov. 2018 salary cap for Pipeline Matrix & Civil | 3152.98
| Oct. 2018 salary cap for Pipeline Matrix & Civil | 5506.78
| Real of PT salaries | 1138659.76
| Real of TP salaries | 569248.34
| Sept. 2018 salary cap for Pipeline Matrix & Civil | 5984.53
| September 2019 salary cap for SOTP (EA FOD Termin | 326.13
| TP Mar 2018 Sal Real | 288706.02
Salaries & Wages Total |  | 2038937.73
Security Expenditure Generic | ESCORT REQUEST BY LYDIAUKO FOR ASALU BUNMI FROM | 202.97
| OGUNU/MICHARRY JETTY LYDIA UKO | 91.37
| TP-OVH TP OVERHEADS 20190228 | 85.27
| TP-OVH TP OVERHEADS 20190331 | 69.01
| TP-OVH TP OVERHEADS 20190531 | 186.73
| TP-OVH TP OVERHEADS 20190630 | 85.26
| TP-OVH TP OVERHEADS 20190731 | 89.33
| TP-OVH TP OVERHEADS 20190831 | 81.17
| TP-OVH TP OVERHEADS 20190930 | 89.31
| WARRI ENVIRONS LYDIA UKO | 456.85
Security Expenditure Generic Total |  | 1437.27
Shop & Welding Eqpt, General | TP-OVH TP OVERHEADS 20190930 | 10.68
Shop & Welding Eqpt, General Total |  | 10.68
Subscription Fees, Institutes/Assoc.s | TP-OVH TP OVERHEADS 20190630 | 41.85
| TP-OVH TP OVERHEADS 20190831 | 290.98
Subscription Fees, Institutes/Assoc.s Total |  | 332.83
Telephone & Accessories, Messaging Eqpt | January 2018 reallocation | 28.79
Telephone & Accessories, Messaging Eqpt Total |  | 28.79
Travel Services / Agents | TP-OVH TP OVERHEADS 20190331 | 3.54
Travel Services / Agents Total |  | 3.54
Travel, Air | Erewhata Fata Emakpo BRISTOW AIRLINE | 442.12
| Erewhata Fata Emakpo BRISTOW AIRLINE | 1603.32
| Hotels and travel | 20201
| Mar.18 Bristow Airline C | 1816.44
| Mr Aniekan Udo-Etuk BRISTOW AIRLINE | 250.08
| Mr O.G Ogunbona Bristow Airline | 496.97
| Mr Christopher Unuigbe BRISTOW AIRLINE | 250.08
| Mr Gimba Fatima BRISTOW AIRLINE | 496.82
| Mr Lateef Orisunmbare BRISTOW AIRLINE | 250.08
| Mr Mohammed Siraj Bristow Airline | 496.97
| Mr Uche Nwabuoku BRISTOW AIRLINE | 250.08
| Mrs Stellamrin Ngozi Ukponu Bristow Airline | 496.97
| NWABUOKU UCHE Comm Airline | 139.65
| ORISUNMBARE LATEEF Comm Airline | 139.65
| TP-OVH TP OVERHEADS 20190228 | 627.07
| TP-OVH TP OVERHEADS 20190331 | 177.95
| TP-OVH TP OVERHEADS 20190430 | 1057.5
| TP-OVH TP OVERHEADS 20190531 | 1913.68
| TP-OVH TP OVERHEADS 20190630 | 367.27
| TP-OVH TP OVERHEADS 20190731 | 334.97
| TP-OVH TP OVERHEADS 20190831 | 967.62
| TP-OVH TP OVERHEADS 20190930 | 462.27
Travel, Air Total |  | 33238.56
Travel, Road, Incl. Taxi, Vehicle Hire | TP-OVH TP OVERHEADS 20190228 | 28.28
| TP-OVH TP OVERHEADS 20190331 | 200.6
| TP-OVH TP OVERHEADS 20190430 | 79.1
| TP-OVH TP OVERHEADS 20190531 | 81.54
| TP-OVH TP OVERHEADS 20190630 | 268.91
| TP-OVH TP OVERHEADS 20190731 | 182.7
| TP-OVH TP OVERHEADS 20190831 | 226.42
| TP-OVH TP OVERHEADS 20190930 | 30.38
Travel, Road, Incl. Taxi, Vehicle Hire Total |  | 1097.93
Unrealised Foreign Currency Loss-Cash/Ca | TP-OVH TP OVERHEADS 20190930 | 0
Unrealised Foreign Currency Loss-Cash/Ca Total |  | 0
Waste Disposal Services | Waste Mgt West CB for June 2019 | 68.54
Waste Disposal Services Total |  | 68.54
Grand Total |  | 3187943.41

## 6mln Boat Catcher (hidden)
Contractor | Scope | M/S | PO Number | Description |  |  | Amt | % Progress | VOWD | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
STEVE INTEGRATED | BASE SCOPE | A. HOOKUP SCOPE DPA |  |  | NGN | USD | FUSD
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 7251375 | 23775 | 75% | 17831.25
|  | 1.2 |  | Onshore demobilisation | 0 | 1712523.15 | 5614.83 | 75% | 4211.1225
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 9629688.75 | 31572.75 | 75% | 23679.5625
|  | 1.4 |  | Offshore demobilisation | 0 | 3845160.9476 | 12607.0851 | 75% | 9455.3138
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 18273858 | 59914.2885 | 75% | 44935.7164
|  | 2 |  | Project Management | 13382.04 | 2729936.16 | 22332.6504 | 80% | 17866.1203
|  | 3 |  | Procurement |  |  |  |  | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 102084.7142 | 20825250.8465 | 170364.2252 | 100% | 170364.2252
|  |  |  | Piping & Accessories (Deliver) | 102084.7142 | 20825250.8465 | 170364.2252 | 100% | 170364.2252
|  | 3.2 |  | Instrument (FOB) | 290182.4417 | 45461348.0024 | 439236.0418 | 100% | 439236.0418
|  |  |  | Instrument (Deliver) | 290182.4417 | 45461348.0024 | 439236.0418 | 100% | 439236.0418
|  | 3.3 |  | Civil/Structural | 1327.003 | 269823.9409 | 2211.6716 | 100% | 2211.6716
|  | 3.4 |  | Mechanical/HVAC | 5722.093 | 2559700 | 14114.552 | 100% | 14114.552
|  | 3.5 |  | Electrical | 18323.872 | 4242138.8385 | 32232.5239 | 100% | 32232.5239
|  | 3.6 |  | Painting | 2971.1066 | 604125 | 4951.8443 | 100% | 4951.8443
|  | 4 |  | Onshore Fabrication |  |  | 0 |  | 0
|  | 4.1 |  | Production of shop drawing | 9439.1004 | 1919283.7467 | 15731.834 | 100% | 15731.834
|  | 4.2 |  | Fabrication of piping spools | 160464.7067 | 32627823.6934 | 267441.1778 | 100% | 267441.1778
|  | 4.3 |  | NDT | 18878.2008 | 3838567.4933 | 31463.668 | 100% | 31463.668
|  | 5 |  | Installation/ Commissioning |  |  | 0 |  | 0
|  | 5.1 |  | Advance tie-in | 44945.73 | 9138965.1094 | 74909.5501 | 85% | 63673.1176
|  | 5.2 |  | Pre-drill installation | 104873.3701 | 21324251.922 | 174788.9502 | 85% | 148570.6077
|  | 5.3 |  | Hook-up | 119855.2801 | 24370573.6251 | 199758.8002 | 85% | 169794.9802
|  | 5.4 |  | Commissioning | 29963.82 | 6092643.4063 | 49939.7001 | 85% | 42448.745
|  | HOOKUP SCOPE DPA SUB-TOTAL |  |  | 1314680.6347 | 283003636.4811 | 2242561.41 |  | 2129814.3415
|  | B. OPTIONAL SCOPE DPA | [6 empty] | 0
|  | 1 |  | Logistics (Land & Offshore) |  |  |  |  | 0
|  |  |  | Marine Logistics |  |  |  |  | 0
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 days for predrill, 6 days for precomissioning/wellhead tie-in) | 224190.6264 | 45585427.368 | 373651.044
|  |  |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System).)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 246328.2907 | 50086752.4376 | 410547.1511
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 0 | 0 | 0
|  |  |  | Land Logistics | 0 | 0 | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 days for material movement) | 572.8 | 137472 | 1023.5279
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) | 859.2 | 206208 | 1535.2918
|  | 2 |  | Habitat |  |  | 0 |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5705.088 | 1160034.56 | 9508.48 | 100% | 9508.48
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 |  | 0
|  |  |  | Instruments/valves on spare flowlines | 278191.6471 | 56565634.9144 | 463652.7452 |  | 0
|  | OPTIONAL SCOPE DPA SUB-TOTAL |  |  | 755847.6522 | 153741529.28 | 1259918.24 |  | 9508.48
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | 1 |  | Removal of Boat Catcher & Crane | 916214.1908 | 214678934.5661 | 1620079.55 | 100% | 1620079.55
|  | 2 |  | Re-installation of Boat Catcher & Crane | 182595.3074 | 39707328.5839 | 312783.27 | 0% | 0
|  | BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE SUB-TOTAL |  |  | 1098809.4982 | 254386263.15 | 1932862.82 |  | 1620079.55
|  | DPA BASE SCOPE TOTAL |  |  | 3169337.785 | 691131428.9112 | 5435342.47 |  | 3759402.3715
|  | A.HOOKUP SCOPE DPJ | [6 empty] | 0
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 7670312.4168 | 25148.5653 | 60% | 15089.1392
|  | 1.2 |  | Onshore demobilisation | 0 | 1811461.6306 | 5939.2185 | 60% | 3563.5311
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 10186029.7101 | 33396.8187 | 60% | 20038.0912
|  | 1.4 |  | Offshore demobilisation | 0 | 4067309.4084 | 13335.4407 | 60% | 8001.2644
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 19329602.9953 | 63375.7475 | 60% | 38025.4485
|  | 2 |  | Project Management | 34888.89 | 7117333.56 | 58224.4099 | 60% | 34934.6459
|  | 3 |  | Procurement |  |  | 0 |  | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 192891.949 | 39349895.6653 | 321908.0003 | 100% | 321908.0003
|  |  |  | Piping & Accessories (Deliver) | 192891.949 | 39349895.6653 | 321908.0003 | 100% | 321908.0003
|  | 3.2 |  | Instrument (FOB) | 521677.8075 | 64881676.1177 | 734404.6144 | 100% | 734404.6144
|  |  |  | Instrument (Deliver) | 521677.8075 | 64881676.1177 | 734404.6144 | 100% | 734404.6144
|  | 3.3 |  | Civil/Structural | 5281.1622 | 1073836.3107 | 8801.937 | 100% | 8801.937
|  | 3.4 |  | Mechanical/HVAC | 2136.186 | 930800 | 5187.9893 | 100% | 5187.9893
|  | 3.5 |  | Electrical |  |  | 0 | 100% | 0
|  | 3.6 |  | Painting | 5460.8939 | 1110381.75 | 9101.4898 | 100% | 9101.4898
|  | 4 |  | Onshore Fabrication |  |  | 0 |  | 0
|  | 4.1 |  | Production of shop drawing | 18878.2008 | 3838567.4933 | 31463.668 | 100% | 31463.668
|  | 4.2 |  | Fabrication of piping spools | 320929.4134 | 65255647.3868 | 534882.3556 | 100% | 534882.3556
|  | 4.3 |  | NDT | 37756.4016 | 7677134.9867 | 62927.336 | 100% | 62927.336
|  | 5 |  | Installation/ Commissioning |  |  | 0 |  | 0
|  | 5.1 |  | Advance tie-in | 76570.9033 | 15569417.0026 | 127618.1722 | 70% | 89332.7205
|  | 5.2 |  | Pre-drill installation | 178665.441 | 36328639.6728 | 297775.735 | 70% | 208443.0145
|  | 5.3 |  | Hook-up | 204189.0754 | 41518445.3403 | 340315.1257 | 70% | 238220.588
|  | 5.4 |  | Commissioning | 51047.2689 | 10379611.3351 | 85078.7814 | 70% | 59555.147
|  | HOOKUP SCOPE DPJ SUB-TOTAL |  |  | 2364943.3493 | 442327674.5654 | 3815198.02 |  | 3480193.5955
B. OPTIONAL SCOPE DPJ
|  | 1 |  | Logistics (Land & Offshore)
Marine Logistics
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 for predrill, 6 days for precomissioning/wellhead tie-in) | 224190.6264 | 45585427.368 | 373651.044
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 0 | 0 | 0
|  |  |  | Provision of Crewboat (Hookup of Last Well post Rigmove)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 410547.1511 | 83477920.7293 | 684245.2519
|  |  |  | Land Logistics | 0 | 0 | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 for material movement) | 572.8 | 137472 | 1023.5279
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) | 859.2 | 206208 | 1535.2918
0
|  | 3 |  | Habitat |  |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5705.088 | 1160034.56 | 9508.48 | 100% | 9508.48
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0
|  |  |  | Instruments/valves on spare flowlines | 296948.4027 | 60379508.5427 | 494914.0044 | 0%
|  | OPTIONAL SCOPE DPJ SUB-TOTAL |  |  | 938823.2682 | 190946571.2 | 1564877.6 |  | 9508.48
|  | DPJ BASE SCOPE TOTAL |  |  | 3303766.6175 | 633274245.7654 | 5380075.62 |  | 3489702.0755
|  | TOTAL BASE SCOPE |  |  | 6473104.4025 | 1324405674.6766 | 10815418.09 |  | 7249104.4469
| OPTIONAL SCOPE | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPA | [6 empty] | 0
|  | 1 |  | DPA - MARINE LOGISTICS |  |  |  |  | 0
|  | 1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPA WELL HOOKUP) |  |  |  |  | 0
|  | 1.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days. | 310875.12 | 63211274.4 | 518125.2
|  | 1.1.4 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 145200 | 29524000 | 242000
|  | 1.1.5 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 477000 | 96990000 | 795000
|  | 1.1.6 |  | Provision of SEWOP Support Vessel | 180000 | 36600000 | 300000
|  | 1.1.7 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 180000 | 36600000 | 300000
|  | 1.1.8 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 72000 | 14640000 | 120000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1365075.12 | 277565274.4 | 2275125.2 |  | 0
|  | 1.2 |  | Boat Catcher/Crane Removal & Debris Survey (ALL DPA WELL HOOKUP) |  |  |  |  | 0
|  | 1.2.1 |  | Provision of DP2 PSV boat – For Medevac/ERP –(Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (In addition to Contractor Crew, allow for 3 Diving crew,6NOV Crew, 5 SPDC) & Debris Survey | 362687.64 | 73746486.8 | 604479.4
|  | 1.2.5 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 556500 | 113155000 | 927500
|  | 1.2.5 |  | Provision of SEWOP Support Vessel | 210000 | 42700000 | 350000
|  | 1.2.6 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 210000 | 42700000 | 350000
|  | 1.2.5 |  | Provision of a Diving Spread comprising: | 0 | 0 | 0
|  | 1.2.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 20064.24 | 4079728.8 | 33440.4
|  | 1.2.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 84000 | 17080000 | 140000
|  |  |  | Sub-total (With Class 230 SEWOP) | 1523508.84 | 309780130.8 | 2539181.4 |  | 0
|  | 1.3 |  | DPA Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 1.3.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days. | 227975.088 | 46354934.56 | 379958.48 |  | 0
|  |  |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 145200 | 29524000 | 242000 |  | 0
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 349800 | 71126000 | 583000 |  | 0
|  | 1.3.4 |  | Provision of SEWOP Support Vessel | 132000 | 26840000 | 220000 |  | 0
|  | 1.3.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 132000 | 26840000 | 220000 |  | 0
|  | 1.3.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 52800 | 10736000 | 88000 |  | 0
|  |  |  | Sub-total (With Class 230 SEWOP) | 1039775.088 | 211420934.56 | 1732958.48 |  | 0
|  | 1.4 |  | Boat Catcher Reinstallation |  |  |  |  | 0
|  | 1.4.1 |  | Provision of DP2 PSV boat for Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position | 186525.072 | 37926764.64 | 310875.12 |  | 0
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 286200 | 58194000 | 477000 |  | 0
|  | 1.4.3 |  | Provision of SEWOP Support Vessel | 108000 | 21960000 | 180000 |  | 0
|  | 1.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 108000 | 21960000 | 180000 |  | 0
|  | 1.4.5 |  | Provision of a Diving Spread comprising: | 0 | 0 | 0 |  | 0
|  | 1.4.6.1 |  | Two LARS systems (for working diver and standby diver resp.) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.6.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.6.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.6.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.6.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10318.752 | 2098146.24 | 17197.92 |  | 0
|  | 1.4.7 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 43200 | 8784000 | 72000 |  | 0
|  |  |  | Sub-total (With Class 230 SEWOP) | 783518.832 | 159315495.84 | 1305864.72 |  | 0
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPA TOTAL |  |  | 4711877.88 | 958081835.6 | 7853129.8 | 0% | 0
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPJ | [6 empty] | 0
|  | 3.1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPJ WELL HOOKUP) |  |  |  |  | 0
|  | 3.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 310875.12 | 63211274.4 | 518125.2 |  | 0
|  | 3.1.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 200 SEWOP with a crane capacity as 5tons@20 m radius Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 128400 | 26108000 | 214000 |  | 0
|  | 3.1.3 |  | Provision of Class 200 SEWOP with a crane capacity as 5tons@20 m radius. Crane must be manriding certified. | 417600 | 84912000 | 696000 |  | 0
|  | 3.1.4 |  | Provision of SEWOP Support Vessel | 180000 | 36600000 | 300000 |  | 0
|  | 3.1.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 180000 | 36600000 | 300000 |  | 0
|  | 3.1.6 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 72000 | 14640000 | 120000 |  | 0
|  |  |  | Sub-total | 1288875.12 | 262071274.4 | 2148125.2 |  | 0
|  | 3.2 |  | DPJ Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 3.2.1 |  | Provision of DP2 PSV boat - (option to MV Bello) – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 227975.088 | 46354934.56 | 379958.48 |  | 0
|  | 3.2.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 200 SEWOP with a crane capacity as 5tons@20 m radius. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 128400 | 26108000 | 214000 |  | 0
|  | 3.2.3 |  | Provision of Class 200 SEWOP with a crane capacity as 5tons@20 m radius for both boat catcher and crane dismantling . Crane must be manriding certified. | 306240 | 62268800 | 510400 |  | 0
|  | 3.2.4 |  | Provision of SEWOP Support Vessel | 132000 | 26840000 | 220000 |  | 0
|  | 3.2.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 132000 | 26840000 | 220000 |  | 0
|  | 3.2.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 52800 | 10736000 | 88000 |  | 0
|  |  |  | Sub-total | 979415.088 | 199147734.56 | 1632358.48 |  | 0
|  | OPTIONAL SCOPE - ADDITIONAL VESSELS - DPJ |  |  | 2268290.208 | 461219008.96 | 3780483.68 |  | 0
|  | TOTAL ADDITIONAL VESSELS |  |  | 6980168.088 | 1419300844.56 | 11633613.48 |  | 0
0
|  |  |  | Crane Services |  |  |  |  | 0
|  | 1 |  | Crane removal |  |  |  |  | 0
|  | 2 |  | Reinstallation of crane | 355816.4344 | 10408657.415 | 389943.18 | 50% | 194971.59
|  |  |  | Telecoms Relocation |  |  |  |  | 0
|  | 1 |  | Mobilisation and 50% relocation works | 59869.6069 | 6086743.3681 | 79826.1425 | 100% | 79826.1425
|  | 2 |  | Complete telecoms works 100% | 59869.6069 | 6086743.3681 | 79826.1425 | 100% | 79826.1425
|  |  |  | Instrumentation (Invesys) |  |  |  |  | 0
|  | 1 |  | 50% Instrumentation works | 205548.054 | 41794770.98 | 342580.09 | 20% | 68516.018
|  | 2 |  | Complete Instrumentation works | 205548.054 | 41794770.98 | 342580.09 | 20% | 68516.018
|  |  |  | Gas Lift Modification |  |  |  |  | 0
|  | 1 |  | Project Management | 77.538 | 15817.745 | 129.3994 | 100% | 129.3994
|  | 2 |  | Procurement | 1300.6952 | 0 | 1300.6952 |  | 0
|  | 3 |  | Onshore Fabrication | 1506.9909 | 306421.4925 | 2511.6516 |  | 0
|  | 4 |  | Installation/Commissioning | 4209.0261 | 564014.4476 | 6058.2538 |  | 0
|  | CRANE SERVICES TELE COM GASLIFT TOTAL |  |  | 893746.0064 | 107057939.7964 | 1244755.6451 |  | 491785.3105
|  | TOTAL OPTIONAL SCOPE |  |  | 7873914.0944 | 1526358784.3564 | 12878369.1251 |  | 491785.3105
DORMALONG | BASE SCOPE | A.HOOKUP SCOPE DPB | [6 empty] | 0
|  | 1 |  | Mobilisation / Demobilisation |  |  |  |  | 0
|  | 1.1 |  | Onshore mobilisation | 0 | 6366052.1022 | 20872.302 | 10% | 2087.2302
|  | 1.2 |  | Onshore demobilisation | 0 | 1503440.6025 | 4929.3135 | 10% | 492.9313
|  | 1.3 |  | Offshore mobilisation, equipment premob, including BOSIET/OSP | 0 | 8453996.6986 | 27718.022 | 10% | 2771.8022
|  | 1.4 |  | Offshore demobilisation | 0 | 3375703.9091 | 11067.8817 | 10% | 1106.7882
|  | 1.5 |  | As-built documentation (DP-A) | 0 | 16042796.3161 | 52599.3322 | 10% | 5259.9332
|  | 2 |  | Project Management | 26177.0838 | 5340125.1038 | 43685.6907 | 2% | 873.7138
|  | 3 |  | Procurement | 0 | 0 | 0 |  | 0
|  | 3.1 |  | Piping & Accessories (FOB) | 81214.7716 | 16513670.2254 | 135357.9527 |  | 0
|  |  |  | Piping & Accessories (Deliver) | 81214.7716 | 16513670.2254 | 135357.9527 |  | 0
|  | 3.2 |  | Instrument (FOB) | 202329.0868 | 41140247.6511 | 337215.1447 |  | 0
|  |  |  | Instrument (Deliver) | 202329.0868 | 41140247.6511 | 337215.1447 |  | 0
|  | 3.3 |  | Civil/Structural | 1054.3317 | 214380.7844 | 1757.2195 |  | 0
|  | 3.4 |  | Mechanical/HVAC | 6728.5847 | 1368145.5548 | 11214.3078 |  | 0
|  | 3.5 |  | Electrical | 15365.6501 | 3124348.848 | 25609.4168 |  | 0
|  | 3.6 |  | Painting | 2360.6065 | 479989.9924 | 3934.3442 |  | 0
|  | 4 |  | Onshore Fabrication | 0 | 0 | 0 |  | 0
|  | 4.1 |  | Production of shop drawing | 12005.6099 | 2441140.6811 | 20009.3498 |  | 0
|  | 4.2 |  | Fabrication of piping spools | 204095.3684 | 41499391.5793 | 340158.9474 |  | 0
|  | 4.3 |  | NDT | 24011.2198 | 4882281.3623 | 40018.6997 |  | 0
|  | 5 |  | Installation/ Commissioning | 0 | 0 |  |  | 0
|  | 5.1 |  | Advance tie-in | 47698.0018 | 9698593.7044 | 79496.6697 |  | 0
|  | 5.2 |  | Pre-drill installation | 111295.3376 | 22630051.977 | 185492.2293 |  | 0
|  | 5.3 |  | Hook-up | 127194.6715 | 25862916.5452 | 211991.1192 |  | 0
|  | 5.4 |  | Commissioning | 31798.6679 | 6465729.1363 | 52997.7798 |  | 0
|  | HOOKUP SCOPE DPB SUB-TOTAL |  |  | 1176872.8507 | 275056920.6507 | 2078698.82 |  | 12592.3989
|  | B. OPTIONAL SCOPE DPB | [6 empty] | 0
|  | 1 |  | Logistics (Land & Offshore) |  |  |  |  | 0
|  |  |  | Marine Logistics | 217198.048 | 44163603.1002 | 361996.7467 |  | 0
|  |  |  | Provision of Platform Supply Vessel (Including premobilisation & Group Maritime Assurance System). Scope is for Movement of Materials/ Equipment (Max 6 for predrill, 6 days for precomissioning/wellhead tie-in) | 0 | 0 | 0 |  | 0
|  |  |  | Provision of Security Escort Vessel for escort of Platform Supply Vessel | 397742.0523 | 80874217.301 | 662903.4205 |  | 0
|  |  |  | Provision of Crewboat (Hookup of Last Well post Rigmove)(Max 24 for predrill, 16 days for precomissioning/wellhead tie-in) | 0 | 0 | 0 |  | 0
|  |  |  | Land Logistics | 554.9342 | 133184.2037 | 991.6037 |  | 0
|  |  |  | Movement of materials from Contractor Base to Onne using low bed (Max 2 for material movement) | 832.4013 | 199776.3056 | 1487.4056 |  | 0
|  |  |  | Movement of materials from Contractor Base to Warri using lowbed (Nominated Jetty); (Max 3 days for material movement) |  |  | 0 |  | 0
|  | 2 |  | Habitat |  |  | 0 |  | 0
|  |  |  | Provide for welding/hotwork habitat (hotwork on the drilling platform including grating cut through (production to cellar deck), demolition scope-related hotwork etc) | 5527.1445 | 1123852.7058 | 9211.9074 |  | 0
|  | 3 |  | Procurement of Instruments on Spare Flowlines |  |  | 0 |  | 0
|  | 4 |  | Instruments/valves on spare flowlines | 287686.4857 | 58496252.0837 | 479477.4761 |  | 0
|  | OPTIONAL SCOPE DPB SUB-TOTAL |  |  | 909541.0659 | 184990885.7 | 1516068.56 |  | 0
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | 1 |  | Removal of Boat Catcher & Crane | 1319619.5832 | 12447957.924 | 1360432.56 |  | 0
|  | 2 |  | Re-installation of Boat Catcher & Crane | 1043395.492 | 226897658.1421 | 1787322.24 |  | 0
|  | BOAT CATCHER SUB-TOTAL |  |  | 2363015.0752 | 239345616.0661 | 3147754.8 |  | 0
|  | DORMANLONG DPA | [6 empty] | 0
|  | B. OPTIONAL SCOPE | [6 empty] | 0
|  | Logistics (Land & Offshore) | [6 empty] | 0
|  |  |  | Marine Logistics |  |  |  |  | 0
|  |  |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System).)(Max 16 days for precomissioning/wellhead tie-in) | 177531.168 | 36098004.16 | 295885.28 |  | 0
|  | SUB-TOTAL |  |  | 177531.168 | 36098004.16 | 295885.28 |  | 0
|  | C. BOAT CATCHER & CRANE REMOVAL/REINSTALLATION SCOPE | [6 empty] | 0
|  | Re-installation of Boat Catcher & Crane | [6 empty] | 0
|  |  |  | Cost for DP-2 Construction & Diving Support Vessel | 330642.9598 | 67230735.1624 | 551071.5997 |  | 0
|  |  |  | Cost for diving services | 135647.3017 | 27581618.0192 | 226078.8362 |  | 0
|  |  |  | Cost of meals& bunks | 32112.4225 | 6529525.8984 | 53520.7041 |  | 0
|  | SUB-TOTAL |  |  | 498402.684 | 101341879.08 | 830671.14 |  | 0
|  | TOTAL |  |  | 5125362.8437 | 836833305.6568 | 7869078.6 |  | 12592.3989
| OPTIONAL SCOPE | 2 |  | DPB - MARINE LOGISTICS |  |  |  |  | 0
|  | 2.1 |  | Travel to Site, Spud & Pre-drill Logistics Scope (ALL DPB WELL HOOKUP) |  |  |  |  | 0
|  | 2.1.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 248700.096 | 50569019.52 | 414500.16 |  | 0
|  | 2.1.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.1.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 381600 | 77592000 | 636000 |  | 0
|  | 2.1.4 |  | Provision of SEWOP Support Vessel | 144000 | 29280000 | 240000 |  | 0
|  | 2.1.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 144000 | 29280000 | 240000 |  | 0
|  | 2.1.6 |  | Cost of meals & bunks (2 work crews for hookup , and allowance of 5 for SPDC POB) | 57600 | 11712000 | 96000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 1134900.096 | 230763019.52 | 1891500.16 |  | 0
|  | 2.2 |  | Boat Catcher/Crane Removal & Debris Survey (ALL DPB WELL HOOKUP) |  |  |  |  | 0
|  | 2.2.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) & Debris Survey | 248700.096 | 50569019.52 | 414500.16 |  | 0
|  | 2.2.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.2.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 381600 | 77592000 | 636000 |  | 0
|  | 2.2.4 |  | Provision of SEWOP Support Vessel | 144000 | 29280000 | 240000 |  | 0
|  | 2.2.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 144000 | 29280000 | 240000 |  | 0
|  | 2.2.6 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0
|  | 2.2.6.1 |  | Two LARS systems (for working diver and standby diver resp.) | 27516.672 | 5595056.64 | 45861.12 |  | 0
|  | 2.2.6.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.6.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 13758.336 | 2797528.32 | 22930.56 |  | 0
|  | 2.2.7 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 57600 | 11712000 | 96000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 1217450.112 | 247548189.44 | 2029083.52 |  | 0
0
|  | 2.3 |  | DPB Pre-Commissioning/Wellhead Tie-in Scope during Rig Move |  |  |  |  | 0
|  | 2.3.1 |  | Provision of DP2 PSV boat – For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes movement to site duration and spud + preloading in position of SEWOP & actual working days,. | 196887.576 | 40033807.12 | 328145.96 |  | 0
|  | 2.3.2 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) | 159000 | 32330000 | 265000 |  | 0
|  | 2.3.3 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0
|  | 2.3.4 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0
|  | 2.3.5 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0
|  | 2.3.6 |  | Cost of meals & bunks (1 work crew for hookup , and allowance of 5 for SPDC POB) | 45600 | 9272000 | 76000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 931587.576 | 189422807.12 | 1552645.96 |  | 0
|  | 2.4 |  | Boat Catcher Reinstallation |  |  |  |  | 0
|  | 2.4.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) | 196887.576 | 40033807.12 | 328145.96 |  | 0
|  | 2.4.2 |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0
|  | 2.4.3 |  | Cost of mob/demob (Including Group Maritime Assurance System) for Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling. SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. (Capacity to accomodate at least 45 people not including SEWOP crew) |  |  | 0 |  | 0
|  | 2.4.3 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.5 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0
|  | 2.4.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 21784.032 | 4429419.84 | 36306.72 |  | 0
|  | 2.4.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 45600 | 9272000 | 76000 |  | 0
|  |  |  | Sub-total with SEWOP 230 | 837939.672 | 170381066.64 | 1396566.12 |  | 0
0
|  |  |  | Crane Services |  |  |  |  | 0
|  | 1 |  | Crane Services | 355816.4344 | 10408657.415 | 389943.18 |  | 0
|  |  |  | Gas Lift Modification |  |  |  |  | 0
|  | 1 |  | Project Management | 88.9406 | 18143.8875 | 148.4288 |  | 0
|  | 2 |  | Procurement | 1491.9742 |  | 1491.9742 |  | 0
|  | 3 |  | Onshore Fabrication | 1728.6076 | 351483.5446 | 2881.0127 |  | 0
|  | 4 |  | Installation/Commissioning | 4828.0014 | 646957.8737 | 6949.1748 |  | 0
|  | Sub-Total |  |  | 363953.9583 | 11425242.7208 | 401413.7705 |  | 0
0
|  | 2.4 |  | Boat Catcher Reinstallation (DPA) |  |  |  |  | 0
|  | 2.4.1 |  | Provision of DP2 PSV boat - For Medevac/ERP – (Including premobilisation & Group Maritime Assurance System). Duration includes actual working days, jackdown + retrieval of SEWOP legs, movement from P1 + positioning in P2 and preloading in position (Allow for 3 Diving crew,6NOV Crew, 5 SPDC) | 196887.576 | 40033807.12 | 328145.96 |  | 0
|  |  |  | Provision of Class 230 SEWOP with a crane capacity as 20tons@20 m radius for both boat catcher and crane dismantling . SEWOP shall have adequate capacity to accommodate Diving spread for removal/reinstallation of boat catcher as specified in previous bid. Crane must be manriding certified. | 302100 | 61427000 | 503500 |  | 0
|  | 2.4.3 |  | Provision of SEWOP Support Vessel | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.4 |  | Provision of Crewboat (Including premobilisation & Group Maritime Assurance System). | 114000 | 23180000 | 190000 |  | 0
|  | 2.4.5 |  | Provision of a Diving Spread comprising: |  |  | 0 |  | 0
|  | 2.4.5.1 |  | Two LARS systems (for working diver and standby diver resp.) | 21784.032 | 4429419.84 | 36306.72 |  | 0
|  | 2.4.5.2 |  | One Dive Control (DC) container & Deck Decompression Chamber (DDC) with sufficeint HP air storage (16-cylinder, 50-liter quads) to deliver primary and secondary air supplies to divers and DDC & Sufficient Oxygen (16-cylinder, 50-liter quads) for decompression treatment (min. 90 m3) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.3 |  | One Machinery Container (with HP and LP compressors and any ancillary equipment) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.4 |  | Diver’s personnel equipment (umbilicals, dive hats, bail out cylinders etc.) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.5.5 |  | One offsite secondary DDC safe haven Deck Decompression Chamber (DDC) | 10892.016 | 2214709.92 | 18153.36 |  | 0
|  | 2.4.6 |  | Cost of meals & bunks (Allow for Boat Catcher/Crane Removal Crew, 3 Diving crew,6 NOV Crew, 5 SPDC) | 45600 | 9272000 | 76000 |  | 0
|  |  |  | Sub-total with SEWOP 200 | 837939.672 | 170381066.64 | 1396566.12 |  | 0
|  | TOTAL |  |  | 5323771.0863 | 1019921392.0808 | 8667775.6505 |  | 0
[7 empty] | 40230641.4655 |  | 7753482.1564
0
Marine Logisitics | [6 empty] | 3826539.34 |  | 3826539.34
DED | [6 empty] | 632656.64 |  | 632656.64
Technical Support service/QA QC | [6 empty] | 641362.18 |  | 641362.18
OTHERS (Catering, Hotel,travels, logistics) | [6 empty] | 66811.42 |  | 66811.42
5167369.58
PMT/OTHERS | [8 empty] | 0
SALARIES | [6 empty] | 2038937.73 |  | 2038937.73
TP OVERHEAD | [6 empty] | 3187943.41 |  | 744596.97
OTHERS (Catering, Hotel,Aviation,Travels, Government Levies) | [6 empty] | 404408.71 |  | 404408.71
3187943.41
16108795.1464

## Sheet1 (hidden)
| Rate | Days | Amount
SWOP | 16036.46 | 70 | 1122552.2 | 67 | 8400
PSV | 9800 | 70 | 686000 |  | 1696970
AHT | 13538.35 | 70 | 947684.5 |  | 5563.8361
Security | 15133.71 | 70 | 1059359.7 | 63 | 13963.8361
fuel | 5200 | 70 | 364000
4179596.4
9800
7485.29
6.53
7641.89
15133.71

## Sheet2 (hidden)
1002013576
| 31923451 | Supply sharp river sand as per work orde | 4894.253 | M3 | 14.44