## OP16 VS OP17 PROJECT COST
OP 16 VS OP17 PROJECT COST COMPARISON
Project |  | OP16 |  | OP17 |  | Savings
|  | 100% | Shell Share | 100% | Shell Share | 100% | Shell Share
Gbaran Nodal Compression | Capex | 300.16 | 90.048 | 205.7301 | 61.719 | 94.4299 | 28.329
| Opex | 8.815 | 2.6445 | 8.4718 | 2.5415 | 0.34324 | 0.10297
Total - GNC |  | 308.975 | 92.6925 | 214.2018 | 64.2605 | 94.7732 | 28.432
Phase 3A Enwhe | Capex | 556.001 | 166.8003 | 498.6013 | 149.5804 | 57.3997 | 17.2199
| Opex | 10.3393 | 3.1018 | 13.5702 | 4.0711 | -3.2309 | -0.96928
Total - PH3A(Enwhe) |  | 566.3402 | 169.9021 | 512.1715 | 153.6514 | 54.1688 | 16.2506
Gbaran Infil - 2A | Capex | 848.456 | 536.3988 | 717.0369 | 448.4328 | 131.419 | 87.966
| Opex | 13 | 3.9 | 13.7 | 4.11 | -0.7 | -0.21
Total GU 2A |  | 861.456 | 540.2988 | 730.7369 | 452.5428 | 130.719 | 87.756
Kolo Creek to Soku - 2B | Capex | 642.8273 | 402.2642 | 587.9 | 364.9 | 55 | 37.3642
| Opex | 12 | 3.6 | 12 | 3.6 | 0 | 0
Total GU 2B |  | 654.8273 | 405.8642 | 599.9 | 368.5 | 55 | 37.3642

## Sheet2 (hidden)
2B | PCP | Orig. GIP | Rev. GIP | CY Target | PLE | LE/ACT
Total Capex Lifecycle SS RV USD mln: | 0 | 458.248 | 458.248 | 398.132 | 383.132 | 359.372 | 60.116 | 15 | 23.76 | 38.76 | 58.1371 | 37.667 | 20.4701
- Total Capex Wells Lifecycle SS RV USD mln: | 0 | 0 | 0 | 156.079 | 156.08 | 160.305 | -156.079 | -0.001 | -4.225
- Total Capex Facilities Lifecycle SS RV USD mln: | 0 | 458.248 | 458.248 | 242.053 | 227.052 | 199.067 | 216.195 | 15.001 | 27.985
- Total Capex Non Wells Non Facilities LFC SS RV USD mln: | 0 | 0 | 0 | 0 | 0 | 0
Total Expex Lifecycle SS RV USD mln: | 0 | 0 | 0 | 0 | 0 | 0
- Total Expex Wells Lifecycle SS RV USD mln: | 0 | 0 | 0 | 0 | 0 | 0
- Total Expex Non Wells Lifecycle SS RV USD mln: | 0 | 0 | 0 | 0 | 0 | 0
Total Development Opex Lifecycle SS RV USD mln: | 0 | 7.951 | 7.951 | 7.732 | 7.732 | 7.731
Total Project Devt Expenditure Lifecycle SS RV USD mln: | 0 | 466.199 | 466.199 | 405.864 | 390.864 | 367.103
Other Costs: Feasex - Pre-FID Costs Lifecycle SS RV USD mln: | 0 | 0 | 0 | 4.132 | 4.132 | 103.008
73.1436
| PCP | Orig. GIP | Rev. GIP | CY Target | PLE | LE/ACT | 51.3529 | 44.6948 | 82.4488
Total Capex Lifecycle SS RV USD mln: | 0 | 560.505 | 564.111 | 526.268 | 496.47 | 441.5014 | 34.237 | 29.798 | 54.9686 | 84.7666 | 127.1436 | 37.667 | 89.4766
- Total Capex Wells Lifecycle SS RV USD mln: | 0 | 0 | 0 | 161.407 | 161.408 | 153.8508
- Total Capex Facilities Lifecycle SS RV USD mln: | 0 | 560.505 | 564.111 | 364.861 | 335.062 | 287.6506 | 34.234
- Total Capex Non Wells Non Facilities LFC SS RV USD mln: | 0 | 0 | 0 | 0 | 0 | 0
Total Expex Lifecycle SS RV USD mln: | 0 | 0 | 0 | 0 | 0 | 0
- Total Expex Wells Lifecycle SS RV USD mln: | 0 | 0 | 0 | 0 | 0 | 0
- Total Expex Non Wells Lifecycle SS RV USD mln: | 0 | 0 | 0 | 0 | 0 | 0
Total Development Opex Lifecycle SS RV USD mln: | 0 | 13.894 | 13.894 | 14.031 | 14.031 | 14.241 |  | 84.7666
Total Project Devt Expenditure Lifecycle SS RV USD mln: | 0 | 574.399 | 578.005 | 540.299 | 510.501 | 455.7424 |  | 127.1436
Other Costs: Feasex - Pre-FID Costs Lifecycle SS RV USD mln: | 0 | 0 | 0 | 10.221 | 10.131 | 10.131

## PDR Cost Q4 2016 (hidden)
PDR_Pmaster Reconciliation
Projects | Activities | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total | GIP
GU Infill 2A | [8 empty] | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
| Wells | 0 | 0 | 0 | 4.6363 | 8.3987 | 23.9168 | 53.0242 | 2014 2014: 69.1847; 2015 2015: 46.2505; 2016 2016: 42.2725; 2017 2017: 7.45 | 255.1337 | 259.5 | 250.6375 | 261.2079 | 6.0743
| Facilties | 0.71689 | 3.741 | 0.41715 | 6.5226 | 9.3366 | 0.042647 | 31.4318 | 2014 2014: 97.1178; 2015 2015: 171.794; 2016 2016: 90.7829; 2017 2017: 94.6888; 2018 2018: 40.688 | 547.2801 | 605.8 | 585.11 | 543.2062 | -4.0739
| PMT | [6 empty] | 11.219 | 2014 2014: 7.6424; 2015 2015: 9.9394; 2016 2016: 11.9113; 2017 2017: 5.01; 2018 2018: 0.32 | 46.0421 | 57.9 | 57.9 | 48.7308 | 2.6887
| Opex ( SCD) | [7 empty] | 2015 2015: 0.3; 2016 2016: 5.3; 2017 2017: 6.3; 2018 2018: 1.1 | 13 | 13.7 | 13.7 | 13 | 0
| Sub- Total | 0.71689 | 3.741 | 0.41715 | 11.1589 | 17.7352 | 23.9594 | 95.675 | 173.9449 | 228.2839 | 150.2668 | 113.4488 | 42.108 | 0 | 0 | 0 | 0 | 861.456 | 936.9 | 907.3475 | 866.145 | 4.6891
10.131 | bar: 2015 2015 to 2022 2022
Projects | Activities | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total | GIP
GU Infill 2A Shell Share | [8 empty] | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
PreFID Cost to be backed out of Prior year cost and treated as Opex | Wells | 0 | 0 | 0 | 1.3909 | 2.5196 | 15.9453 | 35.3512 | 2014 2014: 46.1255; 2015 2015: 30.8352; 2016 2016: 28.1831; 2017 2017: 4.9669 | 165.3177 | 167.1 | 173.0086 | 250.6375
| Facilties | 0.21507 | 1.1223 | 0.12515 | 1.9568 | 2.801 | 0.028433 | 20.9556 | 2014 2014: 64.7484; 2015 2015: 114.535; 2016 2016: 60.525; 2017 2017: 63.129; 2018 2018: 27.1267 | 357.2684 | 389.4 | 403.8869 | 20.699
| PMT | 0 | 0 | 0 | 0 | 0 | 0 | 3.3657 | 2014 2014: 2.2927; 2015 2015: 2.9818; 2016 2016: 3.5734; 2017 2017: 1.503; 2018 2018: 0.096 | 13.8126 | 17.8 | 17.37
| Opex ( SCD) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014 2014: 0; 2015 2015: 0.09; 2016 2016: 1.59; 2017 2017: 1.89; 2018 2018: 0.33 | 3.9 | 4.1 | 4.11
| Sub- Total | 0.21507 | 1.1223 | 0.12515 | 3.3477 | 5.3206 | 15.9737 | 59.6725 | 113.1666 | 148.4421 | 93.8715 | 71.489 | 27.5527 | 0 | 0 | 0 | 0 | 540.2988 | 578.4
128.2572
[9 empty] | 10.2207 | 208.9077 | 64.0984 | 64.632 | 27.2227 | 0
K2S 2B |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells | 0 | 0 | 0 | 0.4312 | 7.1477 | 2.7361 | 59.6633 | 63.7963 | 0.42798 | 64.4734 | 8.94 |  |  | 34.0714 |  |  | 241.6873 | 244 |  | 231.5125 | -10.1748
| Facilties | 0.21414 | 1.1174 | 0.1246 | 1.9483 | 2.7888 | 6.2039 | 17.7573 | 60.2286 | 56.0073 | 96.3653 | 100.412 | [5 empty] | 343.1677 | 426.4 |  | 341.6583 | -1.5094
| PMT | 2013: 9.0437; 10.2207 2014: 16.4185; 208.9077 2015: 16.0293; 64.0984 2016: 8.6709; 64.632 2017: 7.81 | 57.9723 | 60 |  | 59.9006 | 1.9283
| Opex ( SSCD) | 64.0984 2016: 6; 64.632 2017: 3; 27.2227 2018: 3 | 12 | 12 |  | 12 | 0
| Sub- Total | 0.21414 | 1.1174 | 0.1246 | 2.3795 | 9.9366 | 8.9399 | 86.4643 | 140.4434 | 72.4645 | 175.5095 | 120.162 | 3 | 0 | 34.0714 | 0 | 0 | 654.8273 | 742.4 |  | 645.0715 | -9.7559
87.5727
K2S 2B - Shell Share |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells | 0 | 0 | 0 | 0.12936 | 2.1443 | 1.8241 | 39.7775 | 42.533 | 0.28534 | 30.9771 | 12.022 | 5.9456 | 0 | 22.7154 |  |  | 158.3537 | 162.7 | 162.504
| Facilties | 0.064241 | 0.33523 | 0.037381 | 0.58449 | 0.83665 | 4.1361 | 11.8388 | 40.1544 | 37.3401 | 51.6043 | 47.0757 | 22.4553 | 0 | 0 |  |  | 216.4627 | 282 | 283.9824
| PMT | 0 | 0 | 0 | 0 | 0 | 0 | 2.7131 | 4.9256 | 4.8088 | 2.6013 | 2.343 | [5 empty] | 17.3917 | 18 | 18
| Opex ( SSCD) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0.9 | 0.9 |  |  |  |  | 3.6 | 3.6 | 3.6
| Sub- Total | 0.064241 | 0.33523 | 0.037381 | 0.71385 | 2.981 | 5.9603 | 54.3294 | 87.613 | 42.4342 | 86.9826 | 62.3407 | 29.3009 | 0 | 22.7154 | 0 | 0 | 395.8081 | 466.3
84.42
[6 empty] | 4.1317 |  |  |  | 105.9169 | 54.2055 | 49.4187 | 22.4553
Soku NAG |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells
| Facilties | 2.2158 | 0.44649 | 0 | 0 | 0 | 1.3852 | 14.3836 | 32.8685 | 29.304 | 4.9785 | [6 empty] | 85.5821 | 91.6 |  | 85.5821 | 0
| PMT | 4.1317 2013: 1.0698; 4.1317 2014: 1.7848; 105.9169 2015: 0.75566 | 3.6103 | 4.14 |  | 3.6103 | 0
| Opex ( SSCD) | [16 empty] | 0 | 2.4 |  | 0 | 0
| Sub- Total | 2.2158 | 0.44649 | 0 | 0 | 0 | 1.3852 | 15.4534 | 34.6534 | 30.0597 | 4.9785 | 0 | 0 | 0 | 0 | 0 | 0 | 89.1925 | 98.14 |  | 89.1925 | 0
Soku NAG-Shell Share |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells
| Facilties | 0.66473 | 0.13395 | 0 | 0 | 0 | 0.92351 | 9.5896 | 21.9135 | 19.537 | 3.3192 | [6 empty] | 56.0814 | 61.0697
| PMT | 2013: 0.32095; 2014: 0.53545; 2015: 0.2267 | 1.0831 | 1.242
| Opex ( SSCD) | [16 empty] | 0 | 0.72
| Sub- Total | 0.66473 | 0.13395 | 0 | 0 | 0 | 0.92351 | 9.9105 | 22.4489 | 19.7637 | 3.3192 | 0 | 0 | 0 | 0 | 0 | 0 | 57.1645 | 63.0317
112.6
|  | 2015: 53.0466 |  |  | 132.9
9.5
North Bank |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  |  | 22.4
Pmaster | Wells | [18 empty] | 141.3
| Facilties | 2014: 20.817; 2015: 59.4782; 2016: 34.334; 2017: 18.2708 | 132.9 | 151.9 |  | 147.7857 | 14.8857
| PMT | 2014: 1.1864; 2015: 3.3704; 2016: 2.393; 2017: 2.5502 | 9.5 | 9.7 |  | 9.2743 | -0.22569
| Opex ( SSCD) | [16 empty] | 0 | 3.6 |  | 3.6 | 3.6
| Sub- Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.0034 | 62.8486 | 36.727 | 20.821 | 0 | 0 | 0 | 0 | 0 | 142.4 | 165.2 |  | 160.66 | 18.26
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.0034 | 62.8486 | 36.727 | 20.821 | 0 | 0 | 0 | 0 | 0 | 142.4 |  |  | 114.9
4.1
North Bank - Shell Share |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  |  | 112.6 | 132.3
Pmaster | Wells
| Facilties | 2014: 13.8787; 2015: 39.6541; 2016: 22.8905; 2017: 12.1811 | 88.6044 |  |  | 112.6
| PMT | 2014: 0.35592; 2015: 1.0111; 2016: 0.7179; 2017: 0.76507 | 2.85 |  |  | 32.3048
| Opex ( SSCD) | 2017: 0 | 0 |  |  | 50.5755
| Sub- Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2346 | 40.6652 | 23.6084 | 12.9462 | 0 | 0 | 0 | 0 | 0 | 91.4544 | 0 | 19.6
[10 empty] | 54.8999 | 23.6084 | 12.9462 | LC
|  | 2017: 1.6534; 2018: contingency |  |  |  | 32.3048
Gbaran Nodal |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells | [16 empty] | 0 |  |  | 0 | 0
| Facilties | 1.6534 2017: 22.47; contingency 2018: 89.45; contingency 2019: 109.47; contingency 2020: 49.77 | 271.16 | 364.81 |  | 271.1518 | -0.0082324
| PMT | 1.6534 2017: 4.5; contingency 2018: 11.92; contingency 2019: 10.28; contingency 2020: 2.3 | 29 |  |  | 28.9929 | -0.0070501
| Pre FID | 2014: 1.703; 2015: 0.364; 2016: 0.748 | 2.815 |  |  | 2.815 | 0
| Opex ( SSCD) | contingency 2018: 1; contingency 2019: 2.7; contingency 2020: 2.3 | 6 |  |  | 6 | 0
| Sub- Total | 2014: 1.703; 2015: 0.364; 2016: 0.748; 1.6534 2017: 26.97; contingency 2018: 102.37; contingency 2019: 122.45; contingency 2020: 54.37; contingency 2021: 0; contingency 2022: 0 | 308.975 | 364.81 |  | 308.9597 | -0.015283
|  | contingency 2019: 16.45; contingency 2020: 16.45 | 92.6925 | contingency
Gbaran Nodal-Shell Share |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells
| Facilties | 2017: 6.741; 2018: 26.835; 16.45 2019: 32.841; 16.45 2020: 14.931 | 81.348
| PMT | 2017: 1.35; 2018: 3.576; 16.45 2019: 3.084; 16.45 2020: 0.69 | 8.7
| Pre FID | 2014: 0.5109; 2015: 0.1092; 2016: 0.2244 | 0.8445
| Opex ( SSCD) | 2018: 0.3; 16.45 2019: 0.81; 16.45 2020: 0.69 | 1.8
| Sub- Total | [6 empty] | 0 | 0.5109 | 0.1092 | 0.2244 | 8.091 | 30.711 | 36.735 | 16.311 | 0 | 0 | 92.6925 | 0
|  | 2015: 0.6201; 2017: 8.091; 2018: 30.411; 16.45 2019: 35.925; 16.45 2020: 15.621 |  | contingency
Phase 3A Abasere |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells | 15.621 2020: 12; 15.621 2021: 122.4405; 15.621 2022: 28.4745 | 162.915 | 150.8 |  | 163.4844 | 0.56939
| Facilties | 30.411 2018: 29.847; 35.925 2019: 75.5982; 15.621 2020: 78.5096; 15.621 2021: 51.3264; 15.621 2022: 9.6893 | 244.9705 | 475.88 | revised for location prep | 244.0595 | -0.911
| PMT | 30.411 2018: 6.16; 35.925 2019: 11.51; 15.621 2020: 11.31; 15.621 2021: 9.17; 15.621 2022: 2.51 | 40.66 |  |  | 40.6659 | 0.0059148
| Pre FID | 2014: 0.096245; 0.6201 2015: 0.79597; 0.6201 2016: 1.8436; 8.091 2017: 0.389 | 3.1248 |  |  | 3.7358 | 0.611
| Opex ( SSCD) | 35.925 2019: 1; 15.621 2020: 1.5; 15.621 2021: 1.725; 15.621 2022: 1.3 | 5.525 | 12.32 |  | 5.525 | 0
| Sub- Total | 2014: 0.096245; 0.6201 2015: 0.79597; 0.6201 2016: 1.8436; 8.091 2017: 0.389; 30.411 2018: 36.007; 35.925 2019: 88.1082; 15.621 2020: 103.3196; 15.621 2021: 184.6619; 15.621 2022: 41.9738 | 457.1954 | 639 | 45.9 | 457.4707 | 0.2753
|  | 15.621 2021: 22.95; 15.621 2022: 22.95 | 137.1586 | contingency
Phase 3A Abasere - Shell Share |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells | 2020: 3.6; 22.95 2021: 36.7321; 22.95 2022: 8.5424 | 48.8745
| Facilties | 2018: 8.9541; 2019: 22.6795; 2020: 23.5529; 22.95 2021: 15.3979; 22.95 2022: 2.9068 | 73.4912
| PMT | 2018: 1.848; 2019: 3.453; 2020: 3.393; 22.95 2021: 2.751; 22.95 2022: 0.753 | 12.198
| Pre FID | 2014: 0.028874; 2015: 0.23879; 2016: 0.55308; 2017: 0.1167 | 0.93744
| Opex ( SSCD) | 2019: 0.3; 2020: 0.45; 22.95 2021: 0.5175; 22.95 2022: 0.39 | 1.6575
| Sub- Total | 2014: 0.028874; 2015: 0.23879; 2016: 0.55308; 2017: 0.1167; 2018: 10.8021; 2019: 26.4325; 2020: 30.9959; 22.95 2021: 55.3986; 22.95 2022: 12.5922 | 137.1586 |  | 13.77
|  | 22.95 2021: 6.885; 22.95 2022: 6.885 |  | contingency
[13 empty] | 10.8021 | 26.1325 | 26.9459 | 18.1489 | 3.6598
[10 empty] | 0.26766 | 0.55308 | 0.1167 | 0 | 0.3 | 0.45 | 0.5175 | 0.39
[12 empty] | 8.091 | 30.411 | 35.925 | 15.621
Phase 3A Enwhe |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total
Pmaster | Wells | 30.411 2018: 10; 35.925 2019: 50.0167; 15.621 2020: 89.3183; 15.621 2021: 55.5559 | 204.891 | 176 |  | 204.8933 | 0.0023063
| Facilties | 8.091 2017: 36.736; 30.411 2018: 115.6057; 35.925 2019: 85.5666; 15.621 2020: 53.4858; 15.621 2021: 14.1459 | 305.54 | 511.57 | revised for location prep | 304.804 | -0.736
| PMT | 8.091 2017: 6.16; 30.411 2018: 10.51; 35.925 2019: 11.11; 15.621 2020: 11.37; 15.621 2021: 6.42 | 45.57 |  |  | 45.5659 | -0.0040852
| Pre FID | 2015: 0.73026; 2016: 2.87; 8.091 2017: 0.264 | 3.8643 |  |  | 4.6003 | 0.736
| Opex ( SCD) | 30.411 2018: 1; 35.925 2019: 1.675; 15.621 2020: 2; 15.621 2021: 1.8 | 6.475 | 13.83 |  | 6.475 | 0
| Sub- Total | 2014: 0; 2015: 0.73026; 2016: 2.87; 8.091 2017: 43.16; 30.411 2018: 137.1157; 35.925 2019: 148.3683; 15.621 2020: 156.1741; 15.621 2021: 77.9218; 15.621 2022: 0 | 566.3402 | 701.4 |  | 566.3384 | -0.0017789
|  | 15.621 2020: 26.8; 15.621 2021: 26.8 |  | contigency
[18 empty] | 169.9021 |  | 0.736
Phase 3A Enwhe-Shell Share |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | Total |  | 0.264
Pmaster | Wells | 2015: 0; 2016: 0; 2017: 0; 2018: 3; 2019: 15.005; 2020: 26.7955; 2021: 16.6668; 2022: 0 | 61.4673
| Facilties | 2015: 0; 2016: 0; 2017: 11.0208; 2018: 34.6817; 2019: 25.67; 2020: 16.0457; 2021: 4.2438; 2022: 0 | 91.662
| PMT | 2015: 0; 2016: 0; 2017: 1.848; 2018: 3.153; 2019: 3.333; 2020: 3.411; 2021: 1.926; 2022: 0 | 13.671
| Pre FID | 2015: 0.21908; 2016: 0.861; 2017: 0.0792; 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2022: 0 | 1.1593
| Opex ( SCD) | 2015: 0; 2016: 0; 2017: 0; 2018: 0.3; 2019: 0.5025; 2020: 0.6; 2021: 0.54; 2022: 0 | 1.9425
| Sub- Total | 2014: 0; 2015: 0.21908; 2016: 0.861; 2017: 12.948; 2018: 41.1347; 2019: 44.5105; 2020: 46.8522; 2021: 23.3765; 2022: 0 | 169.9021
[12 empty] | 12.8688 | 37.8347 | 29.003 | 19.4567 | 6.1698
|  | 2020: 8.04; 2021: 8.04 |  | contigency
EPU PHASE 2 |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Pmaster | Wells | 2019: 7.64; 2020: 29.31; 2021: 116.6097; 2022: 100.8555 | 254.4152
| Facilties | 2019: 31.54; 2020: 120.96; 2021: 135.31; 2022: 61.11 | 348.92
| PMT | [16 empty] | 0
| Pre FID | 2017: 0.017; 2018: 0.355; 2019: 1.2535 | 1.6255
| Opex ( SCD) | [16 empty] | 0
| Sub- Total | 0 | 0.017 | 0.355 | 40.4335 | 150.27 | 251.9197 | 161.9655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604.9607
contigency
EPU PHASE 2-Shell Share |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Pmaster | Wells | 2019: 2.292; 2020: 8.793; 2021: 34.9829; 2022: 30.2567 | 76.3246
| Facilties | 2019: 9.462; 2020: 36.288; 2021: 40.593; 2022: 18.333 | 104.676
| PMT | [16 empty] | 0
| Pre FID | 2017: 0.0051; 2018: 0.1065; 2019: 0.37605 | 0.48765
| Opex ( SCD) | [16 empty] | 0
| Sub- Total | 0 | 0.0051 | 0.1065 | 12.13 | 45.081 | 75.5759 | 48.5897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181.4882
contigency
GBARAN - SOKU CAPACITY MAXIMISATION PROJECT |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Pmaster | Wells | [16 empty] | 0
| Facilties | 2019: 103.2; 2020: 68.8 | 172
| PMT | [16 empty] | 0
| Pre FID | 2017: 1.372; 2018: 1.457 | 2.829
| Opex ( SCD) | [16 empty] | 0
| Sub- Total | 2023: 0; 2024: 0; 2025: 0; 2026: 0; 2027: 0; 2028: 0; 2029: 0; 2030: 0; 2031: 0 | 174.829
contigency
GBARAN - SOKU CAPACITY MAXIMISATION PROJECT -Shell Share |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Pmaster | Wells | 2031: 0 | 0
| Facilties | 2019: 30.96; 2020: 20.64; 2031: 0 | 51.6
| PMT | 2031: 0 | 0
| Pre FID | 2017: 0.4116; 2018: 0.4371; 2031: 0 | 0.8487
| Opex ( SCD) | 2031: 0 | 0
| Sub- Total | 0 | 0.4116 | 0.4371 | 30.96 | 20.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.4487
Phase 3B Uzu |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Pmaster | Wells | 2020: 52.2815; 2021: 72.4603; 2022: 28.156; 2023: 2.9 | 155.7978 |  | 46.7393
| Facilties | 2019: 55.9; 2020: 90.7; 2021: 63.1 | 209.7 | 568 | 62.91
| PMT | [16 empty] | 0 |  | 0
| Pre FID | 2017: 1.81; 2018: 0.25 | 2.06 |  | 0.618
| Opex ( SSCD) | 2017: 0; 2018: 0; 2019: 1; 2020: 1; 2021: 1; 2022: 0.83621 | 3.8362 |  | 1.1509
| Total | 0 | 1.81 | 0.25 | 56.9 | 143.9815 | 136.5603 | 28.9922 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371.394 | 568 | 111.4182
111.4182 | bar: 2024 to 2031
|  | 2021: 16.1; 2022: 16.1 |  | 371.394 | 0
Phase 3B Uzu |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Pmaster | Wells | 2020: 15.6845; 16.1 2021: 21.7381; 16.1 2022: 8.4468; 16.1 2023: 0.87 | 46.7393
| Facilties | 2019: 16.77; 2020: 27.21; 16.1 2021: 18.93 | 62.91
| PMT | [16 empty] | 0
| Pre FID | 2017: 0.543; 2018: 0.075 | 0.618
| Opex ( SSCD) | 2019: 0.3; 2020: 0.3; 16.1 2021: 0.3; 16.1 2022: 0.25086 | 1.1509
| Total | 0 | 0.543 | 0.075 | 17.07 | 43.1945 | 40.9681 | 8.6977 | 0.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.4182 | 0
1.77
Note on N88: Akinlami, Oluwakemi O SPDC-FPT/PO: Additional cost of $0.611 is the difference btween the original prefid cost and what was supported in OP16(2017)
Note on M90: Akinlami, Oluwakemi O SPDC-FPT/PO: adjusted for OP16 supported number $389k
Note on M107: Akinlami, Oluwakemi O SPDC-FPT/PO: Additional cost of $0.736 is the difference btween the original prefid cost and what was supported in OP16(2017). Prefid date for Enwhe now Feb17
Note on M109: Akinlami, Oluwakemi O SPDC-FPT/PO: adjusted for OP16 supported number $264k

## Sheet1 (hidden)
Uzu | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | total | No Pre-FID Cost
Facilities+Wells+PMT | 0 | 0 | 0 | 55.9 | 142.9815 | 135.5603 | 28.156 | 2.9 | 365.4978 | No Production on infrastructural projects
Opex Pre-FID | 0 | 1.81 | 0.25 | 0 | 0 | 0 | 0 | 0 | 2.06 | No Production on infrastructural projects
Opex SCD | 0 | 0 | 0 | 1 | 1 | 1 | 0.83621 | 0 | 3.8362 | No Production on infrastructural projects
| 0 | 1.81 | 0.25 | 56.9 | 143.9815 | 136.5603 | 28.9922 | 2.9 | 371.394 | No Production on infrastructural projects
No Production on pipeline construction project

## Pre FID Costs (hidden)
Projects | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | Total
Gbaran Ubie Infill Project - 2A | 0.71689 | 3.741 | 0.41715 | 6.5226 | 9.3366 | 0 | [6 empty] | 20.7342
Gbaran Ubie K2S Project - 2B | 0.21414 | 1.1174 | 0.1246 | 1.9483 | 2.7888 | [7 empty] | 6.1933
Phase 3A Abasere | [7 empty] | 0.096245 | 0.79597 | 1.8416 | 0.34 | 0.66 | 3.7338
Phase 3A Enwhe | [8 empty] | 0.73026 | 2.8698 | 3.54 |  | 7.1401
Gbaran Nodal | [7 empty] | 1.703 | 0.364 | 0.748 | 0.543 |  | 3.358

## Evidence
| GNC | ENWHE | 2A | 2B
Banked 1 | 5.84 | 15.75 | 44.984 | 22.49
Banked 2 | 9 | 12 | 9 | 15
Banked 3 | 5.383 | 8.25 | 3.3
Total Banked in 2017 | 20.223 | 36 | 57.284 | 37.49
OP16 vs OP17 variance | 94.4299 | 57.3997 | 131.419 | 55
Portion Baked into OP17 | 74.2069 | 21.3997 | 74.135 | 17.51
Portion captured in #1776, 1777, 6340 & 6342 | 39.777 | 19 | 20 | 20
Additional to mop up | 34.4299 | 2.3997 | 54.135 | -2.49