## Slide 1: Dispose off all 19 SPDC Owned inshore vessels by Q4 2021 (I-0154355)
L2 date
Initiative lead
Chris Zacchaeus
Current stage gate
L1
Initiative sponsor
Victor Ojabo
L3 date
TBD
14/05/2021
Problem statement
  As of April 2021, SPDC owns and operates a fleet of 19 vessels – 6 houseboats, 3 tug-boats, 4 fuel barges, 3 ramp barges, 2 dumb barges certified for radioactive materials and 1 water barge. 11 of the vessels are over 40 years old, while 8 vessels are more than 37 years old on average. These vessels are old, with hulls in poor condition and require over $1.8mln annually for dry docking and maintenance. In addition, the 19 vessels are the source of repeated complaints from customers and the subject of high findings in HSSE and Duty of Care for personnel housed on the houseboats- This brings to bear the inherent high integrity issues associated with the operations of these vessels. Besides NIMASA refusal to renew statutory certificates except SPDC registers as shipping company- SPDC does not intend to operate as a shipping company
Initiative description
  This initiative seeks to identify the disposal process, dispose of all 19 vessels by scrapping, sell off or hybrid of the two by the end of Q3 2021 to eliminate operations and routine maintenance costs, insurance costs, drydock costs for fleet of aged and all associated technical and non- technical HSSE risks.
Estimate impact
I-0154355
Wave ID
Location(s)
SPDC – Shell-owned Marine vessels
Workstream
Opex
Key stakeholders
Decisions needed to mature
What does success look like at the end of the 3-week sprint
  High level assumptions – Opportunity to save US$ 2.2mln budgeted for dry docking in 2021 and N201mln for operate and maintenance cost.
  TBA – Amount accrued from sale of 19 vessels.
  Project Sponsor: Victor Ojabo
  Transformation coach: Alphonsus Akaka
  Implementation Lead: Chris Zacchaeus
  Project Team: Mukhtar Sani, Letty Chukwueke, Olatunji Adefuye & Lazarus Enwereuzor
  Go or No go on the following opportunities:
    Dispose all 19 vessels - SPDC - Asset Managers, PS Mgr. and CP Leadership approval
    NAPIMS approval
  Progression to L2 and aspire L3
  Secure management endorsement on identified strategy for disposing of the vessels
  Clear implementation plan with potential risks and mitigations

## Slide 2: Cost lever tree – Disposal of 19 SPDC Vessels
Categories
Drivers
Driver Tree: Dispose off all 19 SPDC Owned inshore vessels by End Q3 2021 (I-0154355)
Annual savings net Savings - $1.1m + TBD
$46k (one-off)
$2.5m
Hire 10 replacement 3rd party vessels
Hire 2 00 9 vessels on call off for 322days (7 vessels removed from count )
Hire 10 vessels steady state
Annual Rate $2.2m
Annual Rate $268k
Demob 12 Vessels and Mobilise 10 Vessels
Sell off all 19 vessels
TBD
Drydocking
$3.6m
Operate & Maintain
Annual Rate - $1.4m
Residual value from sale of 19 vessels
TBD
Annual Rate - $2.2m
Maintain status quo
(19 vessels)
Drydocking
Annual spent $3.6m
+ Noncompliance issues
Operate & Maintain
-ve
Annual Rate - $2.2m
Annual Rate - $1.4m
Notes: Savings in 2021
Cost saving of drydock - $2.2m
Cost saving of operate & maintain for 3 months in 2021 - $350k
Less cost of hiring 10 steady state vessels for 3 months in 2021 - $550k
Less cost of hiring 2 call off vessels for 3 months in 2021 - $67K
Less cost of demobilization & mobilization of 12 vessels - $46k
Less Cost of Marine Warranty Surveyors – 100k
Total savings for 2021 = $1.78m