## Sprint Plan
WSL | Finance Lead | Item No. | Description of Action | Start Date | End Date | Action Party | Help required/Threat | Completion Status (Open, Inprogress OR Completed)
|  | 1 | Create initiative charter, Prepare 2mins pitch Engage Land logistics team for lateral learning on vehicle disposal process | 27/04/21 | 28/04/21 | Chris Z |  | Closed
|  | 2 | Developed daily plan Complete weekly cadence presentation | 28/04/21 | 29/04/21 | Chris Z |  | Closed
|  | 3 | Onboard CP and BGR team members Start review of financial impact of initiative | 29/04/21 | 30/04/21 | Chris Z | Nomination of personnel by CP & BGR managers | Closed
|  | 4 | Continue computation of vessel disposal financials, Obtain flowchart for vehicle disposal from Land transport & start slide prep | 30/04/21 | 2021-04-05 | Chris Z |  | Closed
|  | 5 | Complete financial impact of vessel disposal, Build business case for scrap versus sale or hybrid and Prepare for cadence | 2021-05-05 | 2021-05-06 | Chris Z |  | Closed
|  | 6 | Determine absolute cost of replacing/hiring 10 steady state vessels and 2 call-up vessels Determine cost of Demob of old vessels -50% complete Achieve 75% completion of slide pack for Tenderboard and NAPIMS | 2021-05-06 | 2021-05-07 | Chris Z |  | Closed
|  | 7 | Complete cost of demob of old vessels & mobiliztio of 10 steady state vessels review and update decision tree Complete MCB and NAPIMS engagement slides pack | 2021-05-07 | 2021-05-10 | Chris Z |  | Closed
|  | 8 | Joint review of mob-demob cost and share justification for disposal with LT Start implementation plan | 2021-05-10 | 2021-05-11 | Chris Z |  | Closed
|  | 9 | Determine cost of engaging Marine Warranty surveyors and seek approval via email | 2021-05-11 | 2021-05-14 | Chris Z | Approval to proceed with initiative and engagement of MWS | Open
|  | 10 | Engagement of marine warranty surveyor (External Valuers)/Raise PO | 2021-05-24 | 2021-05-31 | Tunji/CH | Approval to provide budget to engage MWS
|  | 11 | Alignment on scrapping or sell off | 2021-06-01 | 2021-06-14 | Tunji/ Lazarus
|  | 12 | Dvelop Part A + Part B for presentation to MCB | 15/06/21 | 21/06/21 | Tunji/ Lazarus
|  | 13 | MCB Presentation | 2021-06-21 | 2021-06-25 | Tunji/Lazarus
|  | 14 | Request for Engagement and Presentation to NAPIMS and letter to NAPIMS for approval | 2021-06-28 | 2021-07-05 | Tunji/Letty
|  | 15 | Presentation to NAPIMS for justification & NAPIMS approvals | 2021-07-12 | 2021-07-31 | Tunji/Letty
|  | 16 | Tender for bidding or scrapping process/Award | 2021-08-02 | 2021-08-31 | Tunji/Austin Onamade
|  | 17 | Commence withdrawal & replacement program for the vessels | 2021-08-02 | 2021-08-31 | Chris Z
|  | 18 | Payment and evacuation | 2021-09-01 | 2021-09-30

## Post Sprint Plan
WSL | Finance Lead | Item No. | Description of Action | Start Date | End Date | Action Party | Help required/Threat | Completion Status (Open, Inprogress OR Completed)
|  | 1 | Create initiative charter, Prepare 2mins pitch Engage Land logistics team for lateral learning on vehicle disposal process | 27/04/21 | 28/04/21 | Chris Z |  | Closed
|  | 2 | Developed daily plan Complete weekly cadence presentation | 28/04/21 | 29/04/21 | Chris Z |  | Closed
|  | 3 | Onboard CP and BGR team members Start review of financial impact of initiative | 29/04/21 | 30/04/21 | Chris Z | Nomination of personnel by CP & BGR managers | Closed
|  | 4 | Continue computation of vessel disposal financials, Obtain flowchart for vehicle disposal from Land transport & start slide prep | 30/04/21 | 2021-04-05 | Chris Z |  | Closed
|  | 5 | Complete financial impact of vessel disposal, Build business case for scrap versus sale or hybrid and Prepare for cadence | 2021-05-05 | 2021-05-06 | Chris Z |  | Closed
|  | 6 | Determine absolute cost of replacing/hiring 10 steady state vessels and 2 call-up vessels Determine cost of Demob of old vessels -50% complete Achieve 75% completion of slide pack for Tenderboard and NAPIMS | 2021-05-06 | 2021-05-07 | Chris Z |  | Closed
|  | 7 | Complete cost of demob of old vessels & mobiliztio of 10 steady state vessels review and update decision tree Complete MCB and NAPIMS engagement slides pack | 2021-05-07 | 2021-05-10 | Chris Z |  | Closed
|  | 8 | Joint review of mob-demob cost and share with LT Start implementation plan | 2021-05-10 | 2021-05-11 | Chris Z |  | Closed
|  | 9 | Determine cost of engaging Marine Warranty surveyors and seek approval via email | 2021-05-11 | 2021-05-14 | Chris Z |  | Open