## JAN'23-COST SAVINGS EAST
[5 empty] | DAILY RATE |  |  | MARINE EAST POTENTIAL SAVINGS.
S/N | VESSEL NAMES | TYPE | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | N | $ | Remark
1 | MV-EBINYO-II | TUGBOAT | WELLS | SOKU WELL 31 | 70327.98 | 654.08 | 2022-11-14 | 2023-01-13 | 2023-01-31 | 18 | 1265903.64 | 11773.44 | Saving is achieved as vessel was demobbed before planned demobilization date of 31st Jan.2023
2 | MV-ONOME | TUGBOAT |  |  | 70327.98 | 654.08 | 2022-11-16 | 2023-01-16 | 2023-01-31 | 15 | 1054919.7 | 9811.2 | Saving is achieved as vessel was demobbed before planned demobilization date of 31st Jan.2023
3 | DOUBRA-1 | RAMP BARGE |  |  | 32572.94 | 302.94 | 2022-11-14 | 2023-01-18 | 2023-01-31 | 13 | 423448.22 | 3938.22 | Saving is achieved as vessel was demobbed before planned demobilization date of 31st Jan.2023
4 | OGHENEYOMA | WATER BARGE |  |  | 35534.25 | 330.48 | 2022-11-14 | 2023-01-13 | 2023-01-31 | 18 | 639616.5 | 5948.64 | Saving is achieved as vessel was demobbed before planned demobilization date of 31st Jan.2023
5 | MV-NENEMEN-II | TUGBOAT | OABP | SOKU F/S | 70327.98 | 654.08 | 2022-10-17 | 2023-01-13 | 2023-01-15 | 2 | 140655.96 | 1308.16 | Saving is achieved as vessel was demobbed before planned demobilization date of 15th Jan.2023
6 | MV-EDOSE | TUGBOAT |  |  | 70327.98 | 654.08 | 2023-01-11 | 2023-01-13 | 2023-01-15 | 2 | 140655.96 | 1308.16 | OPTIMIZED TO DE-MOB PACIFIC-1 HOUSEBOAT FROM SOKU GP AFTER COMPLETION OF OABP ACTIVITY. ELIMINATING NEED FOR A NEW TUGBOAT FOR HB DEMOB
7 | PACIFIC-1 | 40 MAN HOUSEBOAT |  |  | 98459.33 | 915.71 | 2022-10-17 | 2023-01-13 | 2023-01-15 | 2 | 196918.66 | 1831.42 | Saving is achieved as vessel was demobbed before planned demobilization date of 15th Jan.2023
[10 empty] | 70 | 3862118.64 | 35919.24
Note on B3: Egejuru, Ebere SPDC-UPO/G/USLM: Saving is achieved as vessel was demobbed before Actual demobilization date of 31st Jan.2023
Note on B4: Egejuru, Ebere SPDC-UPO/G/USLM: Saving is achieved as vessel was demobbed before Actual demobilization date of 31st Jan. 2023
Note on B5: Egejuru, Ebere SPDC-UPO/G/USLM: Saving is achieved as vessel was demobbed before Actual demobilization date of 31st Jan. 2023
Note on B6: Egejuru, Ebere SPDC-UPO/G/USLM: Saving is achieved as vessel was demobbed before Actuual demobilization date of 31st Jan. 2023
Note on B7: Egejuru, Ebere SPDC-UPO/G/USLM: Saving is achieved as vessel was demobbed before Actual demobilization date of 15th Jan. 2023
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RE-CYCLE TO DE-MOB PACIFIC-1 HOUSEBOAT FROM SOKU GP AFTER COMPLETION OF OABP ACTIVITY FROM 11TH-13TH AFTER
Note on B9: Egejuru, Ebere SPDC-UPO/G/USLM: Saving is achieved as vessel was demobbed before Actual demobilization date of 15th Jan. 2023

## JAN '23 COST SAVINGS WEST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | Remark
1 | JOETEK VII | NNRA TUG | 4510482357 | WELLS | OGBOTOBO | 135587.07 | 1260.72 | 2023-01-01 | 2023-01-28 | 2023-04-02 | 7 | 949109.49 | 8825.04 | Savings achieved through early demobilization of NNRA barge than the planned date
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[11 empty] | Total | 949109.49 | 8825.04

## JAN '23 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
[10 empty] | 0 | 0 | 0
Note on B9: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZATION OF EXISTING FLEET RATHER THAN CALL UP TO SUPPORT NGC OPS

## FEB '23 COST SAVINGS WEST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | Remark
1 | GODFIRST 1 | HOUSEBOAT | 4510478188 | OAPB | SEIBOU | 120090.84 | 1116.88 | 2023-01-02 | 2023-02-13 | 28/2/2023 | 15 | 1801362.6 | 16753.2 | Saving is achieved as vessel was demobbed before planned demobilization date of 28th Feb 2023
2 | MV FAVOUR 2 | TUGBOAT | 4510478189 | OAPB | SEIBOU | 70327.98 | 654.08 | 2023-01-02 | 2023-02-13 | 28/2/2023 | 15 | 1054919.7 | 9811.2 | Saving is achieved as vessel was demobbed before planned demobilization date of 28th Feb 2024
3 | JOHNESCO A1 | LANDING CRAFT | 4510482595/4510482320/4510482595 | WELLS | OGBOTOBO | 129000 |  | 2023-01-02 | 2023-01-13 | 28/2/2023 | 15 | 1935000 | 0 | Saving is achieved as vessel was demobbed for optimization reason before planned demobilization date of 28th Feb 2025
4 | MV PERELADE | ESTUARY SUPPORT VESSEL | 4510483358 | WELLS | FORCADOS | 271442 | 2524.5 | 2023-02-01 | 2023-02-09 | 28/2/2023 | 19 | 5157398 | 47965.5 | Saving is achieved as vessel was demobbed for optimization reason before planned demobilization date of 28th Feb 2026
5 | JOETEK NURSE | ESTUARY SUPPORT VESSEL | 4510471027/4510480210 | WELLS | FORCADOS | 271442 | 2524.5 | 2023-01-01 | 2023-02-16 | 28/2/2023 | 12 | 3257304 | 30294 | Saving is achieved as vessel was demobbed for optimization reason before planned demobilization date of 28th Feb 2027
6 | TUG ACTIVE | RIG TUGBOAT | 4510475925 | WELLS | OGBOTOBO | 135587.07 | 1260.72 | 2023-01-01 | 2023-02-20 | 28/2/2023 | 8 | 1084696.56 | 10085.76 | Saving is achieved as vessel was offhired before planned demobilization date of 28th Feb 2028
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[11 empty] | Total | 14290680.86 | 114909.66

## FEB '23 COST AVOIDANCE WEST
COST AVOIDANCE
[5 empty] | DAILY RATE | [6 empty] | Remark
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | ACTUAL HIRED DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | ENL VICTORY | RAMP BARGE | ERT | ESCRAVOS | 32592.94 | 302.94 | 2023-02-13 | 2023-02-28 | 16 | 521487.04 | 4847.04 | Saving is achieved through vessel sharing opportunities between OES Respect Rig and ERT Ops at Escravos reducing fleet size by 1
2 | MV FAVOUR 5 | TUGBOAT | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2023-02-18 | 2023-02-23 | 6 | 421967.88 | 3924.48 | Saving is achieved through vessel sharing opportunities between OES Respect Rig and ERT Ops at Escravos reducing fleet size by 1
3 | EBIS II | RAMP BARGE | WEST ASSET | TUNU NODE | 32592.94 | 302.94 | 2023-02-18 | 2023-02-23 | 6 | 195557.64 | 1817.64 | Saving is achieved through vessel sharing opportunities between OES Respect Rig and ERT Ops at Escravos reducing fleet size by 1
4 | TRJ MOYOWA | TUGBOAT | PROJECT | FORCADOS | 70327.98 | 654.08 | 2023-02-24 | 2023-02-27 | 4 | 281311.92 | 2616.32 | Saving is achieved through vessel sharing opportunities between OES Respect Rig and ERT Ops at Escravos reducing fleet size by 1
5 | OLA 1 | RAMP BARGE | PROJECT | FORCADOS | 32592.94 | 302.94 | 2023-02-24 | 2023-02-27 | 4 | 130371.76 | 1211.76 | Saving is achieved through vessel sharing opportunities between OES Respect Rig and ERT Ops at Escravos reducing fleet size by 1
[9 empty] | 36 | 1550696.24 | 14417.24

## FEB '23 COST SAVINGS EAST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | Remark
3 | ST506 | LANDING CRAFT | 4510484421 | ASSET | NUN RIVER | 129625 |  | 2023-01-01 | 2023-02-18 | 28/2/2023 | 10 | 1296250 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date of 28th Feb 2023
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[11 empty] | Total | 1296250 | 0

## FEB'23 MISSED OPPORTUNITY
MISSED OPPORTUNITY/DELAYED MOBILIZATION COST TO BUSINESS
[6 empty] | DAILY RATE |  |  | MARINE WEST DELAYS TO OPS
S/N | NAME OF VESSEL | TYPE | VENDOR | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | TOLERABLE DELAYS DATE | EXPECTED SERVICE DAYS | ACTUAL DELAYS IN DAYS | N | $ | REMARK
1 | TBA | TUGBOAT | E.A TEMILE | ERT | ESCRAVOS | 70327.98 | 654.08 | 2023-02-03 | 2023-02-05 | 1900-01-29 | 2 | 70327.98 | 654.08 | Vendor unable to secure premob compliant kits.
2 | TBA | RAMP BARGE | E.A TEMILE | ERT | ESCRAVOS | 32592.94 | 302.94 | 2023-02-03 | 2023-02-05 | 1900-01-29 | 2 | 32592.94 | 302.94
3 | TBA | TUGBOAT | UNITOP | ERT | ESCRAVOS | 70327.98 | 654.08 | 2023-02-13 | 2023-02-15 | 1900-01-29 | 2 | 70327.98 | 654.08 | Vendor unable to secure premob compliant kits
4 | TBA | RAMP BARGE | UNITOP | ERT | ESCRAVOS | 32592.94 | 302.94 | 2023-02-13 | 2023-02-15 | 1900-01-29 | 2 | 32592.94 | 302.94
5 | TBA | TUGBOAT | OKPES CONSTRUCT | ERT | ESCRAVOS | 70327.98 | 654.08 | 2023-02-13 | 2023-02-15 | 1900-01-29 | 2 | 70327.98 | 654.08 | Vendor unable to secure premob compliant kits
6 | TBA | RAMP BARGE | OKPES CONSTRUCT | ERT | ESCRAVOS | 32592.94 | 302.94 | 2023-02-13 | 2023-02-15 | 1900-01-29 | 2 | 32592.94 | 302.94
7 | MV SEMEN | TUGBOAT | MAC-NAY | WEST ASSET | OTUMARA | 70327.98 | 654.08 | 2023-02-16 | 2023-02-27 | 2023-02-27 | 1 | 70327.98 | 654.08 | Escort unavailability due to election led to P.O extension.
8 | OGUNU ISLAND | RAMP BARGE | MAC-NAY | WEST ASSET | OTUMARA | 32592.94 | 302.94 | 2023-02-16 | 2023-02-27 | 2023-02-27 | 1 | 32592.94 | 302.94
[11 empty] | 14 | 411683.68 | 3828.08

## MAR '23 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | Remark
1 | MV BUDUKA | TUGBOAT | 4510478188 | ERT | ESCRAVOS | 70327.98 | 654.08 | 2023-01-03 | 2023-03-03 | 2023-09-03 | 6 | 421967.88 | 3924.48 | Saving is achieved as vessel was demobbed before planned demobilization date
2 | APUTU II | RAMP BARGE | 4510478189 | ERT | ESCRAVOS | 32592.94 | 302.94 | 2023-01-03 | 2023-03-03 | 2023-09-03 | 6 | 195557.64 | 1817.64 | Saving is achieved as vessel was demobbed before planned demobilization date
3 | PRINCESS AWANATE | RIG TUG BOAT | 4510484560 | WELLS | TUNU | 135587.07 | 1260.72 | 2023-01-03 | 2023-03-13 | 31/3/2023 | 18 | 2440567.26 | 22692.96 | Saving is achieved as vessel was demobbed before planned demobilization date
4 | ALTAR LINK | FUEL BARGE | 4510484001/4510483997 | FUEL ADMIN | OGUNU | 33066.36 | 307.53 | 2023-01-03 | 2023-03-17 | 31/3/2023 | 14 | 462929.04 | 4305.42 | Saving is achieved as vessel was demobbed before planned demobilization date
5 | MV SHANTEL | TUGBOAT | 4510484307/4510484956 | ERT | ESCRAVOS | 70327.98 | 654.08 | 2023-01-03 | 2023-03-17 | 31/3/2023 | 14 | 984591.72 | 9157.12 | Saving is achieved as vessel was demobbed before planned demobilization date
6 | MV EGO | TUGBOAT | 4510484303 | ERT | ESCRAVOS | 70327.98 | 654.08 | 2023-01-03 | 2023-03-17 | 31/3/2023 | 14 | 984591.72 | 9157.12 | Saving is achieved as vessel was demobbed before planned demobilization date
7 | SMU-TUNS 1 | RAMP BARGE | 4510484303 | ERT | ESCRAVOS | 32592.94 | 302.94 | 2023-01-03 | 2023-03-17 | 31/3/2023 | 14 | 456301.16 | 4241.16 | Saving is achieved as vessel was demobbed before planned demobilization date
8 | TRJ MOYOWA | TUGBOAT | 4510484302 | ERT | ESCRAVOS | 70327.98 | 654.08 | 2023-01-03 | 2023-03-17 | 31/3/2023 | 14 | 984591.72 | 9157.12 | Saving is achieved as vessel was demobbed before planned demobilization date
9 | OLA 1 | RAMP BARGE | 4510484302 | ERT | ESCRAVOS | 32592.94 | 302.94 | 2023-01-03 | 2023-03-17 | 31/3/2023 | 14 | 456301.16 | 4241.16 | Saving is achieved as vessel was demobbed before planned demobilization date
10 | AJAKURAMA ISL. | DUMB BARGE | 4510484578 | WELLS | TUNU | 32592.94 | 302.94 | 2023-01-03 | 2023-03-28 | 31/3/2023 | 3 | 97778.82 | 908.82 | Saving is achieved as vessel was demobbed before planned demobilization date
11 | R.B PERERE | DUMB BARGE | 4510476448 4510473132/4510484577 | WELLS | TUNU | 32592.94 | 302.94 | 2023-01-03 | 2023-03-28 | 31/3/2023 | 3 | 97778.82 | 908.82 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[10 empty] | Total | 120 | 7582956.94 | 70511.82

## MAR '23 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE. |  |  |  |  | Remark
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | ENL VICTORY | RAMP BARGE | ERT | ESCRAVOS | 32592.94 | 302.94 | 2023-03-01 | 2023-03-31 | 2023-03-17 | 14 | 456301.16 | 4241.16 | Saving is achieved through vessel sharing opportunities between OES Respect Rig and ERT Ops at Escravos reducing fleet size by 1 - Material movement
2 | MV FAVOUR 5 | TUGBOAT | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2023-03-18 | 2023-03-31 | 2023-03-29 | 13 | 914263.74 | 8503.04 | Saving is achieved through vessel sharing opportunities between OES Respect Rig and ERT Ops at Escravos reducing fleet size by 1 - Material movement
3 | EBIS III | RAMP BARGE | WEST ASSET | TUNU NODE | 32592.94 | 302.94 | 2023-03-18 | 2023-03-31 | 2023-03-29 | 13 | 423708.22 | 3938.22 | Saving is achieved through vessel sharing opportunities between OES Respect Rig and ERT Ops at Escravos reducing fleet size by 1 - Material movement
4 | MV EGO | TUGBOAT | PROJECT | ESCRAVOS | 70327.98 | 654.08 | 2023-03-13 | 2023-03-15 | 2023-03-15 | 3 | 210983.94 | 1962.24 | Saving is achieved through vessel sharing opportunities between ERT team and Project team reducing fleet size by 1 - - Material movement
5 | SMU-TUNS 1 | RAMP BARGE | PROJECT | ESCRAVOS | 32592.94 | 302.94 | 2023-03-13 | 2023-03-15 | 2023-03-15 | 3 | 97778.82 | 908.82 | Saving is achieved through vessel sharing opportunities between ERT team and Project team reducing fleet size by 1 - Material movement
6 | MV TIMI III | TUGBOAT | FUEL ADMIN | FORCADOS | 70327.98 | 654.08 | 2023-03-25 | 2023-03-28 | 2023-03-28 | 4 | 281311.92 | 2616.32 | Saving is achieved through vessel sharing opportunities between Fuel Admin and Project team reducing fleet size by 1 - tugboat for fuel barge demob
[10 empty] | 50 | 2384347.8 | 22169.8
Note on B7: Igben, Kingsley D SPDC-UPC/G/USLM: USED TO DEMOB LAND LOG KITS FROM ESCRAVOS
Note on B8: Igben, Kingsley D SPDC-UPC/G/USLM: USED TO DEMOB LAND LOG KITS FROM ESCRAVOS
Note on B9: Igben, Kingsley D SPDC-UPC/G/USLM: OPTIMIZE A RIG TUGBOAT TO DEMOB YINS OIL 1 FROM FOT

## MAR. MISSED OPPORTUNITY
MISSED OPPORTUNITY/DELAYED MOBILIZATION COST TO BUSINESS
[6 empty] | DAILY RATE |  |  | MARINE WEST DELAYS TO OPS
S/N | NAME OF VESSEL | TYPE | VENDOR | TEAM | LOCATION | N | $ | EXPECTED OFF-HIRED DATE | OFF-HIRE (DELAYS DATE) | ACTUAL DEMOB | ACTUAL DELAYS IN DAYS | N | $ | REMARK
1 | YINS OIL 1 | FUEL BARGE | REAL POINT | FUEL ADMIN | FORCADOS | 33066.36 | 307.53 | 2023-03-24 | 2023-03-29 | 2023-03-29 | 6 | 70327.98 | 654.08 | Vendors unable to secure premob compliant Tugboats for on-time vessels demob
2 | R.B TIMI III | FLAT TOP BARGE | EBUERE | WELLS | TUNU | 32592.94 | 302.94 | 2023-03-20 | 2023-03-23 | 2023-03-23 | 3 | 32592.94 | 302.94
[11 empty] | 9 | 102920.92 | 957.02
Note on K4: Igben, Kingsley D SPDC-UPC/G/USLM: Delays caused by seeking opportunistic room to demob kits
Note on K5: Igben, Kingsley D SPDC-UPC/G/USLM: Delays caused by vendor's inability to get a compliant barge

## APR '23 COST SAVINGS
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | Remark
1 | MV OMAS BRAKUMOH | RIG TUGBOAT | 4510484579 | WELLS | TUNU | 135587.07 | 1260.72 | 2023-01-04 | 2023-04-16 | 20/4/2023 | 4 | 542348.28 | 5042.88 | Saving is achieved as vessel was demobbed before planned demobilization date
2 | MV BUDUKA | TUGBOAT | 4510487330 | PIPELINE | NUN RIVER | 70327.98 | 654.08 | 22/4/2023 | 2023-04-29 | 2023-05-05 | 6 | 421967.88 | 3924.48 | Saving is achieved as vessel was demobbed before planned demobilization date
3 | DV FAVOUR | TUGBOAT | 4510483773/4510485421 | WEST ASSET | OTUMARA | 70327.98 | 654.08 | 14/4/2023 | 2023-04-23 | 24/4/2023 | 1 | 70327.98 | 654.08 | Saving is achieved as vessel was demobbed before planned demobilization date
4 | DML V | RAMP BARGE | 4510483773/4510485421 | WEST ASSET | OTUMARA | 32592.94 | 302.94 | 14/4/2023 | 2023-04-23 | 24/4/2023 | 1 | 32592.94 | 302.94 | Saving is achieved as vessel was demobbed before planned demobilization date
5 | MV EGO | TUGBOAT | 4510485277 | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2023-01-04 | 2023-04-20 | 30/4/2023 | 10 | 703279.8 | 6540.8 | Saving is achieved as vessel was demobbed before planned demobilization date
6 | OYENDI | ENV. BARGE | 4510485224 | WEST ASSET | TUNU NODE | 37015.29 | 344.25 | 2023-01-04 | 2023-04-20 | 30/4/2023 | 10 | 370152.9 | 3442.5 | Saving is achieved as vessel was demobbed before planned demobilization date
7 | MV TABATHA 1 | TUGBOAT | 4510484843 | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 29/3/2023 | 2023-04-21 | 2023-04-27 | 6 | 421967.88 | 3924.48 | Saving is achieved as vessel was demobbed before planned demobilization date
8 | ROMSON II | RAMP BARGE | 4510484843 | WEST ASSET | TUNU NODE | 32592.94 | 302.94 | 29/3/2023 | 2023-04-21 | 2023-04-27 | 6 | 195557.64 | 1817.64 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[10 empty] | Total | 44 | 2758195.3 | 25649.8

## APR '23 COST AVOIDANCE
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE. |  |  |  |  | Remark
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
2 | MV FAVOUR 5 | TUGBOAT | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2023-04-08 | 2023-04-22 | 2023-04-22 | 15 | 1054919.7 | 9811.2 | Saving is achieved through vessel sharing opportunities between WEST ASSET and ERT Ops Teams reducing fleet size by 1 - Material movement
3 | EBIS III | RAMP BARGE | WEST ASSET | TUNU NODE | 32592.94 | 302.94 | 2023-04-08 | 2023-04-22 | 2023-04-22 | 15 | 488894.1 | 4544.1 | Saving is achieved through vessel sharing opportunities between WEST ASSET and ERT Ops Teams reducing fleet size by 1 - Material movement
4 | BUDUKA | TUGBOAT | PIPELINE | ODIMODI | 70327.98 | 654.08 | 2023-04-27 | 2023-04-30 | 2023-04-30 | 4 | 281311.92 | 2616.32 | Saving is achieved by USING THE EXISTING FLEET(PAPATA-1) TO DEMOB TRP HB FROM ODIMODI
5 | WINIFRED | TUGBOAT | PIPELINE | ODIMODI | 70327.98 | 654.08 | 2023-04-27 | 2023-04-30 | 2023-04-30 | 4 | 281311.92 | 2616.32 | Saving is achieved by USING THE EXISTING FLEET(NEMMEN-1) TO DEMOB TRP HB FROM ODIMODI
[10 empty] | 38 | 2106437.64 | 19587.94
Note on B6: Igben, Kingsley D SPDC-UPC/G/USLM: USED EXISTING FLEET(PAPATA-1) TO DEMOB TRP HB FROM ODIMODI
Note on B7: Igben, Kingsley D SPDC-UPC/G/USLM: USED EXISTING FLEET (NEMMEN-1)TO DEMOB TRP HB FROM ODIMODI

## APR. MISSED OPPORTUNITY
MISSED OPPORTUNITY/DELAYED MOBILIZATION COST TO BUSINESS
[6 empty] | DAILY RATE |  |  | MARINE WEST DELAYS TO OPS
S/N | NAME OF VESSEL | TYPE | VENDOR | TEAM | LOCATION | N | $ | EXPECTED OFF-HIRED DATE | OFF-HIRE (DELAYS DATE) | ACTUAL DEMOB | ACTUAL DELAYS IN DAYS | N | $ | REMARK
1 | ALMIGHTY TOURIST | LANDING CRAFT | ZIKSON | EAST ASSET | SOKU | 129000 |  | 2023-04-22 | 2023-04-26 | 2023-04-26 | 4 | 516000 |  | ESCORT AVAILABILITY DELAYED VESSEL DISPATCH
[11 empty] | 4 | 516000 | 0
Note on K4: Igben, Kingsley D SPDC-UPC/G/USLM: Delays caused by seeking opportunistic room to demob kits

## MAY '23 COST SAVINGS EAST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE EAST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | REMARK
1 | MV-TETE-II | TUGBOAT | 4510471014/4510486004/4510487970 | PIPELINE | NUN-RIVER | 70327.98 | 654.08 | 2023-02-15 | 2023-05-22 | 2023-06-30 | 39 | 632951.82 | 25509.12 | Saving is achieved as vessel was demobbed before planned demobilization date
2 | EXCLUSIVE-II | 100 MAN HOUSEBOAT | 4510471055/4510486003 | PIPELINE | NUN-RIVER | 120090.84 | 1116.88 | 2023-02-15 | 2023-05-22 | 2023-06-30 | 39 | 1561180.92 | 43558.32 | Saving is achieved as vessel was demobbed before planned demobilization date
[11 empty] | Total | 2194132.74 | 69067.44

## MAY'-23'COST AVOIDANCE EAST
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE EAST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $ | REMARK
1 | MV-HECHS-1 | TUGBOAT | PIPELINE | NUN RIVER | 70327.98 | 654.08 | 2023-05-19 | 2023-05-26 | 2023-05-22 | 8 | 562623.84 | 5232.64 | Saving is achieved through vessel sharing opportunities using existing Tugboat to support Houseboat demobilization from NunRiver - Material movement
[11 empty] | 562623.84 | 5232.64
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USED EXISTING FLEET TO ASSIT IN THE DEMOB OF EXCLUSIVE-II HOUSEBOAT ON THE 22ND MAY.

## MAY '23 COST SAVINGS WEST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | REMARK
1 | MV ONOME 1 | TUGBOAT | 4510487683 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
2 | MV TRJ MOYOWA | TUGBOAT | 4510481830 | DFTP | NORTH BANK | 70327.98 | 654.08 | 24/5/2023 | 2023-05-30 | 2023-06-03 | 3 | 210983.94 | 1962.24 | Saving is achieved as vessel was demobbed before planned demobilization date
3 | ROMSON II | RAMP BARGE | 4510481830 | DFTP | NORTH BANK | 32592.94 | 302.94 | 24/5/2023 | 2023-05-30 | 2023-06-03 | 3 | 97778.82 | 908.82 | Saving is achieved as vessel was demobbed before planned demobilization date
4 | MV WINIFRED | TUGBOAT | 4510484370 | DFTP | BENISEDE | 70327.98 | 654.08 | 2023-01-05 | 2023-05-03 | 2023-07-05 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
5 | MV FLEET XIV | TUGBOAT | 4510487565 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-03-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
6 | MV KESSY III | TUGBOAT | 4510487559 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-03-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
7 | MV NENEMEN II | TUGBOAT | 4510487561 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-03-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
8 | MV OKORITE 1 | TUGBOAT | 4510487560 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-03-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
9 | MV FAITH | TUGBOAT | 4510487562 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-03-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
10 | MV OMIETE II | TUGBOAT | 4510484756 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
11 | NIMITEIN IV | TUGBOAT | 4510484756 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
12 | MV MEMEN I | TUGBOAT | 4510485021 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
13 | MV EHIJOZIE VI | TUGBOAT | 4510485021 | PIPELINE | NDORO | 70327.98 | 654.08 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was demobbed before planned demobilization date
14 | CLEM 08 | 100 MAN HB | 4510485846 | PIPELINE | NDORO | 120090.84 | 1116.88 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 480363.36 | 4467.52 | Saving is achieved as vessel was demobbed before planned demobilization date
15 | CLEM 09 | 100 MAN HB | 4510485846 | PIPELINE | NDORO | 120090.84 | 1116.88 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 480363.36 | 4467.52 | Saving is achieved as vessel was demobbed before planned demobilization date
16 | TAMUOMEMI HILTON 1 | 100 MAN HB | 4510485845 | PIPELINE | NDORO | 120090.84 | 1116.88 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 480363.36 | 4467.52 | Saving is achieved as vessel was demobbed before planned demobilization date
17 | TAMUOMEMI HILTON 2 | 100 MAN HB | 4510485845 | PIPELINE | NDORO | 120090.84 | 1116.88 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 480363.36 | 4467.52 | Saving is achieved as vessel was demobbed before planned demobilization date
18 | OLOHIGHBE 1 | 100 MAN HB | 4510485845 | PIPELINE | NDORO | 120090.84 | 1116.88 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 480363.36 | 4467.52 | Saving is achieved as vessel was demobbed before planned demobilization date
19 | ROSS 3 | 100 MAN HB | 4510485123 | PIPELINE | NDORO | 120090.84 | 1116.88 | 2023-01-05 | 2023-05-16 | 20/5/2023 | 4 | 480363.36 | 4467.52 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[10 empty] | Total | 74 | 6285374.04 | 58455.7

## MAY '23 COST AVOIDANCE WEST
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $ | REMARK
1 | QUEEN LORI | TUGBOAT | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2023-05-20 | 2023-05-25 | 2023-05-25 | 6 | 421967.88 | 3924.48 | Saving is achieved through vessel sharing opportunities between ASSET and WELLS teams
2 | SAKINAH II | FLAT TOP BARGE | WEST ASSET | TUNU NODE | 32592.94 | 302.94 | 2023-05-20 | 2023-05-25 | 2023-05-25 | 6 | 195557.64 | 1817.64 | Saving is achieved through vessel sharing opportunities between ASSET and WELLS teams
[10 empty] | 12 | 617525.52 | 5742.12

## MAY. MISSED OPPORTUNITY
MISSED OPPORTUNITY/DELAYED MOBILIZATION COST TO BUSINESS
[6 empty] | DAILY RATE |  |  | MARINE WEST DELAYS TO OPS
S/N | NAME OF VESSEL | TYPE | VENDOR | TEAM | LOCATION | N | $ | EXPECTED OFF-HIRED DATE | OFF-HIRE (DELAYS DATE) | ACTUAL DEMOB | ACTUAL DELAYS IN DAYS | N | $ | REMARK
1 | PRINCESS OWANATE | RIG TUGBOAT | EBIDESE | WEST | OGBOTOBO | 135587.07 | 1260.72 | 2023-05-29 | 2023-05-31 | 2023-05-31 | 4 | 542348.28 | 5042.88 | ESCORT UNAVAILABILITY DELAYED DISPATCH
2 | LOHO 1 | TUGBOAT | JOE-ASIDOS | WEST | TUNU | 70327.98 | 654.08 | 2023-05-26 | 2023-05-31 | 2023-05-31 | 4 | 281311.92 | 2616.32 | FUEL UNAVAILABILITY DELAYED DISPATCH
[11 empty] | 8 | 823660.2 | 7659.2
Note on I3: Igben, Kingsley D SPDC-UPC/G/USLM: Expected sail out date
Note on K4: Igben, Kingsley D SPDC-UPC/G/USLM: Delays caused by absence of escort
Note on I5: Igben, Kingsley D SPDC-UPC/G/USLM: Expected sail out date
Note on K5: Igben, Kingsley D SPDC-UPC/G/USLM: Delays caused by absence of escort

## JUNE'23 COST SAVINGS EAST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE EAST POTENTIAL SAVINGS.
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | REMARK
1 | MV-EDOSE | TUGBOAT | 4510488276 | WELLS | SOKU FIELD | 70327.98 | 654.08 | 2023-04-19 | 2023-06-19 | 2023-06-30 | 11 | 632951.82 | 7194.88 | Saving is achieved as vessel was demobbed before planned demobilization date
2 | MV-GLORY-II | TUGBOAT | 4510489729 | WELLS | SOKU FIELD | 70327.98 | 654.08 | 2023-04-19 | 2023-06-19 | 2023-06-30 | 11 | 773607.78 | 7194.88 | Saving is achieved as vessel was demobbed before planned demobilization date
3 | MV-DABEL ANGEL VI | TUGBOAT | 4510489730 | WELLS | SOKU FIELD | 70327.98 | 654.08 | 2023-04-19 | 2023-06-19 | 2023-06-30 | 11 | 773607.78 | 7194.88 | Saving is achieved as vessel was demobbed before planned demobilization date
4 | MV-DANIELLA-1 2019 | TUGBOAT | 4510488278 | WELLS | SOKU FIELD | 70327.98 | 654.08 | 2023-04-19 | 2023-06-19 | 2023-06-30 | 11 | 773607.78 | 7194.88 | Saving is achieved as vessel was demobbed before planned demobilization date
6 | GLORIOUS-VIII | 60 MAN HOUSEBOAT | 4510488277 | WELLS | SOKU FIELD | 109564.07 | 1018.98 | 2023-04-19 | 2023-06-19 | 2023-06-30 | 11 | 1205204.77 | 11208.78 | Saving is achieved as vessel was demobbed before planned demobilization date
7 | SOMEJE-III | WATER BARGE | 4510485280 | WELLS | SOKU FIELD | 35534.25 | 330.48 | 2023-04-19 | 2023-06-12 | 2023-06-30 | 18 | 639616.5 | 5948.64 | Saving is achieved as vessel was demobbed before planned demobilization date
8 | BOMO-V | RAMP BARGE | 4510488280 | WELLS | SOKU FIELD | 32572.94 | 302.94 | 2023-04-19 | 2023-06-17 | 2023-06-30 | 13 | 423448.22 | 3938.22 | Saving is achieved as vessel was demobbed before planned demobilization date
9 | TOOCHI-2 | RAMP BARGE | 4510484595 | WELLS | SOKU FIELD | 32572.94 | 302.94 | 2023-04-19 | 2023-06-16 | 2023-06-30 | 14 | 456021.16 | 4241.16 | Saving is achieved as vessel was demobbed before planned demobilization date
10 | MIRACLE-II | RAMP BARGE | 4510488279 | WELLS | SOKU FIELD | 32572.94 | 302.94 | 2023-04-19 | 2023-06-15 | 2023-06-30 | 15 | 488594.1 | 4544.1 | Saving is achieved as vessel was demobbed before planned demobilization date
11 | MARIEN-1 | RAMP BARGE | 4510488280 | WELLS | SOKU FIELD | 32572.94 | 302.94 | 2023-04-19 | 2023-06-14 | 2023-06-30 | 16 | 521167.04 | 4847.04 | Saving is achieved as vessel was demobbed before planned demobilization date
12 | BOMO-III | RAMP BARGE | 4510488280 | WELLS | SOKU FIELD | 32572.94 | 302.94 | 2023-04-19 | 2023-06-20 | 2023-06-30 | 10 | 325729.4 | 3029.4 | Saving is achieved as vessel was demobbed before planned demobilization date
[11 empty] | Total | 7013556.35 | 66536.86

## JUNE '23 COST SAVINGS WEST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST SAVINGS. |  |  |  |  | REMARK
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD | Column1
1 | PRINCESS OWANATE | RIG TUGBOAT | 4510489737 | WELLS | OGBOTOBO | 120090.84 | 1116.88 | 2023-01-06 | 2023-06-06 | 2023-12-06 | 6 | 720545.04 | 6701.28 | Saving is achieved as vessel was demobbed before planned demobilization date
2 | VERTEX | FLAT TOP BARGE | 4510489737 | WELLS | OGBOTOBO | 32592.94 | 302.94 | 2023-01-06 | 2023-06-06 | 2023-12-06 | 6 | 195557.64 | 1817.64 | Saving is achieved as vessel was demobbed before planned demobilization date
3 | MV TIMI II | TUGBOAT | 4510489746 | WELLS | BENISEDE | 70327.98 | 654.08 | 2023-09-06 | 2023-06-14 | 2023-06-20 | 6 | 421967.88 | 3924.48 | Saving is achieved as vessel was demobbed before planned demobilization date
4 | MV KRISTINE II | TUGBOAT | 4510484370 | WELLS | BENISEDE | 70327.98 | 654.08 | 2023-09-06 | 2023-06-14 | 2023-06-20 | 6 | 421967.88 | 3924.48 | Saving is achieved as vessel was demobbed before planned demobilization date
5 | ENIYE 1 | WATER BARGE | 4510489746 | WELLS | BENISEDE | 35534.25 | 330.48 | 2023-01-06 | 2023-06-14 | 2023-06-20 | 6 | 213205.5 | 1982.88 | Saving is achieved as vessel was demobbed before planned demobilization date
6 | MV EBIMO | TUGBOAT | 4510488138 | OABP | BENISEDE | 70327.98 | 654.08 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 8 | 562623.84 | 5232.64 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[12 empty] | 0 | 0 | Saving is achieved as vessel was demobbed before planned demobilization date
[10 empty] | Total | 38 | 2535867.78 | 23583.4

## JUNE '23 COST AVOIDANCE WEST
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $ | REMARK
1 | MV FAVOUR 5 | TUGBOAT | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2023-06-16 | 2023-06-19 | 2023-06-19 | 4 | 281311.92 | 2616.32 | Saving is achieved through vessel sharing opportunities between ASSET and OABP teams
2 | EBIS III | FLAT TOP BARGE | WEST ASSET | TUNU NODE | 32592.94 | 302.94 | 2023-06-16 | 2023-06-19 | 2023-06-19 | 4 | 130371.76 | 1211.76 | Saving is achieved through vessel sharing opportunities between ASSET and OABP teams
Saving is achieved through vessel sharing opportunities between ASSET and OABP teams
[10 empty] | 8 | 411683.68 | 3828.08

## JUNE. MISSED OPPORTUNITY WEST
MISSED OPPORTUNITY/DELAYED MOBILIZATION COST TO BUSINESS
[6 empty] | DAILY RATE |  |  | MARINE WEST DELAYS TO OPS
S/N | NAME OF VESSEL | TYPE | VENDOR | TEAM | LOCATION | N | $ | EXPECTED OFF-HIRED DATE | OFF-HIRE (DELAYS DATE) | ACTUAL DEMOB | ACTUAL DELAYS IN DAYS | N | $ | REMARK
1 | MV WINIFRED | TUGBOAT | ESINMON | WEST | OGBOTOBO | 70327.98 | 654.08 | 2023-06-18 | 2023-06-19 | 2023-06-19 | 1 | 70327.98 | 654.08 | ESCORT UNAVAILABILITY DELAYED DISPATCH
2 | DML XIV | RAMP BARGE | ESINMON | WEST | ESCRAVOS | 32592.94 | 302.94 | 2023-06-18 | 2023-06-19 | 2023-06-19 | 1 | 32592.94 | 302.94 | FUEL UNAVAILABILITY DELAYED DISPATCH
[11 empty] | 2 | 102920.92 | 957.02
Note on I3: Igben, Kingsley D SPDC-UPC/G/USLM: Expected sail out date

## JULY '23 COST SAVINGS WEST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS. |  |  |  |  | REMARK
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | MV SEMEN 1 | TUGBOAT | 4510490457 | WELLS | BENISEDE | 70327.98 | 654.08 | 2023-04-07 | 2023-07-14 | 28/7/2023 | 14 | 984591.72 | 9157.12 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
2 | MV EGO | TUGBOAT | 4510490457 | WELLS | BENISEDE | 70327.98 | 654.08 | 2023-12-07 | 2023-07-22 | 30/7/2023 | 8 | 562623.84 | 5232.64 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
3 | MV MIEBII/SEMEN 1 | TUGBOAT | 4510490812 | WEST ASSET | OTUMARA | 70327.98 | 654.08 | 13/7/2023 | 2023-07-25 | 2023-07-31 | 6 | 421967.88 | 3924.48 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
4 | YINS OIL 1 | ENV. BARGE | 4510490812 | WEST ASSET | OTUMARA | 37015.29 | 344.25 | 13/7/2023 | 2023-07-25 | 2023-07-31 | 6 | 222091.74 | 2065.5 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
5 | KESSY 1 | TUGBOAT | 4510490455 | WELLS | BENISEDE | 70327.98 | 654.08 | 2023-12-07 | 2023-07-22 | 30/7/2023 | 8 | 562623.84 | 5232.64 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
6 | MV PAPA GEORGE | TUGBOAT | 4510489711 | WELLS | TUNU | 70327.98 | 654.08 | 2023-12-07 | 2023-07-29 | 2023-05-08 | 7 | 492295.86 | 4578.56 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[10 empty] | Total | 49 | 3246194.88 | 30190.94

## JULY '23 COST AVOIDANCE WEST
COST AVOIDANCE | [12 empty] | REMARK
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE.
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
[10 empty] | 0 | 0 | 0

## JULY. MISSED OPPORTUNITY WEST
MISSED OPPORTUNITY/DELAYED MOBILIZATION COST TO BUSINESS
[6 empty] | DAILY RATE |  |  | MARINE WEST DELAYS TO OPS
S/N | NAME OF VESSEL | TYPE | VENDOR | TEAM | LOCATION | N | $ | EXPECTED OFF-HIRED DATE | OFF-HIRE (DELAYS DATE) | ACTUAL DEMOB | ACTUAL DELAYS IN DAYS | N | $ | REMARK
[11 empty] | 0 | 0 | 0
Note on I3: Igben, Kingsley D SPDC-UPC/G/USLM: Expected sail out date

## AUG '23 COST SAVINGS WEST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS. |  |  |  |  | REMARK
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | ST 278 | LANDING CRAFT | 4510490346/4510492492/50 | WELLS | TUNU WELL LIFT | 129000 |  | 2023-07-07 | 26/8/2023 | 31/8/2023 | 5 | 645000 | 0 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
2 | LAMCO PRAISE | LANDING CRAFT | 4510487938/4510488631 | WELLS | TUNU BR 301 | 57249 |  | 2023-01-01 | 2023-07-08 | 31/8/2023 | 24 | 1373976 | 0 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
3 | PRINCESS TARA | TUGBOAT | 4510490813 | WEST ASSET | NORTH BANK | 70327.98 | 654.08 | 2023-01-08 | 2023-09-08 | 2023-08-19 | 10 | 703279.8 | 6540.8 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
4 | AMARIS 10 | RAMP BARGE | 4510490813 | WEST ASSET | NORTH BANK | 32592.94 | 302.94 | 2023-01-08 | 2023-09-08 | 2023-08-19 | 10 | 325929.4 | 3029.4 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
5 | UIL XI | TUGBOAT | 4510489707/4510489708 | WELLS | TUNU WELL LIFT | 70327.98 | 654.08 | 2023-01-08 | 2023-08-13 | 31/8/2023 | 18 | 1265903.64 | 11773.44 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
6 | MV SIMMENTAL | RIG TUGBOAT | 4510488630/4510490476 | WELLS | TUNU BR 301 | 135587.07 | 1260.72 | 2019-01-10 | 2023-08-26 | 31/8/2023 | 5 | 677935.35 | 6303.6 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
7 | MV QUEEN LORI | RIG TUGBOAT | 4510488630/4510490476 | WELLS | TUNU BR 301 | 135587.07 | 1260.72 | 2019-01-10 | 2023-08-26 | 31/8/2023 | 5 | 677935.35 | 6303.6 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
8 | HANNAH 3 | FLAT TOP BARGE | 4510487939/4510488632 | WELLS | TUNU BR 301 | 32592.94 | 302.94 | 2023-01-08 | 2023-08-25 | 31/8/2023 | 6 | 195557.64 | 1817.64 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
9 | JENNELLE | RAMP BARGE | 4510491499 | WELLS | TUNU WELL LIFT | 32592.94 | 302.94 | 2023-01-08 | 2023-08-16 | 31/8/2023 | 15 | 488894.1 | 4544.1 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
10 | MV EBUERE IV | TUGBOAT | 4510488796 | WELLS | OES RESPECT | 70327.98 | 654.08 | 2023-01-08 | 2023-08-06 | 21/8/2023 | 15 | 1054919.7 | 9811.2 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
11 | MV KRISTINE II | TUGBOAT | 4510490837/4510492704 | WELLS | TUNU WELL LIFT | 70327.98 | 654.08 | 2023-01-08 | 2023-08-26 | 31/8/2023 | 5 | 351639.9 | 3270.4 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
12 | MV EBUERE IV | TUGBOAT | 4510490837/4510492704 | WELLS | TUNU WELL LIFT | 70327.98 | 654.08 | 2023-09-08 | 2023-08-20 | 23/8/2023 | 3 | 210983.94 | 1962.24 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
13 | MV SHALLOM II | TUGBOAT | 4510490837/4510492704 | WELLS | TUNU WELL LIFT | 70327.98 | 654.08 | 2023-10-08 | 2023-08-20 | 24/8/2023 | 4 | 281311.92 | 2616.32 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
14 | ELOHO VI | RAMP BARGE | 4510490837/4510492704 | WELLS | TUNU WELL LIFT | 32592.94 | 302.94 | 2023-01-08 | 2023-08-16 | 31/8/2023 | 15 | 488894.1 | 4544.1 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
15 | JUBICHRIS | RAMP BARGE | 4510490837/4510492704 | WELLS | TUNU WELL LIFT | 32592.94 | 302.94 | 2023-01-08 | 2023-08-24 | 31/8/2023 | 7 | 228150.58 | 2120.58 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
16 | ND 619 | WATER BARGE | 4510490837/4510492704 | WELLS | TUNU WELL LIFT | 35534.25 | 330.48 | 2023-01-08 | 2023-08-14 | 31/8/2023 | 17 | 604082.25 | 5618.16 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
17 | BABY JEM 1 | FLAT TOP BARGE | 4510488633/4510490480 | WELLS | TUNU BR 301 | 32592.94 | 302.94 | 2023-01-08 | 2023-08-10 | 31/8/2023 | 21 | 684451.74 | 6361.74 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
18 | FOZ EWOMAOGHENE` | FLAT TOP BARGE | 4510488633/4510490480 | WELLS | TUNU BR 301 | 32592.94 | 302.94 | 2023-01-08 | 2023-08-25 | 31/8/2023 | 6 | 195557.64 | 1817.64 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
19 | MV DAVINA | TUGBOAT | 4510488633/4510490480 | WELLS | TUNU BR 301 | 70327.98 | 654.08 | 2023-01-08 | 2023-08-30 | 31/8/2023 | 1 | 70327.98 | 654.08 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
20 | MSL IV | CORAL BARGE | 4510488633/4510490480 | WELLS | TUNU BR 301 | 37015.29 | 344.25 | 2023-01-08 | 2023-08-25 | 31/8/2023 | 6 | 222091.74 | 2065.5 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
21 | MARIEN VI | WATER BARGE | 4510488633/4510490480 | WELLS | TUNU BR 301 | 35534.25 | 330.48 | 2023-01-08 | 2023-08-26 | 31/8/2023 | 5 | 177671.25 | 1652.4 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
22 | FOZ EWOMAOGHENE` | FLAT TOP BARGE | 4510488633/4510490480 | WELLS | TUNU BR 301 | 32592.94 | 302.94 | 2023-01-08 | 2023-08-28 | 31/8/2023 | 3 | 97778.82 | 908.82 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
23 | GOLDSHOLD IV | CORAL BARGE | 4510488696 | WELLS | TUNU BR 301 | 37015.29 | 344.25 | 2023-01-08 | 2023-08-08 | 22/8/2023 | 14 | 518214.06 | 4819.5 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
24 | BOMO IV | FLAT TOP BARGE | 4510489721/4510491502 | WELLS | TUNU WELL LIFT | 32592.94 | 302.94 | 2023-01-08 | 2023-08-22 | 31/8/2023 | 9 | 293336.46 | 2726.46 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
25 | YINS OIL 4 | ENV. BARGE | 4510489706/4510492703 | WELLS | TUNU WELL LIFT | 37015.29 | 344.25 | 2023-01-08 | 2023-08-20 | 31/8/2023 | 11 | 407168.19 | 3786.75 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
26 | PRINCESS BISGAR | NNRA TUG | 4510482353/4510491590 | WELLS | TUNU BR 301 | 135587.07 | 1260.72 | 2023-01-08 | 2023-08-08 | 31/8/2023 | 23 | 3118502.61 | 28996.56 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
27 | ENL VICTORY | NNR BARGE | 4510482353/4510491590 | WELLS | TUNU BR 301 | 34547.4 | 321.3 | 2023-01-08 | 2023-08-08 | 31/8/2023 | 23 | 794590.2 | 7389.9 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[10 empty] | Total | 113 | 16154084.36 | 131434.93

## AUG '23 COST AVOIDANCE WEST
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE. |  |  |  |  | REMARK
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | MV FAVOUR 5 | TUGBOAT | WEST ASSET | TUNU NODE | 70327.98 | 654.08 | 2023-07-28 | 2023-08-04 | 2023-08-04 | 8 | 562623.84 | 5232.64 | Saving is achieved through vessel sharing opportunities between ASSET and OABP teams for material delivery to Tunu field site
2 | EBIS III | FLAT TOP BARGE | WEST ASSET | TUNU NODE | 32592.94 | 302.94 | 2023-07-28 | 2023-08-04 | 2023-08-04 | 8 | 260743.52 | 2423.52 | Saving is achieved through vessel sharing opportunities between ASSET and OABP teams for material delivery to Tunu field site
3 | MV FAVOUR 3 | TUGBOAT | WEST ASSET | FORCADOS | 70327.98 | 654.08 | 2023-08-12 | 2023-08-14 | 2023-08-14 | 3 | 210983.94 | 1962.24 | Saving is achieved through vessel sharing opportunities between ASSET and Project teams for material delivery to FOT
4 | JOETEK VIII | RAMP BARGE | WEST ASSET | FORCADOS | 32592.94 | 302.94 | 2023-08-12 | 2023-08-14 | 2023-08-14 | 3 | 97778.82 | 908.82 | Saving is achieved through vessel sharing opportunities between ASSET and Project teams for material delivery to FOT
5 | HEPZEBAH 6 | RAMP BARGE | WELLS | BENISEDE | 32592.94 | 302.94 | 2023-08-02 | 2023-08-11 | 2023-08-11 | 10 | 325929.4 | 3029.4 | Saving is achieved through vessel sharing opportunities between CWI and OES Respect Rig teams for material delivery to BENESEDE field
6 | MV SHALLOM II | TUGBOAT | PROJECT | OGBOTOBO | 70327.98 | 654.08 | 2023-08-28 | 2023-09-01 | 2023-09-01 | 5 | 351639.9 | 3270.4 | Saving is achieved through vessel sharing opportunities between CWI and Major Project teams for material delivery to OGBOTOBO field
7 | JOETEK XI | RAMP BARGE | PROJECT | OGBOTOBO | 32592.94 | 302.94 | 2023-08-28 | 2023-09-01 | 2023-09-01 | 5 | 162964.7 | 1514.7 | Saving is achieved through vessel sharing opportunities between CWI and Major Project teams for material delivery to OGBOTOBO field
[10 empty] | 42 | 1972664.12 | 18341.72

## AUG. MISSED OPPORTUNITY WEST
MISSED OPPORTUNITY/DELAYED MOBILIZATION COST TO BUSINESS
[6 empty] | DAILY RATE |  |  | MARINE WEST DELAYS TO OPS
S/N | NAME OF VESSEL | TYPE | VENDOR | TEAM | LOCATION | N | $ | EXPECTED OFF-HIRED DATE | OFF-HIRE (DELAYS DATE) | ACTUAL DEMOB | ACTUAL DELAYS IN DAYS | N | $ | REMARK
1 | MV FLEET XIV | TUGBOAT | EDEMYX | WELLS | ESCRAVOS | 70327.98 | 654.08 | 2023-08-02 | 2023-08-04 | 2023-08-04 | 2 | 140655.96 | 1308.16 | ESCORT UNAVAILABILITY DELAYED DISPATCH
2 | IBADHE II | RAMP BARGE | EDEMYX | WELLS | ESCRAVOS | 32592.94 | 302.94 | 2023-08-02 | 2023-08-04 | 2023-08-04 | 2 | 65185.88 | 605.88 | ESCORT UNAVAILABILITY DELAYED DISPATCH
3 | ENOHO V | LANDING CRAFT | MARSHAL | WEST ASSET | OGBOTOBO | 129066 |  | 2023-08-11 | 2023-08-12 | 2023-08-12 | 1 | 129066 | 0
4 | MV DEBORAH 1 | TUGBOAT | VERTICAL OPTION | WELLS | TUNU | 70327.98 | 654.08 | 2023-08-22 | 2023-08-25 | 2023-08-25 | 3 | 210983.94 | 1962.24 | Delay caused by Zero fuel holding stock by fuel team. Escort and Lucnh pack for boat crew.
5 | MV MERCIFUL GOD | TUGBOAT | EDEMYX | WELLS | TUNU | 70327.98 | 654.08 | 2023-08-23 | 2023-08-25 | 2023-08-25 | 3 | 210983.94 | 1962.24
[11 empty] | 11 | 756875.72 | 5838.52
Note on I3: Igben, Kingsley D SPDC-UPC/G/USLM: Expected sail out date

## SEPT. '23 COST SAVINGS WEST
COST SAVING
[6 empty] | DAILY RATE |  |  | MARINE WEST POTENTIAL SAVINGS. |  |  |  |  | REMARK
S/N | NAME OF VESSEL | TYPE | PO | TEAM | LOCATION | N | $ | HIRE DATE | ACTUAL OFF-HIRE | EXPECTED OFF-HIRE | ACTUAL SAVINGS IN DAYS | NGN | USD
1 | MARIEN VII | TUGBOAT | 4510488139 | OABP | BENISEDE | 70327.98 | 654.08 | 2023-01-09 | 2023-09-22 | 30/9/2023 | 8 | 562623.84 | 5232.64 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
2 | TOOCHI 7 | HOUSEBOAT | 4510490651 | OABP | BENISEDE | 120090.84 | 1116.88 | 2023-01-09 | 2023-09-22 | 30/9/2023 | 8 | 960726.72 | 8935.04 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
3 | PAPA INDIAN | TUGBOAT | 4510490434 | OABP | BENISEDE | 70327.98 | 654.08 | 2023-01-09 | 2023-09-22 | 30/9/2023 | 8 | 562623.84 | 5232.64 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
4 | MV JOPO ISL/SEMEN 1 | TUGBOAT | 4510492463 | WELLS | NORTH BANK | 70327.98 | 654.08 | 2023-01-09 | 2023-09-12 | 24/9/2023 | 12 | 843935.76 | 7848.96 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
5 | DVB 1 | RAMP BARGE | 4510492463 | WELLS | NORTH BANK | 32592.94 | 302.94 | 2023-01-09 | 2023-09-12 | 24/9/2023 | 12 | 391115.28 | 3635.28 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
6 | MV SHALLOM II | TUGBOAT | 4510492459 | WELLS | NORTH BANK | 70327.98 | 654.08 | 2023-01-09 | 2023-09-16 | 30/9/2023 | 14 | 984591.72 | 9157.12 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
7 | JOETEK XI | RAMP BARGE | 4510492459 | WELLS | NORTH BANK | 32592.94 | 302.94 | 2023-01-09 | 2023-09-16 | 30/9/2023 | 14 | 456301.16 | 4241.16 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
8 | OMS 105 | FLAT TOP BARGE | 4510490480 | WELLS | BR 301 | 32592.94 | 302.94 | 2023-01-09 | 2023-09-09 | 25/9/2023 | 16 | 521487.04 | 4847.04 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
9 | SAKINAH II | FLAT TOP BARGE | 4510490480 | WELLS | BR 301 | 32592.94 | 302.94 | 2023-01-09 | 2023-09-11 | 25/9/2023 | 14 | 456301.16 | 4241.16 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
10 | MSL V | FLAT TOP BARGE | 4510490480 | WELLS | BR 301 | 32592.94 | 302.94 | 2023-01-09 | 2023-09-14 | 25/9/2023 | 10 | 325929.4 | 3029.4 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
11 | OMA BRAKUMOH | RIG TUGBOAT | 4510488633/4510490480 | WELLS | BR 301 | 135587.07 | 1260.72 | 2023-01-09 | 2023-09-09 | 25/9/2023 | 16 | 2169393.12 | 20171.52 | Saving is achieved as vessel was promptly demobbed before planned demobilization date reducing waiting time on site
[12 empty] | 0 | 0
[12 empty] | 0 | 0
[10 empty] | Total | 62 | 8235029.04 | 76571.96

## SEPT '23 COST AVOIDANCE WEST
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE. |  |  |  |  | REMARK
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | MV LEADGATE | TUGBOAT | WEST ASSET | BRASS CREEK | 70327.98 | 654.08 | 2023-09-15 | 2023-09-17 | 2023-09-17 | 3 | 210983.94 | 1962.24 | Saving is achieved through vessel sharing opportunities between PIPELINE and WELLS teams for material delivery to Tunu field site
2 | DIKI ISLAND | RAMP BARGE | WEST ASSET | BRASS CREEK | 32592.94 | 302.94 | 2023-09-15 | 2023-09-17 | 2023-09-17 | 3 | 97778.82 | 908.82 | Saving is achieved through vessel sharing opportunities between PIPELINE and WELLS teams for material delivery to Tunu field site
3 | MV FAVOUR 2 | TUGBOAT | WEST ASSET | NORTH BANK | 70327.98 | 654.08 | 2023-09-15 | 2023-09-17 | 2023-09-17 | 3 | 210983.94 | 1962.24 | Saving is achieved through vessel sharing opportunities between ASSET and WELLS teams for material delivery to Escravos field site
4 | JOETEK VIII | RAMP BARGE | WEST ASSET | NORTH BANK | 32592.94 | 302.94 | 2023-09-15 | 2023-09-17 | 2023-09-17 | 3 | 97778.82 | 908.82 | Saving is achieved through vessel sharing opportunities between ASSET and WELLS teams for material delivery to Escravos field site
[10 empty] | 12 | 617525.52 | 5742.12

## SEPT. MISSED OPPORTUNITY WEST
MISSED OPPORTUNITY/DELAYED MOBILIZATION COST TO BUSINESS
[6 empty] | DAILY RATE |  |  | MARINE WEST DELAYS TO OPS
S/N | NAME OF VESSEL | TYPE | VENDOR | TEAM | LOCATION | N | $ | EXPECTED OFF-HIRED DATE | OFF-HIRE (DELAYS DATE) | ACTUAL DEMOB | ACTUAL DELAYS IN DAYS | N | $ | REMARK
[11 empty] | 0 | 0 | 0
Note on I3: Igben, Kingsley D SPDC-UPC/G/USLM: Expected sail out date

## SEPT '23 COST AVOIDANCE EAST
COST AVOIDANCE
[5 empty] | DAILY RATE |  |  | MARINE WEST COST AVOIDANCE. |  |  |  |  | REMARK
S/N | NAME OF VESSEL | TYPE | TEAM | LOCATION | N | $ | EXPECTED HIRED DATE | EXPECTED OFF-HIRE DATE | ACTUAL OFF-HIRE DATE | ACTUAL SAVINGS IN DAYS | N | $
1 | MV DEE PITA | LANDING CRAFT | WEST ASSET | SOKU | 129625 | 0 | 2023-09-21 | 2023-10-06 | 2023-10-06 | 16 | 2074000 | 0 | Saving is achieved through vessel sharing opportunity between EXPLORATION and ASSET teams for EIA Survey activity at SOKU
[10 empty] | 16 | 2074000 | 0

## SUMMARY
PROJECT NEPTUNE - MONTHLY COST SAVINGS AND MISSED OPPORTUNTIES FOR INSHORE MARINE OPS
S/N | MONTH | COST SAVING |  |  |  | COST AVOIDANCE |  |  |  | MISSED OPPORTUNITIES |  | TOTAL
|  | EAST |  | WEST |  | EAST |  | WEST
|  | N | $ | N | $ | N | $ | N | $ | N | $ | N | $
1 | 2023-01-01 | 3862118.64 | 35919.24 | 949109.49 | 8825.04 | 0 | 0 | 0 | 0 | 0 | 0 | 4811228.13 | 44744.28
2 | 2023-02-01 | 1296250 | 0 | 14290680.86 | 114909.66 | 0 | 0 | 1550696.24 | 14417.24 | 411683.68 | 3828.08 | 16725943.42 | 125498.82
3 | 2023-03-01 | 0 | 0 | 7582956.94 | 70511.82 | 0 | 0 | 2384347.8 | 22169.8 | 102920.92 | 957.02 | 9864383.82 | 91724.6
4 | 2023-04-01 | 0 | 0 | 2758195.3 | 25649.8 | 0 | 0 | 2106437.64 | 19587.94 | 516000 | 0 | 4348632.94 | 45237.74
5 | 2023-05-01 | 2194132.74 | 69067.44 | 6285374.04 | 58455.7 | 562623.84 | 5232.64 | 617525.52 | 5742.12 | 823660.2 | 7659.2 | 8835995.94 | 130838.7
6 | 2023-06-01 | 7013556.35 | 66536.86 | 2535867.78 | 23583.4 | 0 | 0 | 411683.68 | 3828.08 | 102920.92 | 957.02 | 9858186.89 | 92991.32
7 | 2023-07-01 | 0 | 0 | 3246194.88 | 30190.94 | 0 | 0 | 0 | 0 | 0 | 0 | 3246194.88 | 30190.94
8 | 2023-08-01 | 0 | 0 | 16154084.36 | 131434.93 | 0 | 0 | 1972664.12 | 18341.72 | 756875.72 | 5838.52 | 17369872.76 | 143938.13
9 | 2023-09-01 | 0 | 0 | 8235029.04 | 76571.96 | 2074000 | 0 | 617525.52 | 5742.12 | 0 | 0 | 10926554.56 | 82314.08
10 | 2023-10-01 | [10 empty] | 0 | 0
11 | 2023-11-01 | [10 empty] | 0 | 0
12 | 2023-12-01 | [10 empty] | 0 | 0
|  | 14366057.73 | 171523.54 | 62037492.69 | 540133.25 | 2636623.84 | 5232.64 | 9660880.52 | 89829.02 | 2714061.44 | 19239.84 | 85986993.34 | 787478.61
w