## BIOGAS PLAN
S/N | DESCRIPTION OF ACTION | START DATE | END DATE
1 | Identify local vendors with capability to execute scope | 2018-06-06 | 2018-11-06
2 | Request For Information (RFI) | 2018-11-06 | 22/6/2018
3 | Invite Companies for Presentation at Shell I.A. (With Key Stakeholder) | 25/6/2018 | 29/6/2018
4 | Request for Cost Information (For benchmarks) | 2018-02-07 | 2018-09-07
5 | Consult internally with GHG champion & other identified Stakeholders to align with company aspirations | 2018-10-07 | 13/7/2018
6 | Engage infrastructure for area within RA to undertake pilot | 2018-11-07 | 20/7/2018
7 | MTB/SCC submission - PART A Approval | 23/7/2018 | 30/7/2018
8 | Issue ITT to Vendors | 2018-02-08 | 23/8/2018
9 | Undertake OLB | 23/8/2018 | 23/8/2018
10 | Part B - submission - Line approval | 27/8/2018 | 27/8/2018
11 | Award Pilot Contract | 31/8/2018 | 31/8/2018
12 | Sign Contract and kick off | 2018-03-09 | 2018-07-09
13 | Site Mobilisation/Execution | 21/9/2018 | 31/12/2018

## COST INFO
S/N | COST INCURRED ON VARIOUS WASTE STREAMS | Cost per Ton (NGN) | Likely Savings (%) | Based on
1 | Current cost executing biodegradeable Waste (Food) per ton
2 | Current cost executing biodegradeable Waste (STP) per ton