## Roadmap (IDEAL) (hidden)
1
2 | [15 empty] | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019
3 | [15 empty] | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
4 |  |  | 02/02/18 ROADMAP (IDEAL CASE)
5
6
7 | [63 empty] | 2019
8 |  |  | NOTE: ONLY CENTRAL RESOURCES, BLS NEED TO COMMIT CERTAIN LEVEL OF RESOURCES WHICH WOULD BE DETAILED | [12 empty] | 5 | 12 | 19 | 26 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
9 | [15 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M | T | W | T | F | #REF! | #REF! | M
10 | # | Category | Item | Output | Duration | Start | End | Owner | # ppl | # days | EWR/EY days | Support ppl | Comments |  | Stage | 5 #REF!: Feb; 5 #REF!: Mar; 2 #REF!: Apr; 7 M: May; 4 M: Jun; 2 M: Jul; 6 M: Aug; 3 M: Sep; 1 M: Oct; 5 M: Nov; 3 M: Dec; 2019 1 M: Jan+; 2019 1 T: Feb; 2019 1 T: Mar; 2019 1 #REF!: Apr; 2019 1 T: May; 2019 1 F: Jun; 2019 1 #REF!: Jul; 2019 1 W: Aug; 2019 1 #REF!: Sep; 2019 1 M: Oct; 2019 1 T: Nov; 2019 1 #REF!: Dec
11 | 1 | Processes | Map end to end procurement and supply chain processes for SOCAR business lines |  | 58 | 2018-01-19 | 2018-03-18 | [7 empty] | DI | bar: 5 #REF! to 12 #REF!
12 | 2 | Processes | - Conduct end to end processes diagnostics in STAR (1 week field visit) |  |  | 2018-02-26 | 2018-03-04 |  | 3 | 5 | 5 |  |  |  | DI | 26 #REF!: 3
13 | 3 | Processes | - Conduct end to end processes diagnostics in Petkim (1 week field visit) |  |  | 2018-03-04 | 2018-03-11 |  | 3 | 5 | 5 |  |  |  | DI | 5 #REF!: 3
14 | 5 | Processes | Identify improvement areas in current processes of STAR, Petkim and other BLs |  |  | 2018-03-11 | 2018-03-18 |  | 3 | 5 |  |  |  |  | DI | 12 #REF!: 3
15 | 6 | Processes | Design end state of supply chain value chain and its sub-processes (1): |  |  | 2018-03-18 | 2018-08-01 |  | 5 | fulltime | 1.5 pw |  |  |  | DE | 19 #REF!: 5; 26 #REF!: 5; 2 #REF!: 5; 9 #REF!: 5; 16 #REF!: 5; 23 #REF!: 5; 30 M: 5; 7 M: 5; 14 M: 5; 21 M: 5; 28 M: 5; 4 M: 5; 11 M: 5; 18 M: 5; 25 M: 5; 2 M: 5; 9 M: 5; 16 M: 5; 23 M: 5; 30 M: 5
16 | 7 | Processes | - Process flowchart for end to end supply chain value chain and its sub-processes (1) |  |  | 2018-03-18 | 2018-06-01 | [7 empty] | DE | bar: 19 #REF! to 28 M
17 | 8 | Processes | - Define roles and responsibilities allocation across different business lines, functions and positions within the fucntions (RACI matrix) |  |  | 2018-03-18 | 2018-06-01 | [7 empty] | DE | bar: 19 #REF! to 28 M
18 | 9 | Processes | - Develop an end to end toolkit (2) for each sub-process for full SC value chain: |  |  | 2018-03-18 | 2018-08-01 | [7 empty] | DE | bar: 19 #REF! to 30 M
19 | 10 | Processes | - Develop policies for each sub-process for full SC value chain |  |  | 2018-03-18 | 2018-08-01 | [7 empty] | DE | bar: 19 #REF! to 30 M
20 | 11 | Processes | - Develop work processes/procedures for each sub-process for full SC value chain |  |  | 2018-03-18 | 2018-08-01 | [7 empty] | DE | bar: 19 #REF! to 30 M
21 | 12 | Processes | - Develop relevant documentation and user manuals for substantiation of end to end supply chain toolkit |  |  | 2018-05-01 | 2018-09-01 | [7 empty] | DE | bar: 7 M to 27 M
22 | 13 | Processes | Hold alltogether and 1:1 workshop sessions to collect inputs, feedbacks to newsly designed end to end SC toolkit (2) |  |  | 2018-04-01 | 2018-09-01 | SOCAR | [6 empty] | DE | bar: 2 #REF! to 27 M
23 |  | Processes | - Session 1 Flowcharts |  |  | 2018-04-02 | 2018-04-05 | SOCAR | 3 | 3 | 3 |  |  | add 4 sessions 3 days * 4 ppl | DE | 2 #REF!: 3
24 |  | Processes | - Session 2 Practices |  |  | 2018-05-06 | 2018-05-08 | SOCAR | 3 | 3 | 3 |  |  | add 4 sessions 3 days * 4 ppl | DE | 7 M: 3
25 |  | Processes | - Session 3 Standard documents |  |  | 2018-06-04 | 2018-06-07 | SOCAR | 3 | 3 | 3 |  |  | add 4 sessions 3 days * 4 ppl | DE | 4 M: 3
26 |  | Processes | - Session 4 Strategies |  |  | 2018-07-02 | 2018-07-05 | SOCAR | 3 | 3 | 3 |  |  | add 4 sessions 3 days * 4 ppl | DE | 2 M: 3
27 | 14 | Processes | Amend the relevant SC toolkit documentation in line with feedback of stakeholders (BLs and HQ) |  |  | 2018-08-01 | 2018-09-01 |  | 5 | fulltime | 1 pw |  |  |  | DE | 6 M: 5; 13 M: 5; 20 M: 5; 27 M: 5
28 | 15 | Processes | Start roll-out of newly designed SC toolkit (pilot) in select BLs in part of SC value chain (Contracts Management pilot for Tank Farm project) |  |  | 2018-09-01 | 2018-11-01 | SOCAR | 5 | fulltime | 1 pw |  |  |  | O | 3 M: 5; 10 M: 5; 17 M: 5; 24 M: 5; 1 M: 5; 8 M: 5; 15 M: 5; 22 M: 5; 29 M: 5
29 | 17 | Processes | Full roll-out of new SC toolkit to all BLs in full SC value chain |  |  | 2018-11-01 | 2019-04-01 | SOCAR | 3 | [5 empty] | R | 5 M: 3; 12 M: 3; 19 M: 3; 26 M: 3; 3 M: 3; 10 M: 3; 17 M: 3; 24 M: 3; 31 M: 3; 2019 1 M: 3; 2019 2 T: 3; 2019 3 W: 3; 2019 4 T: 3; 2019 5 F: 3; 2019 6 #REF!: 3; 2019 7 #REF!: 3; 2019 8 M: 3; 2019 9 T: 3; 2019 10 W: 3; 2019 11 T: 3; 2019 12 F: 3; 2019 13 #REF!: 3; 2019 14 #REF!: 3; 2019 15 M: 3; 2019 16 T: 3; 2019 17 W: 3; 2019 18 T: 3; 2019 19 F: 3; 2019 20 #REF!: 3; 2019 21 #REF!: 3; 2019 22 M: 3; 2019 23 T: 3; 2019 24 W: 3; 2019 25 T: 3; 2019 26 F: 3; 2019 27 #REF!: 3; 2019 28 #REF!: 3; 2019 29 M: 3; 2019 30 T: 3; 2019 31 W: 3; 2019 1 T: 3; 2019 2 F: 3; 2019 3 #REF!: 3; 2019 4 #REF!: 3; 2019 5 M: 3; 2019 6 T: 3; 2019 7 W: 3; 2019 8 T: 3; 2019 9 F: 3; 2019 10 #REF!: 3; 2019 11 #REF!: 3; 2019 12 M: 3; 2019 13 T: 3; 2019 14 W: 3; 2019 15 T: 3; 2019 16 F: 3; 2019 17 #REF!: 3; 2019 18 #REF!: 3; 2019 19 M: 3; 2019 20 T: 3; 2019 21 W: 3; 2019 22 T: 3; 2019 23 F: 3; 2019 24 #REF!: 3; 2019 25 #REF!: 3; 2019 26 M: 3; 2019 27 T: 3; 2019 28 W: 3; 2019 1 T: 3; 2019 2 F: 3; 2019 3 #REF!: 3; 2019 4 #REF!: 3; 2019 5 M: 3; 2019 6 T: 3; 2019 7 W: 3; 2019 8 T: 3; 2019 9 F: 3; 2019 10 #REF!: 3; 2019 11 #REF!: 3; 2019 12 M: 3; 2019 13 T: 3; 2019 14 W: 3; 2019 15 T: 3; 2019 16 F: 3; 2019 17 #REF!: 3; 2019 18 #REF!: 3; 2019 19 M: 3; 2019 20 T: 3; 2019 21 W: 3; 2019 22 T: 3; 2019 23 F: 3; 2019 24 #REF!: 3; 2019 25 #REF!: 3; 2019 26 M: 3; 2019 27 T: 3; 2019 28 W: 3; 2019 29 T: 3; 2019 30 F: 3; 2019 31 #REF!: 3
30 | 18 | Governance | Understand current authority matrix in all business lines |  | 55 | 2018-01-19 | 2018-03-15 | [7 empty] | DI | bar: 5 #REF! to 12 #REF!
31 | 19 | Governance | Develop Operating Principle Guildeline from the Corporation to the Business Lines & PMO | Operating principle guideline document |  | 2018-03-15 | 2018-05-01 | [5 empty] | to be supported by ops and CEO; describes standardization requirements, key suppliers/contracts, why this has to take place and how to do it |  | DE | bar: 19 #REF! to 30 M
32 | 20 | Governance | Define and align on interface between central PSC and BLs (roles and responsibilities split, decision making councils, team set-up) |  |  | 2018-04-01 | 2018-07-01 | [7 empty] | DE | bar: 2 #REF! to 25 M
33 | 21 | Governance | - Align on required R&Rs of procurement and business |  |  | 2018-04-01 | 2018-06-01 | [7 empty] | DE | bar: 2 #REF! to 28 M
34 | 22 | Governance | - Define cross functional and cross BL councils that are required to support integrated way of working |  |  | 2018-05-01 | 2018-06-01 | [7 empty] | DE | bar: 7 M to 28 M
35 | 23 | Governance | - Align on cross functional and cross BL team set up to support integrated way of working |  |  | 2018-06-01 | 2018-07-01 | SOCAR | [6 empty] | DE | bar: 4 M to 25 M
36 | 24 | Governance | Define authority matrix for approvals both at BL and corporate level |  |  | 2018-04-01 | 2018-05-01 | [7 empty] | DE | bar: 2 #REF! to 30 M
37 | 25 | Governance | Obtain board approval for change of authority matrix |  |  | 2018-05-01 | 2018-09-01 | SOCAR | [6 empty] | O | bar: 7 M to 27 M
38 | 26 | Governance | Pilot in one BLs |  |  | 2018-09-01 | 2018-11-01 | SOCAR | [6 empty] | O | bar: 3 M to 29 M
39 | 27 | Governance | Roll-out new governance system |  |  | 2018-11-01 | 2019-04-01 | SOCAR | [6 empty] | R | bar: 5 M to 2019 31 #REF!
40 | 28 | Organization | Hire 5-10 FTEs for central PSC function to support design and operationalization stages (interim state) |  | 120 | 2018-02-01 | 2018-06-01 | [7 empty] | S | bar: 5 #REF! to 28 M
41 | 29 | Organization | Understand current organization design of procurement and supply chain in all business lines |  | 5 | 2018-03-05 | 2018-03-10 |  | 3 | 1 | 1 day |  |  |  | DI | bar: 5 #REF!
42 | 30 | Organization | Design Central PSC organization (structure, roles and responsibilities, FTE requirements and footprint, categories split vs BLs, etc.) | High level R&Rs |  | 2018-03-01 | 2018-09-01 |  | 1 | [5 empty] | DE | bar: 5 #REF! to 27 M
43 | 31 | Organization | - Assess required organizational structure, e.g. level of centralization vs decentralization |  |  | 2018-03-01 | 2018-05-01 | [7 empty] | DE | bar: 5 #REF! to 30 M
44 | 32 | Organization | - Assess category split between business lines and central operations |  |  | 2018-03-01 | 2018-07-01 | [7 empty] | DE | bar: 5 #REF! to 25 M
45 | 33 | Organization | - Define R&Rs | High level R&Rs |  | 2018-04-01 | 2018-06-01 | [7 empty] | DE | bar: 2 #REF! to 28 M
46 | 34 | Organization | - Align on R&R split between HQ and BLs | Decision: BL vs Central responsibilities | 14 | 2018-05-01 | 2018-07-01 | SOCAR |  |  |  |  | F2F |  | DE | bar: 7 M to 25 M
47 | 35 | Organization | - Assess FTE requirements in line with expected scope of work | # of FTEs (additional VS reallocation from BLs) |  | 2018-06-01 | 2018-07-01 | [7 empty] | DE | bar: 4 M to 25 M
48 | 36 | Organization | - Define footprint for FTEs (Istanbul vs Izmir split) |  |  | 2018-06-01 | 2018-07-01 | [7 empty] | DE | bar: 4 M to 25 M
49 | 37 | Organization | - Define Central PSC organization structure for HQ and BLs | Proposed PSC org chart |  | 2018-07-01 | 2018-09-01 | [5 empty] | completed after some understanding on processes is obtained |  | DE | bar: 2 M to 27 M
50 | 38 | Organization | Discuss and agree Central PSC org with leadership & BLs | CEO approval of Central PSC org |  | 2018-09-01 | 2018-11-01 | SOCAR | [6 empty] | DE | bar: 3 M to 29 M
51 | 39 | Organization | IF REQUIRED: Obtain board approval for final Central PSC organization | Board approval |  | 2018-11-01 | 2018-12-01 | SOCAR | [6 empty] | O | bar: 5 M to 26 M
52 | 40 | Organization | Roll-out / Go live (hire/reallocate) |  |  | 2018-12-01 | 2019-04-01 | SOCAR | [6 empty] | R | bar: 3 M to 2019 31 #REF!
53 | 41 | Organization | Design performance management for central PSC (scorecard, targets alignment, tracking mechanism, KPIs cascade) | KPI for each position |  | 2019-01-01 | 2019-03-01 |  | 1 | [5 empty] | DE | bar: 2019 1 M to 2019 28 W
54 | 42 | Organization | - Establish clear scorecard KPIs so that both contribution to business and service levels can be tracked | KPI for each position |  | 2019-01-01 | 2018-10-01 | [7 empty] | DE
55 | 43 | Organization | - Establish mechanism to align targets with other functions and resolve conflicts | Aligned targets |  | 2019-01-01 | 2018-10-01 | [7 empty] | DE
56 | 44 | Organization | - Identify and design tracking mechanism of key performance areas (e.g., definition and tracking of savings) |  |  | 2018-10-01 | 2018-11-01 | [7 empty] | DE | bar: 1 M to 29 M
57 | 45 | Organization | - Establish clear cascading KPIs for each position in CPSC organization |  |  | 2018-10-01 | 2018-11-01 | [7 empty] | DE | bar: 1 M to 29 M
58 | 46 | Organization | Define targets for 2019 in line with the strategy | Targets for each CPSC employee |  | 2019-03-01 | 2019-04-01 | SOCAR | [6 empty] | O | bar: 2019 1 T to 2019 31 #REF!
59 | 47 | Organization | Hold regular performance conversations, path to targets review and feedback sessions with PSC team | Targets for each CPSC employee |  | 2019-04-01 | 2019-12-31 | SOCAR | [6 empty] | C | bar: 2019 1 #REF! to 2019 30 #REF!
60 | 48 | People | Review existing procurement & supply chain talent pool (Petkim, STAR, Petlim, SOCAR Distribution, etc.) |  | 61 | 2018-04-01 | 2018-06-01 |  | 1 |  | 1 |  |  |  | DI | bar: 2 #REF! to 28 M
61 | 49 | People | Conduct full assessment of development areas for PSC team | Gaps / Training needs |  | 2018-06-01 | 2018-07-01 |  | 1 | [5 empty] | DI | bar: 4 M to 25 M
62 | 50 | People | Develop content for courses | Course materials |  | 2018-05-01 | 2018-10-01 |  | 1 |  |  |  | as practices become available |  | DE | bar: 7 M to 24 M
63 | 51 | People | - Contracts management courses | Course materials |  | 2018-05-01 | 2018-06-01 | [5 empty] | as practices become available |  | DE | bar: 7 M to 28 M
64 | 52 | People | - Materials management courses | Course materials |  | 2018-06-01 | 2018-10-01 | [5 empty] | as practices become available |  | DE | bar: 4 M to 24 M
65 | 53 | People | Deliver trainings | Training schedule |  | 2018-06-01 | 2019-04-01 | [7 empty] | C | bar: 4 M to 2019 31 #REF!
66 | 54 | People | Train the trainers |  |  | 2018-06-01 | 2018-08-01 | [5 empty] | as practices become available / intensive onboarding to align with practices |  | C | bar: 4 M to 30 M
67 | 55 | People | Provide on the job coaching |  |  | 2018-06-01 | 2019-04-01 | [5 empty] | assign subject matter experts / train the trainers to support implementation of the practices |  | C | bar: 4 M to 2019 31 #REF!
68 | 56 | Systems | Review existing systems and needs for SOCAR Turkiye business lines (Petkim, STAR, Petlim, SOCAR Distribution, etc.) |  | 55 | 2018-01-19 | 2018-03-15 |  |  |  | 200MH X 2 M |  |  |  | DI | bar: 5 #REF! to 12 #REF!
69 | 57 | Systems | Review best practice software tools and solutions for each step of the PSC process |  |  | 2018-03-01 | 2018-04-01 |  | 3 | [5 empty] | DE | 5 #REF!: 3; 12 #REF!: 3; 19 #REF!: 3; 26 #REF!: 3
70 | 58 | Systems | Identify improvement areas in current software tools of STAR, Petkim and other BLs |  |  | 2018-03-01 | 2018-04-01 | [7 empty] | DE | bar: 5 #REF! to 26 #REF!
71 | 59 | Systems | Design an end state integrated software solution for end to end supply chain value chain and its sub-processes (e.g. strategic procurement, ops procurement, contracts management, materials management, warehousing, logistics, spare parts management) |  |  | 2018-04-01 | 2018-06-01 |  | 3 |  | 200MH X 2 M |  |  |  | DE | 2 #REF!: 3; 9 #REF!: 3; 16 #REF!: 3; 23 #REF!: 3; 30 M: 3; 7 M: 3; 14 M: 3; 21 M: 3; 28 M: 3
72 | 60 | Systems | Run a tender process to gather offers from different software vendors and select the target system |  |  | 2018-06-01 | 2018-08-01 | SOCAR | 3 | [5 empty] | O | 4 M: 3; 11 M: 3; 18 M: 3; 25 M: 3; 2 M: 3; 9 M: 3; 16 M: 3; 23 M: 3; 30 M: 3
73 | 61 | Systems | Start installation / implementation / integration |  |  | 2018-08-01 | 2019-04-01 | [7 empty] | R | bar: 6 M to 2019 31 #REF!
74 | 62 | Value Creation | Initiatives implementation in Operations Procurement |  | 410 | 2018-02-15 | 2019-04-01 | [7 empty] | V | bar: 19 #REF! to 2019 31 #REF!
75 | 63 | Value Creation | Initiatives implementation in Administrative Procurement |  |  | 2018-01-01 | 2018-08-01 | [7 empty] | V | bar: 5 #REF! to 30 M
76 | 64 | Value Creation | Initiatives implementation in Projects Procurement |  |  | 2018-06-01 | 2019-04-01 | [7 empty] | V | bar: 4 M to 2019 31 #REF!
77 | 65 | Value Creation | Initiatives for Tank Farm project (TBD w/Egbert) | [11 empty] | V
78 | 66 | Value Creation | Alignment of Petkim Shutdown and project Venus (TBD w/Egbert) |  |  |  |  | SOCAR | [6 empty] | V
79 | 67 | Value Creation | Early inventory alignment to reduce STAR spare parts inventory (TBD w/Egbert) | [11 empty] | V
80
81 | [8 empty] | TOTAL | [5 empty] | # ppl | 5 #REF!: 0; 12 #REF!: 0; 19 #REF!: 0; 26 #REF!: 3; 5 #REF!: 7; 12 #REF!: 7; 19 #REF!: 9; 26 #REF!: 9; 2 #REF!: 13; 9 #REF!: 10; 16 #REF!: 10; 23 #REF!: 10; 30 M: 10; 7 M: 14; 14 M: 11; 21 M: 11; 28 M: 11; 4 M: 14; 11 M: 11; 18 M: 11; 25 M: 11; 2 M: 13; 9 M: 10; 16 M: 10; 23 M: 10; 30 M: 10; 6 M: 7; 13 M: 7; 20 M: 7; 27 M: 7; 3 M: 6; 10 M: 6; 17 M: 6; 24 M: 6; 1 M: 5; 8 M: 5; 15 M: 5; 22 M: 5; 29 M: 5; 5 M: 3; 12 M: 3; 19 M: 3; 26 M: 3; 3 M: 3; 10 M: 3; 17 M: 3; 24 M: 3; 31 M: 3; 2019 1 M: 4; 2019 2 T: 4; 2019 3 W: 4; 2019 4 T: 4; 2019 5 F: 4; 2019 6 #REF!: 4; 2019 7 #REF!: 4; 2019 8 M: 4; 2019 9 T: 4; 2019 10 W: 4; 2019 11 T: 4; 2019 12 F: 4; 2019 13 #REF!: 4; 2019 14 #REF!: 4; 2019 15 M: 4; 2019 16 T: 4; 2019 17 W: 4; 2019 18 T: 4; 2019 19 F: 4; 2019 20 #REF!: 4; 2019 21 #REF!: 4; 2019 22 M: 4; 2019 23 T: 4; 2019 24 W: 4; 2019 25 T: 4; 2019 26 F: 4; 2019 27 #REF!: 4; 2019 28 #REF!: 4; 2019 29 M: 4; 2019 30 T: 4; 2019 31 W: 4; 2019 1 T: 4; 2019 2 F: 4; 2019 3 #REF!: 4; 2019 4 #REF!: 4; 2019 5 M: 4; 2019 6 T: 4; 2019 7 W: 4; 2019 8 T: 4; 2019 9 F: 4; 2019 10 #REF!: 4; 2019 11 #REF!: 4; 2019 12 M: 4; 2019 13 T: 4; 2019 14 W: 4; 2019 15 T: 4; 2019 16 F: 4; 2019 17 #REF!: 4; 2019 18 #REF!: 4; 2019 19 M: 4; 2019 20 T: 4; 2019 21 W: 4; 2019 22 T: 4; 2019 23 F: 4; 2019 24 #REF!: 4; 2019 25 #REF!: 4; 2019 26 M: 4; 2019 27 T: 4; 2019 28 W: 4; 2019 1 T: 3; 2019 2 F: 3; 2019 3 #REF!: 3; 2019 4 #REF!: 3; 2019 5 M: 3; 2019 6 T: 3; 2019 7 W: 3; 2019 8 T: 3; 2019 9 F: 3; 2019 10 #REF!: 3; 2019 11 #REF!: 3; 2019 12 M: 3; 2019 13 T: 3; 2019 14 W: 3; 2019 15 T: 3; 2019 16 F: 3; 2019 17 #REF!: 3; 2019 18 #REF!: 3; 2019 19 M: 3; 2019 20 T: 3; 2019 21 W: 3; 2019 22 T: 3; 2019 23 F: 3; 2019 24 #REF!: 3; 2019 25 #REF!: 3; 2019 26 M: 3; 2019 27 T: 3; 2019 28 W: 3; 2019 29 T: 3; 2019 30 F: 3; 2019 31 #REF!: 3; 2019 1 #REF!: 0
82
83 |  |  | NOTES:
84 |  |  | (1) - e.g. strategic procurement, ops procurement, contracts management, materials management, warehousing, logistics, spare parts management)
(2) - policies, work practices (procedures) and standard documents
[18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
EWR | bar: 26 #REF! to 12 #REF!; 2 #REF!; 7 M; 4 M; 2 M; 5 M to 31 M
EY | bar: 26 #REF! to 12 #REF!; 2 #REF!; 7 M; 4 M; 2 M; 5 M to 31 M
[6 empty] | SOCAR - SCM |  |  |  |  | PROCUREMENT MANAGER (BP GUY) | bar: 19 #REF! to 29 M
[6 empty] | SOCAR - SCM |  |  |  |  | INSPECTION/EXPEDITING | bar: 19 #REF! to 29 M
[6 empty] | SOCAR - SCM |  |  |  |  | WAREHOUSING | bar: 19 #REF! to 29 M
[6 empty] | SOCAR - SCM |  |  |  |  | STRATEGY | bar: 19 #REF! to 29 M
[6 empty] | SOCAR - SCM |  |  |  |  | LOGISTICS | bar: 19 #REF! to 29 M
[6 empty] | SOCAR - SCM |  |  |  |  | EP | bar: 5 #REF! to 30 M
[6 empty] | SOCAR - SCM |  |  |  |  | SYSTEMS | bar: 5 #REF! to 30 M
[6 empty] | MCKINSEY |  |  |  |  | SYSTEMS + PROCESSES | bar: 5 #REF! to 30 M
[6 empty] | MCKINSEY |  |  |  |  | PROCESSES | bar: 26 #REF! to 12 #REF!; 2 #REF!; 7 M; 4 M; 2 M; 5 M to 31 M
[6 empty] | MCKINSEY |  |  |  |  | ORG + PROCESSES | bar: 5 #REF! to 27 M
[6 empty] | MCKINSEY |  |  |  |  | TALENT REVIEW + PROCESSES | bar: 2 #REF! to 25 M
[6 empty] | MCKINSEY |  |  |  |  | TRANING + PROCESSES | bar: 7 M to 24 M
Formulas:
Start = [End, row above]
Start = [Start, row above]
End = [Start]+7
End = [End, row above]
Note on J12: Laman Valizada: LV/EWR/ER
Note on J15: Laman Valizada: PM
Note on J22: Laman Valizada: BL leads for each group EY/EWR/LV/AK
Note on J23: Laman Valizada: BL leads for each group EY/EWR/LV/AK
Note on J24: Laman Valizada: BL leads for each group EY/EWR/LV/AK
Note on J25: Laman Valizada: BL leads for each group EY/EWR/LV/AK
Note on J26: Laman Valizada: BL leads for each group EY/EWR/LV/AK
Note on J27: Laman Valizada: us + 1 dedicated person for reviewing BL needs (bp guy?)
Note on J28: Laman Valizada: us + 1 dedicated person for reviewing BL needs (bp guy?)
Note on J68: Laman Valizada: BP GUY, EP, PMK (EXPERT)

## Implementation plan
[9 empty] | year > | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021
[9 empty] | month > | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
|  |  | Completed | On track | At risk | Delayed | Cancelled |  | if needed - grouping of type of steps > | V - value creation | [126 empty] | Diagnostics | [31 empty] | DI - diagnostics | [48 empty] | S - set-up | [38 empty] | DE - design | [38 empty] | O - operationalization | [67 empty] | R - roll-out | [49 empty] | C- capability building
|  | AIRFRAMES | [7 empty] | 2020 | [213 empty] | 2021
[9 empty] | day > | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
# | Category | Item | Status | Duration | Start | End | Owner | Comments | Stage | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan+ | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun | [29 empty] | Jul | [30 empty] | Aug | [30 empty] | Sep | [29 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec
1 | COMMERCIAL | Obtain approval from the Steering Committee to engage the vendor | On track | 25 | 2020-06-01 | 2020-06-26 | Ike |  | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE
2 | COMMERCIAL | Develop vendor engagement strategy (BATNA) | On track | 14 | 2020-06-26 | 2020-07-10 | Amina |  | DE | [25 empty] | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE
3 | COMMERCIAL | Schedule engagement with vendor | On track | 14 | 2020-06-26 | 2020-07-10 | Ian |  | DE | [25 empty] | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE
4 | COMMERCIAL | Engage the vendor to agree operating model with 4 aircrafts | On track | 21 | 2020-07-10 | 2020-07-31 | Contract Holder |  | DE | [39 empty] | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE
5 | COMMERCIAL | Release the note to the vendor + 90 days notification period | On track | 91 | 2020-07-31 | 2020-10-30 | Contract Holder |  | DE | [60 empty] | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE | DE
6 | COMMERCIAL | Financial benefits start accruing | On track | 62 | 2020-10-30 | 2020-12-31 |  |  | V | [151 empty] | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V
7 | PROCESS | Conduct "Demand on paper" exercise: simulate operational planning to meet historic demand for 4 representative weeks covering various activity levels; identify all instances when demand wouldn't be met and potential optimisation approach | On track | 21 | 2020-07-31 | 2020-08-21 | Ian (working team: Robbert + schedulers + Krishna) |  | O | [60 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
8 | PROCESS | Incorporate requirements for constraint-based demand planning into end-to-end logistics mnagement system | On track | 25 | 2020-08-21 | 2020-09-15 | Ike |  | O | [81 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
9 | PROCESS | Agree integrated logistics scheduling process with the key stakeholders to ensure buy-in and collaboration | On track | 45 | 2020-09-15 | 2020-10-30 | Ike |  | O | [106 empty] | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O | O
10 | PROCESS | Operate based on revised process | On track | 62 | 2020-10-30 | 2020-12-31 | Ian |  | V | [151 empty] | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V | V
11 | [8 empty] | DE
12 | [8 empty] | DE
13 | [8 empty] | DE
14 | [8 empty] | DE
15 | [8 empty] | DE
16 | [8 empty] | DE
17 | [8 empty] | O
18 | [8 empty] | O
19 | [8 empty] | O
20 | [8 empty] | R
21 | [8 empty] | R
22 | [8 empty] | R
23 | [8 empty] | DI
24 | [8 empty] | DE
25 | [8 empty] | DE
26 | [8 empty] | DE
27 | [8 empty] | DE
28 | [8 empty] | DE
29 | [8 empty] | DE
30 | [8 empty] | O
31 | [8 empty] | O
32 | [8 empty] | R
33 | [8 empty] | S
34 | [8 empty] | DI
35 | [8 empty] | DE
36 | [8 empty] | DE
37 | [8 empty] | DE
38 | [8 empty] | DE
39 | [8 empty] | DE
40 | [8 empty] | DE
41 | [8 empty] | DE
42 | [8 empty] | DE
43 | [8 empty] | DE
44 | [8 empty] | O
45 | [8 empty] | R
46 | [8 empty] | DE
47 | [8 empty] | DE
48 | [8 empty] | DE
49 | [8 empty] | DE
50 | [8 empty] | DE
51 | [8 empty] | O
52 | [8 empty] | C
53 | [8 empty] | DI
54 | [8 empty] | DI
55 | [8 empty] | DE
56 | [8 empty] | DE
57 | [8 empty] | DE
58 | [8 empty] | C
59 | [8 empty] | C
60 | [8 empty] | C
61 | [8 empty] | DI
62 | [8 empty] | DE
63 | [8 empty] | DE
64 | [8 empty] | O
65 | [8 empty] | R
66 | [8 empty] | V
67 | [8 empty] | V
68 | [8 empty] | V
69 | [8 empty] | V
70 | #REF! | #REF! |  | 0 |  |  |  |  | #REF!
71 | #REF! | #REF! |  | 0 |  |  |  |  | #REF!
Formulas:
At risk = [Delayed, row above]
At risk = [At risk, row above]
Delayed = [At risk]+14
Delayed = [Delayed, row above]

## Actions
ACTION TRACKER
Last update:
# | Activity | Action | Responsible | Timeline | Forecast | Actual date received | Status | comments
1
2
3
4
5 | 0 Preparation for Feb 15 | Structure the roadmap & send to Egbert | Laman | 29/01 (next Monday) |  |  | Done
6
7 | 0 Preparation for Feb 15 | Schedule 2 VCs per week with Egbert | Laman | 29/01 (next Monday) |  |  | Done | 8:30 morning till 10pm / Monday Wednesday Friday
8
9
10
11
12
13
14
15
16
17
18
19 | 2 Design | Egbert to share example of the Ops Guideline | Egbert | 09/02 (next Friday) |  |  | Done
20 | 2 Design | Send savings targets estimation methodology | McK | 09/02 (next Friday) |  |  | Done
21
22
23