## AC-09 Risk Assessment
2348070232858
TOP EVENT: POSSIBLE FIRE OUTBREAK / OIL SPILL
UWI | Traffic Light Status | Cluster | AC | Well Name | WFM Type | Well Status | Reasons | People | Asset | Community | Environment | Overal Risk | Current Mitigations in Place | General Comments | Mitigation Actions | Action Timeline | Action Party | Expected Closure Date | Recommendation
400000001640 | R | Cluster 95 | 9 | FOCY102 | LP | Closed in | LS: FWVI SS: SSSV2, SSV2, SV2, UMV2, | C2 | C3 | C3 | C3 | Medium | 1. Wellhead caged. 2. SS: Not a flowing conduit - quit production. 3. LS valve tested and integral (MV, SV and SSSV functional). 3. Xmas tree cap integral and available. | SS: The measured CITHP is 48 bar. No functional barrier. LS: FWV is the only failure in LS. | SS: 1. Well should remain closed-in 2. Prod Ops to measure current CITHP and confirm. 3. Grease failed valves with grease guns. 4. If greasing fails, well to be suspended with a downhole plug (Securing proposal signed off). LS: 1. Routine Surveillance to be carried out on the LS & SS. 2. Grease failed valves with grease guns and carry out a repeat WIT. 3. Change out the FWV for LS. | SS 1. 05/08/2021. 2. 05/08/2021. 3. 05/08/2021 4. 30/04/2022. LS 1. Daily 2. 05/08/2021. 3. 30/04/2022.. | SS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. Opns - Femi / Dapiriye. 4. CWI - Chinedu LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu |  | 1. Leave SS closed-in 2. Leave FORC102L Flowing
400000001378 | R | FODPA | 9 | FOCY123 | LP | Flowing | LS: SSSV, SV SS: SSSV2, LMV2, SV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead IDS cage available but deactivated. 2. LS valves tested and integral (MV, SSV and FWV) 3. SS valves teated and integral (FWV and SSV). 3. Xmas tree cap integral and available. | SS: The measured CITHP is 10 bar. No functional barrier. LS:The measured CITHP is 17 bar. The well is an intermittent producer (PBU) well | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC123L/S flowing. Leave FORC123S flowing as PBU
400000001377 | R |  | 9 | FOCY122 | LP | Flowing | LS: SSV, SS: LMV2, SSSV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead IDS cage available but deactivated. 2. LS can not flow naturally and currently closed-in. All Xmas tree valves functional. 2. LS valves tested and integral (SCSSSV, MV, SV and FWV) 3. SS valve tested and integral (SV / FWV). 4. Xmas tree cap integral and available. | SS: The measured CITHP is 34 bar. Only 1 functional barrier. LS:The measured CITHP is 38 bar. | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | leave FORC122L/S Flowing
400000001638 | R | Cluster 95 | 9 | FOCY100 | LP | Closed in | LS: SSSV, SV SS: LMV2, SSSV2,, SV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage. 2. LS MV & WV integral. 3. SS valves teated and integral (FWV and SSV). 4. Xmas tree cap integral and available. | SS: The measured CITHP is 40bar. No functional barrier. LS:The measured CITHP is 65 bar. | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave both arms closed-in
400000001635 | R | Cluster JA | 9 | FOCY135 | LP | Flowing | LS: SSV, LMV, SS: SSV2, LMV2, SSSV2 | C3 | C3 | C3 | C4 | MEDIUM | 1. No wellhead cage 2. LS cannot flow naturally. 3. LS SCSSSV, SV & WV integral. 4. SS valves tested and integral (SV / FWV). 5. Xmas tree cap integral and available. | SS: Well currently flowing with 1 barrier. CITHP = 18 barg LS: Quit production. CITHP = 13 barg | Top LS/SS 1. Daily Radar surveillance from Geomatics Team 2. Visit the cluster for surveillance - FORC135 3. FORC135S bean check should be suspended till the second barrier (LMV and ScSSSV) is fixed. 4. Continue to Flow FORC135S and monitor sand production level from sampling. 5. Check the Well integrity sequence to prioritize the high risk. | LS/SS 1. Daily 2. Once every 2 days 3. 30/04/2022. 4. monthly 5. Once | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. Ops - Femi / Dapririye 4. Ops - Femi / Dapririye 5. Chinedu | 1. 14th Feb 2020. 2. 14th Feb 2020. 3. Daily. 4. 30th Mar 2020 | 1. Fix ScSSV & failed valves immediately.
400000001631 | R | Cluster 20 | 9 | FOCY047S1 | LP | Flowing | LS: SSSV, SV | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage. 3. LS valves tested and integral (MV / FWV ). 3. Xmas tree cap integral and available.. 4. SS integral (no issues) | LS:The measured CITHP is 15 barg. SS: Integral with no failures | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC047L/S Flowing
400000001362 | R | Cluster 2 | 9 | FOCY028 | LP | Closed in | LS: SSV SSSV, SS: SV2, SSSV2, UMV2 | C3 | C3 | C3 | C4 | MEDIUM | 1. Wellhead cage. 2. LS: SSV and SSSV failed (Other WH valves passed). 3. SS: SV2, UMV2 and SSSV2 failed test. 4. Xmas tree cap integral and available. | LS:The measured CITHP is 165psig SS: The measured CITHP is 550psig. All strings closed in due to bulkline outage The well is in Estuary (Offshore). | Top LS/SS 1. Daily Radar surveillance from Geomatics Team 2. Visit the cluster for surveillance - FORC028 3. FORC028 will remain closed-in till restoration of cluster integrity. 4. Prioritize the AC-09 wells in the Well integrity securing sequence. | LS/SS 1. Daily 2. Once every 2 days 3. once 5. Once | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. Opns - Femi / Dapiriye 4. CWI - Chinedu |  | Leave Closed-in
|  | Standalone Yokri Land | 9 | FOCY127S1 | GL | Flowing | T: SSSV, SV | C4 | C2 | C4 | C2 | Medium | 1. Valve tested and ok (MV & WV) 2. Xmas tree cap. 3. Standalone Yokri Land well | The well is in close proximity to people in the community and it is a concern. | 1. Grease valves with grease guns. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC127T well Flowing
|  | Cluster 5A | 9 | FOCY131 | LP | Flowing | LS: SSV2 SS: SSSV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage and fence 2. XMT tree cap integral and available 3. Valves tested ok (MV, SV & FWV). | The well is in Estuary (Offshore). LS: Producing. CITHP = 28 barg SS: Closed-in. CITHP = 20 barg SSV stuck in open position. | 1. Obtain grease/grease guns and grease failed valve (Ops) 2. Carry out daily surveillance on the well. 3. Carry out SLM on ScSSV & failed valves. 3. Change out ScSSV if CM is unsuccessful. | 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | 1. Leave LS flowing. 2. Leave SS Closed-in.
|  | Cluster 9 | 9 | FOCY056 | LP | Closed in | LS: SSSV, SSV. SS: SV2, SSV2, SSSV2 | C3 | C3 | C3 | C4 | MEDIUM | 1. IDS Wellhead cage dismantled and not functional. 2. Well on deviation 3. LS: SSV, SSSV failed. (others WH valves passed) 4. SS: SV, SSV, SSSV failed (FWV passed) 3. Xmas tree cap integral and available.. | The well is in Estuary (Offshore). LS: CITHP = 100 barg SS: Closed-in. CITHP = 10 barg | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC056L/S closed-in
|  | Cluster 51 | 9 | FOCY072S1 | LP | Closed in | T: SSSV, SSV | C3 | C3 | C3 | C4 | MEDIUM | 1. No wellhead cage. 2. Well on deviation. 3. Singe string: SSV and SSSV failed test. 3. Xmas tree cap integral and available. 4. FORC072T is flowing | FORC072T is flowing; CITHP 334psig Flow to Yokri | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | 1. 05/08/2021 2. Daily 3.30/04/2022. 4.30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Fix failed valves and open-up well after rig demob
|  | Cluster JA | 9 | FOCY134 | LP | Flowing | LS: SV SS: SV2, SSSV2, | C3 | C3 | C3 | C4 | MEDIUM | 1. No Wellhead cage. 2. CMB WIT/SIT in Nov 2021: LS:SV and SS: SV and SSSV 3 FORC134L is producing 4. Xmas tree cap integral and available. | Long string is producing; short string is closed in. Flows to Estuary | Top LS/SS 1. Daily Radar surveillance from Geomatics Team 2. Visit the cluster for surveillance - FORC134 3. FORC134S will remain closed-in (PBU well) 4. Prioritize the AC-09 wells in the Well integrity securing sequence. | LS/SS 1. Daily 2. Once every 2 days 3. once 5. Once | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. Opns - Femi / Dapiriye 4. CWI - Chinedu |  | 1. Leave LS flowing. 2. Leave SS Closed-in.
|  | Cluster 16 | 9 | FOCY125 | LP | Flowing | SSSV, UMV | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage 2. All the valves are integral except the UMV and SSSV | No assurance task on this well > 2017 | 1. Plan for CM 2. Carry out monthly surveillance on well 3. Functional wellhead cage. 4. All the other valves are functional 5. Review the CMB WIT/SIT with the Engineer (Tunji -) 6. CWI to fix the wells - Share the plan (Chinedu)
|  | Location 9 | 9 | FOCY114 | LP | Flowing | LS: SV, UMV SS: SV2, SSSV | C3 | C3 | C3 | C4 | MEDIUM | 1. No Wellhead cage. 2. Cmb WIT/SIT of Sept 21 showed failures: LS: SV and UMV failed. SS: SV and SSSV failed 3. Xmas tree cap integral and available. 4. FORC114S is producing on gaslift | Long string is closed-in; Short string is still producing. Yokri Well | Top LS/SS 1. Daily Radar surveillance from Geomatics Team 2. Visit the cluster for surveillance - FORC028 3. FORC114L will remain closed-in (Fish in hole) 4. Prioritize the AC-09 wells in the Well integrity securing sequence. | LS/SS 1. Daily 2. Once every 2 days 3. once 5. Once | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. Opns - Femi / Dapiriye 4. CWI - Chinedu | 1. Leave LS flowing. 2. Leave SS Closed-in. | 1. Leave LS closed-in 2. Leave SS flowing
Tammy Biambo