## Team Members
Role |  | Name | Email ID | Status
AF | Asset Focal | Ajayi, Olakunle J SPDC-UPC/G/USR Orjiakor, Charles SPDC-UPC/G/USMP | olakunle.ajayi@shell.com C.Orjiakor@shell.com | In -progress
AREE | Asset Rotating Equipment Engineer - Rotating Equipment Focal | Odunze, Kenechukwu A SPDC-UPC/G/USM Idio, Samuel N SPDC-PTP/O/NE Amoye, Godfrey T SPDC-UPC/G/USM Digbani, Tamunofiri M SPDC-UPC/G/USMR | Kenechukwu.Odunze@shell.com Samuel.Idio@shell.com Godfrey.Amoye@shell.com tamuno.digbani@shell.com | Not started
APT | Asset PACO TA - Control valve Focal | Awe, Afolabi T SPDC-UPC/G/USM | Afolabi.Awe@shell.com | Completed
APTME | Asset Proactive Technical Montioring Eng | Ajayi, Olakunle J SPDC-UPC/G/USR Orjiakor, Charles SPDC-UPC/G/USMP Henshaw, Gideon SPDC-UPC/G/USMR Uche, Ugochukwu S SPDC-UPC/G/USM | olakunle.ajayi@shell.com C.Orjiakor@shell.com G.Henshaw@shell.com Ugochukwu.Uche@shell.com | On Hold
ADE / AIDT | Asset Data Engineer /Asset Information Technology | Ariyo, Oluwatoyin A SNBO-PTIZ/C/ND Egwu, Emmanuel O SPDC-PTIZ/C/N Enyinnaya, Ikedichi C SPDC-PTIZ/C/NA | O.Ariyo@shell.com Emmanuel.Egwu@shell.com ikedichi.enyinnaya@shell.com | Delayed
ADS | Asset Data Scientist | Saka, Adesina M SPDC-PTIZ/C/NS Omoko, Nonso SPDC-PTIZ/C/NS Ajayi, Olakunle J SPDC-UPC/G/USR | adesina.saka@shell.com nonso.omoko@shell.com olakunle.ajayi@shell.com
AREL | Asset Reliability Engineer | Umunna, Odinakachi N SPDC-UPC/G/USR | Odinakachi.Umunna@shell.com
APE | Asset Process Engineer | Parker, Aisha SPDC-PTP/O/NE | Nana-Aisha.Parker@shell.com
AFO | Asset Field Operations | Zimughan, Joseph T SPDC-UPC/G/UCG Unutaro, Joshua OE SPDC-UPC/G/UCG Memberr, Igbigioyibo E SPDC-UPC/G/UCG Oniwo, Abraham A SPDC-UPC/G/UCG Ovoh, Anthony E SPDC-UPC/G/UCG Akinlolu, Haruna I SPDC-UPC/G/UCG Ibrahim, Saheed O SPDC-UPC/G/UCG Ekanem, IT N SPDC-UPC/G/UCG Njoku, Richard O SPDC-UPC/G/UCG Durodola, Oba' A SPDC-UPC/G/UCG Bosini, Oghenevwogaga M SPDC-UPC/G/UCG Hanson, Enobong J SPDC-UPC/G/UCG Bestman, Soikramari D SPDC-UPC/G/USMD | Joseph.Zimughan@shell.com joshua.unutaro@shell.com Igbigioyibo.Memberr@shell.com Abraham.Oniwo@shell.com anthony.ovoh@shell.com haruna.akinlolu@shell.com saheed.ibrahim@shell.com Itoro.Ekanem@shell.com richard.njoku@shell.com Obadamilare.Durodola@shell.com Oghenevwogaga.Bosini@shell.com Enobong.Hanson@shell.com soikramari.bestman@shell.com
AEE | Asset Electrical Engineer | Onumadu, Chibuzo S SPDC-UPC/G/USM Osaigbovo, Diana R SPDC-UPC/G/USMD | Chibuzo.Onumadu@shell.com Diana.Osaigbovo@shell.com
PINS | Predictive Maintanance TAO Instrumentation Engineer | Sahl, Mohammed SSSCCH-PTS/TMW | Mohammed.Sahl@shell.com
PREQ | Predictive Maintanance TAO Rotating Equipment Engineer | Behera, Soumya R SSSCCH-PTS/TMI | Soumya.Behera@shell.com
PDS | Predictive Maintanance Data Scientist | Sudhakar, Sidarth SSSCCH-PTIY/FHC Mishra, Atul SSSCCH-PTIY/FHC | S.Sudhakar@shell.com Atul.Mishra@shell.com
PDE | Predictive Maintanance Data Engineer | Ranjan, Ashish SBOBNG-PTIY/FHC Farrant, Colin SITI-PTIY/FHC | A.Ranjan2@shell.com Colin.Farrant2@shell.com
PDL | Predictive Maintanance Deployment Lead | Ravi, Gopi SBOBNG-PTIZ/T/M | Gopi.G.Ravi@shell.com
PPLM | Predictive Maintanance Product Line Manager | Blake, Richard J GSNL-PTIZ/T/M | Richard.Blake@shell.com
PPO | Predictive Maintanance Product Owner | Burrell, Susan GSUK-PTS/IG Melendez, Jorge L GSUSI-PTS/IG | Susan.Burrell@shell.com Jorge.Melendez@shell.com
PBDO | Predictive Maintenance BOM/Deployment Owner | Ofori, Kebin M SPDC-UPC/G/US | kebin.ofori@shell.com

## CV
Control Valve Predictive Analytics (Jan - Jun 2022)
sn | Task | Description | Primary Focal | Supported | Status | Comment | Status Update | Deliverable | Time
1 | Preparation / Kick-off
| Pre requiste activities | Confirm resource availability | PDL / AF |  | Completed |  |  | Resource list | Jan
|  | Capability Assessment of resource persons | PDL / AF |  | Completed |  |  | RACI
|  | Determine Asset Readiness/Resources | PDL / AF |  | Completed |  |  | RACI
|  | Define scope | PDL / AF |  | Completed | Activate relevant instrument tags |  | List of CVs with tag names
|  | Communication, stakeholder alignments | PDL / AF |  | Completed | Detail scope to be communicated to stakeholders |  | Meeting minutes
|  | IRM Assesment to load data in C3 | PDL |  | Completed |  |  | IRM sign off e-mail
2 | Access
| Tool access to all stakeholders | List of users need access to C3 tool | AF |  | Completed |  |  | user list | Feb
|  | Provide required access to C3 tool | PDL |  | Completed | Access provided |  | SNOW Request
|  | Provide acess to PDM TAO for local PI Server and SeeQ | AIDT | AIDT | Completed | Access provided |  | Access confirmation
3 | Gather data
| Deliver good quality data, and good failure cases | Provided Tags list for agreed Control valves | APT | AIDT | Completed | 115 CV's are identified as Phase-1 |  | csv files | Jan - Feb
|  | Provide P& ID's for all control valves | AF | AFO | Completed | Uploaded in the Sharepoint | kunle will share the required P&ID's | P&ID's
|  | Provide SAP Reports (Functional locations) | AF | AFO | Completed |  |  | csv files
|  | Examine all the information provided (tag list, P&ID's, Limits, etc..) | PINS | APT | Completed
4 | Data Load
| Load required data in to C3 for modelling | Create AF Hierachy | PDE | AIDT | Completed | Row No 18,19,20 are critical path |  |  | Feb
|  | Load all tags / data in to C3 | PDE / PDS | AIDT | Completed | Row No 18,19,20,23,are critical path | Data is loaded until 2021 remaining data will be loaded by this week
|  | Data Quality / availability Checks | PDE / PDS | AIDT | Completed | Row 24 critical path | .Mode tags created but not getting required data in format | Report
5 | Model Training and Review
|  | Run no model scripts for control valve | PDS | AIDT / ADS | Completed | 70 No Model Possible - may increase after manual model review |  | Report | Mar
|  | Run bulk jobs for auto live models | PDS | AIDT / ADS | Completed | 45 CV's bulk jobs in-progress - 26 Transmiters, 9 CV's has 1 month data Sahl to check with PI team if we can get history data from Source |  | Report
|  | Working Sessions - Model Trainign, Bulk Jobs, Model Review | PINS / PDS / AF | AIDT / ADS / All | Completed | 1st session completed on 22nd April, 2nd session planned for 3rd June |  | Meeting minutes | Apr-June
|  | Perform Model review and training for remaining valves | PINS / AF | AIDT / ADS | In -progress
|  | Make models live | PINS / AF | AIDT / ADS | In -progress | Currently we have 6 valves live
6 | Review anomaly detection
| Sign-off from SME that model is identifying anomalies | Integrate C3 Alerts in to EBS and setup email alert system | PDL |  | Completed |  |  |  | Apr
|  | Training sessions for Assets focal and Survielance team | Nikki |  | Completed
|  | Provide list of users need access to EBS | AF |  | Completed
|  | Provide access to all users | PDL |  | Completed
|  | Evaluate detected analomalies from EBS | PINS / AF | APTME | In -progress | Row no 31 is critical path
|  | Perform root cause analysis | PINS / AF | APTME | In -progress | Row no 31 is critical path
7 | Training & Handover
| Training to handover model training and review | Provide EBS training | Nikki | APTME / All | Completed | Planned for 11th may |  |  | May
|  | Share all recordings and user guides | Nikki | AF | Completed
|  | Perform model training and review for some of the valves | ADS / AIDT | PINS | Completed
|  | Prepare check list for Product support team (local data scientist/ Local C3 IT team) | PINS / PDS / AF | ADS / AIDT | Completed |  |  |  | June
|  | Prepare and implement Surveilance model for PDM | APTME | AINS | Completed

## CE
Compressor Predictive Analytics (Jan - Jun 2022)
sn | Task | Description | Team/Role | Supported | Status | Comment | Deliverable | Expected Data of Completion
1 | Preparation / Kick-off
| Pre requiste activities | Confirm resource availability | PDL / AF |  | Completed | TAO RE not yet identified (Soumya supporting) | Resource list | Jan - Feb
|  | Capability Assessment of resource persons | PDL / AF |  | Completed |  | RACI
|  | Determine Asset Readiness/Resources | AF |  | Completed |  | RACI
|  | Define scope | PDL / AF |  | Completed | Kickoff meeting planned for 8/2 | Populated REQ template
|  | Communication, stakeholder alignments | PDL / AF |  | Completed | Detail scope to be communicated to stakeholders | Meeting minutes
|  | IRM Assesment to load data in C3 | PDL |  | Completed |  | IRM sign off e-mail
2 | Access
| Tool access to all stakeholders | List of users need access to C3 tool | AF |  | Completed |  | Knowledge | 2022-02-09
|  | Provide required access to C3 tool | PDL |  | Completed | Row no 14 is critical | Knowledge | 2022-02-25
|  | Provide acess to PDM TAO for local PI Server and SeeQ | AIDT |  | Completed |  |  | 2022-02-11
3 | Gather data
| Deliver good quality data, and good failure cases | Provided Tags list for agreed Critical Equipment | AF | AFO/APT/ARET | Completed |  | Populated REQ template | 2022-02-18
|  | Provide process book displays and P& ID's for all equipments | AF/AIDT | AFO/APT/ARET | Completed |  | Populated REQ template | 2022-02-18
|  | Provide UTL links for operating limits | AF/FO | AFO/APT/ARET | Completed |  | Populated REQ template | 2022-02-18
|  | provide all shutdown and failure events | AF/AGE | AFO/APT/ARET | Completed |  | Populated REQ template | 2022-02-18
|  | Examine all the information provided (tag list, P&ID's, Limits, etc..) | PREQ | AFO/APT/ARET | Completed | Row no 18,19,20,21 is critical | Populated REQ template | 2022-02-25
4 | Data Load
| Load required data in to C3 for modelling | Create AF Hierachy | PDE | AIDT/ADS | Completed |  | Document | 2022-03-04
|  | Load all tags / data in to C3 | PDE / PDS | AIDT/ADS | Completed |  | data | 2022-03-11
|  | Data Quality / availability Checks | PDE / PDS | AIDT/ADS | Completed |  | data | 2022-03-18
5 | Model Training and Review
|  | Working Sessions - Model Training and Model Review | PREQ / PDS / AF | AIDT/ADS | Completed |  |  | 2022-04-29
|  | Perform Model review and training for all equipments | PREQ / AF | AIDT/ADS | In -progress |  | Code | 2022-04-29
|  | Make models live | PREQ / AF | AIDT/ADS | In -progress |  | List of anomalies | 2022-05-06
6 | Review anomaly detection
| Sign-off from SME that model is identifying anomalies | Integrate C3 Alerts in to EBS and setup email alert system | PDL | AIDT/ADS | Completed |  | Document | 2022-05-11
|  | Training sessions for Assets focal and Survielance team | PDL | AIDT/ADS | Completed
|  | Provide access to all users | PDL | APTME | Completed |  | Document | 2022-05-18
|  | Evaluate detected analomalies from EBS | PREQ / AF | APTME | In -progress |  |  | May - Dec
|  | Perform root cause analysis | PREQ / AF | APTME | In -progress |  |  | May - Dec
7 | Training & product handover
| Training to handlover model training and review | Provide EBS training | PREQ | APTME / All | Completed |  |  | 2022-06-07
|  | Share all recordings and user guides | PDL | AF | Completed |  |  | 2022-06-10
|  | Retrian models if required | ADS / AIDT | PREQ | Completed |  |  | May - Dec
|  | Continue Surveilance, prepare and implement surveillance model for PDM | APTME | AINS | Completed |  |  | June - Dec