## Slide 1
Business Case/objectives:
The SSAGS project in the Tunu Node is a significant part of SPDC’s domestic gas supply plan which was commissioned to eliminate gas flaring and gather AG from all the four flowstations to supply the gathered AG and NAG gas from the Tunu Node facilities primarily to the Domgas via the East-Lagos Pipeline System (ELPS). The gas is routed through the EA riser platform A (RPA) and the Forcados Yokri Integrated Platform (FYIP) CPF with flexibility to supply to NLNG via the offshore gas gathering system (OGGS) pipeline network.
There is currently high flared gas volume in the Node even with the commissioned AG compressors, this has been attributed to some identified issues in the facilities across the Node. The high flared gas volume in the Node is a deviation from the Zero routine flare design intent of the SSAGS project and causing a non-compliance of the Non-flaring policy of the Federal Government of Nigeria.
Objective:
This opportunity seeks to eliminate gas flaring in the Tunu Node facilities by meeting the design intent of the SSAGS project in the Node, complying with the Non-flaring policy of the Federal Government of Nigeria and increasing revenue from additional gas to gas sales.
Project and Asset integrated facility review – July 2020
Joint PEFS review – July 2020
Phase 1 - flare reduction to 2mmscfd by October, 2020 (Eliminate process flare)
  Reduce purge and pilot gas across the Node.
  Check for possible passing spill over valves and relief valves in the flowstations.
  Resolve issues with Opukushi flash gas compressor.
  Check and validate the flare meters across the Node E.g Ogbotobo.
Phase 2 – Flare reduction to 1mmscfd by Dec 2020
  Replace the Benisede flare thermocouple.
  Resolve Backpressure issues at the commingling of the AG gas from the Main AG compressor and the gas from the NAG well.
  Carry out optimization of the volume of gas from the export used for volume compensation to operate above the high turn down rate for the Main AG compressor in Tunu.
Phase 3 – Flare reduction to <1mmscfd by Dec 2021
  Carry out modification works to route some NAG volume to main AG compressor to for operation above the high turn down rate of the compressor.
  Replace the flare ignition system of the flares in Tunu Node to achieve zero routine flaring
Input High-level Timeline:
L0-L1
L2: Impacts fully identified and FCF calculated
L3: When to get approval for implementation
L4: When to complete all major actions implementation
L5: Initiative End
All the AG compressor fully commissioned and operating as designed.
Reduce flaring to 2MMscfd (phase 1), & to 1mmsscfd in phase 2.
Increase gas to export for additional gas sale.
Availability of x budget for phase 2
All materials in country for phase 2
Available Shutdown window
Eliminate routine flare in the Node to comply with the Non-flaring policy of the Federal government of Nigeria.
Avoid cost of about USD$0.96Mln for the period of 6months for Flare penalty.
Generate additional revenue from additional gas to gas sales.
Achieve GHG abatement (data?) from x to y.
  Project Sponsor: Meshach Maichibi
  Implementation Lead: Busari Abiodun
  Project Team:
Segun Adomokhai, Alaka Olanrewaju, Itene Gaga, Adeleke Ngozi,, Iain Rollo, Victor Alozie, Anyanwu James
Potential Benefits & Measurement:
Project Milestones /Actions:
Critical Success Factors:
Project Team/Sponsor:
Project Charter: Reduce Tunu Node flare from 8MMSCFD to 2MMSCFD by Dec ‘20
Business Case/Objectives
High-Level Timeline: