## Slide 1
Team Digitalization 2021 - 2022 Project Timeline
Conduct survey to obtain baseline data
June 29th
Awareness Session
via SE family connect
July 13th
Create a MS Team
Space for SE Department
Sept 28th
Deploy Incident Management Dashboard
Aug 30th
Deploy Performance Management Tool
Oct 29th
Phase 2 Augmented
Reality Launch
Sept 30th
1
5
9
10
6
2
3
Execute a batch
of Power BI training
Launch Connected Workers
in assets (Bonga + Gbaran/Tunu)Review Process
Dec 10th
Dec 1st
Sub- Team | Legend
Collaboration | 
Augmented Reality | 
Digitalized Checklist | 
Power BI | 
8
Freeze at L3
June 30th
4
Pilot & launch
Augmented reality.
Sept 1st
11
Launch Connected Workers (L&H, DROPs, LoB
7
Pilot Connected Workers in Marine 4DX in COG
Oct 1st
1st Feb 2022

## Slide 2
Project Title: SE Simplification and Efficiency – Cost saving through Digitalization (2021 YTD Report)
Key Workstream Deliverables
2021 Planned
Leverage on Digital Transformation to save $500k, improve SE process & create efficiency
Develop workstream charter, activity plan, source actual SE budget 2019/2020/2021
Engage SE LTs, Internal & External Stakeholders
Pilot and deploy digital tools and train SE professional and users
Deploy sensing/baseline surveys, review and improve digital transformation programme
Lookahead including Post Reshape Activities
Initial scope expanded from 1 to > 22 initiatives/opportunities for Digital Transformation
4 sub-workstreams project charters achieved with nominated SE LT sponsors
Trained in the use of Fit4 and defined initiatives in Fit4
Wide engagement achieved with (SE LT, DE, LT sponsors, SCiN Digital Team, Shell Global IT)
Team achieved 100% agreed activity plan (Freeze at Fit4 L3 awaiting w/c 15th June)
Cost obtained for 4 Augmented Reality (AR) devices ~$ 25K + 10 Connected Workers ipads ($59K)
Team completed Connected Workers electronic Marine Safety 4DX checklist (awaiting Pilot – Sept 2021), achieved 50% development of PowerBi Incident dashboard backend and agreed with SE capability development to provide a batch of PowerBi training.
2021 YTD Achieved
Team Collaboration
Roll Out 1 - Awareness session via SE Family connect – July 13th 2021
Sensing & effectiveness feedback survey – August 23rd -30th 2021
Rout Out 2 - Create MS Teams space for SE Organisation – Sept 28th 2021
Augmented Reality
Pilot & launch Augmented Reality (AR) Tools. Phase 1 (Sept’21). Phase 2 (Dec ‘21). Others Feb 2022.
Run Maintain Mar 2022
Digitalized Checklist (Connected Workers
Pilot Marine Safety 4DX Digital Tool (Sept 2021)
Launch Connected Workers in assets (Bonga + Gbaran/Tunu)
Review Process (Dec 21)
Launch Connected Workers (Other Risk Areas i.e L&H, DROPs etc) in other LoB (Feb 22)
Power BI
Deploy Incident Management Dashboard (August 2021)
Execute a batch of Power BI training (August 2021)
Deploy Performance Management Tool. (October 2021)
Team: Bayo Awosanya, Ilamina Ebinum, Chikezie Odinaka, Dauda Shittu