## Cadence
| Opportunity/Objective: | SE Process Simplification through Digitalisation | MW Summary:
Project Sponsor
Project Champion
Project Manager
| Project Team Members | Bayo Awosanya,Ilamina Ebinum, Daud Shittu, Chikezie Odinaka
Cadence Meeting | Achieved Last Week | Promised for Next Week | Due Date | Help Needed | Resolutions | Unresolved Actions
2021-03-17 | Achieved engagement with Digitalisation Lead in Hague | Engagement with Digital & Technology Lead in Nigeria | 2021-03-22 | Nil
2021-03-17 | Did not achieve engagement with Digital & Technology Lead in Nigeria | Resend survey to all SE to collect pain points | 2021-03-23 | Esther Okereke to help resend survey to all SE
2021-03-17 | Held cascade session at SE Family Connect on 16th March | Update/record progress as L2 on Fit4 | 2021-03-23 | Help from Isaac Bejide
2021-03-17 | Updated L2 on Fit4
2021-04-08 | Digitalisation opportunities captured and summed into 4 tools /product categories 1) Augmented Reality, 2) Digitalized Checklist System, 3) Action Tracking/System, 4) Team Collaboration. Product delivery task assigned to subteam members | Workstream to agree achievable tools/products in the funnel and timeline and set up challenge session with DE (Amadi Amadi) | 2021-04-16 | Challenge session with DE (Amadi Amadi) and receive steer
2021-04-08 | Updated L3 on Fit4 | Update Fit4 (Approve L3) in Fit4