## ORIGINAL-TOTAL PLAN - CWI SCOPE
TOTAL PLAN/ CWI SCOPE
MONTH | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
TOTAL PLAN | 205 | 159 | 85 | 18 | 60 | 17
TOTAL ACTUAL | JUNE: 50; JULY: 30
CWI PLAN | 125 | 89 | 32 | 10 | 40 | 13
CWI ACTUAL | JUNE: 15; JULY: 25
losed

## UPDATED RED WELL PLAN - 17 JUL
CURRENT RED - 17TH JULY 2018
MONTH | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER
CWI PLAN | 65 | 65 | 65 | 65 | 65
CWI ACTUAL | 0 | 0 | 0 | 0 | 0
TOTAL PLAN | 112 | 113 | 112 | 113 | 113
TOTAL ACTUAL | 0 | 0 | 0 | 0 | 0
TOTAL RED WELL COUNT FOR CWI ONLY = 325

## EMERGING RED WELLS
EMERGING - CWI ACTION PLAN
7
MONTHS | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER
WEEKS | 2018-07-01 | 2018-07-08 | 2018-07-15 | 2018-07-22 | 2018-07-29 | 2018-08-05 | 2018-08-12 | 2018-08-19 | 2018-08-26 | 2018-09-02 | 2018-09-09 | 2018-09-16 | 2018-09-23 | 2018-09-30 | 2018-10-07 | 2018-10-14 | 2018-10-21 | 2018-10-28 | 2018-11-04 | 2018-11-11 | 2018-11-18 | 2018-11-25
CWI WEEKLYPLAN | 11 | 11 | 11 | 11 | 11 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 4 | 40 | 40 | 40 | 40 | 35 | 35 | 35 | 35
CWI MONTHLY PLAN | 2018-07-01: 55; 2018-08-05: 28; 2018-09-02: 20; 2018-10-07: 160; 2018-11-04: 175
CWI WEEKLY ACTUAL | 2018-07-01: 3; 2018-07-08: 5; 2018-07-15: 5
TOTAL WEEKLY PLAN | 12 | 12 | 12 | 12 | 11 | 24 | 24 | 24 | 24 | 8 | 8 | 7 | 7 | 7 | 47 | 47 | 47 | 48 | 57 | 57 | 57 | 57
TOTAL WEEKLY ACTUAL | 2018-07-01: 3; 2018-07-08: 5; 2018-07-15: 5
TOTAL MONTHLY PLAN | 2018-07-01: 59; 2018-08-05: 96; 2018-09-02: 37; 2018-10-07: 189; 2018-11-04: 228
EMERGING FOR JUNE WAS ADDED TO JULY TOTAL
EMERGING FOR DECEMBER WAS ADDED TO NOVEMBER TOTAL
=55+28+20+160+175