## Slide 1: Portfolio Capex East Asset
Gbaran GTG2 Core Engine Exchange (I-0056548)
RAM: High
Asset/People
Cost: $3.12M(in 2022)
MTO ranking:
10,075,000
HBA Risk:
High
Activity Summary: 1) Gbaran GTG2 Core Engine Exchange =2.95M
2) FSR Fees = 170k
Total $3.12M
Key Risk
Gbaran GTG2 (power generation unit) Core engine have accumulated 16,114 hours and will be due for exchange by QI 2023 based on OEM recommended run hours of 24,000hrs. Non implementation of this exchange/overhaul will lead to potential catastrophic failure of the unit and deferment of Gbaran daily production of 1.250mmscf and 50kbbls/d, hence the need to include this budget on OP22 budget.
Priority Ranking:
P1
Contract status:
4610053511
Execution party:
MRTA
Logistics Support:
nil
NAPIMS approval:
NAPIMS not yet engaged
Execution status:
Awaiting approval for procurement of spares.
Support required:
Approve budget for Engine exchange
Materials status:
Spares yet to be ordered

## Slide 2: Portfolio Capex East Asset
GBARAN SGT400 TYCO R4 F&G PROTECTION SYSTEM ANNUAL HEALTH CHECK
(I-0056548)
RAM: High
Asset/People
Cost: $250K (in 2022)
MTO ranking:
10,075,000
HBA Risk:
High
Activity Summary:
GBARAN SGT400 TYCO R4 F&G PROTECTION SYSTEM ANNUAL HEALTH CHECK = $250K
Key Risk: SGT400 Tyco F&G R4 protection is critical to availability of the five SGT400 units in Gbaran and sustenance of Gbaran daily production of 1,250MMscf and 50kbbls/d.
Note: This improves the reliability and availability of the five SGT400 units in Gbaran.
Priority Ranking:
P1
Contract status:
Plan to put Contract in place.
Execution party:
MRTA
Logistics Support:
nil
NAPIMS approval:
NAPIMS not yet engaged
Execution status:
Awaiting approval for procurement of spares.
Support required:
Approve budget for unit health checks.
.
Materials status:

## Slide 3: Portfolio Capex East Asset
Gbaran AGC2 Gearbox inspection (I-0056582)
RAM: High
Asset/People
Cost: $300K (in 2022)
MTO ranking:
5,010,000
HBA Risk:
High
Activity Summary:
Gbaran AGC2 Gearbox inspection = $300k
Total =$300k
Key Risk:
Gbaran AGC2 Voith BHS gearbox was inspected last in 2016 as against the recommended 3yearly inspections hence the need provide this Fund on notional budget to enable procurement of the spares and carryout timely intervention to prevent potential catastrophic failure of the Gearbox and compressor train down time for a long haul.
Priority Ranking:
P1
Contract status:
Plan to put contract in place.
Execution party:
MRTA
Logistics Support:
nil
NAPIMS approval:
NAPIMS not yet engaged
Execution status:
Awaiting approval to mobilize
Support required:
Secure notional budget for procurement of spares
Materials status:

## Slide 4: Portfolio Capex East Asset
GBARAN AGC1 AND 2 CCC ANNUAL HEALTH CHECK (I-0056582)
RAM: High
Asset/People
Cost: $400K (in 2022)
MTO ranking:
5,010,000
HBA Risk:
High
Activity Summary:
GBARAN AGC1 AND 2 CCC ANNUAL HEALTH CHECK =$400k
Total = F$400K
Key Risk:
AG Compressor CCC annual inspections are critical to availability of the two AGC1&2 units in Gbaran and sustenance of Gbaran daily production of 1,250bscf and 50kbbls/d.
Priority Ranking:
P1
Contract status:
Plan to put a LTSA in place.
Execution party:
MRTA
Logistics Support:
nil
NAPIMS approval:
NAPIMS not yet engaged
Execution status:
Awaiting approval to mobilize
Support required:
Secure notional budget for procurement of spares
Materials status: