## Slide 1: Power Opukushi Military Camp from the AG Booster Station
Critical Success Factors
Opportunity Statement
Business Case
Governance & Accountability
Plan /Schedule
Goal Statement (Indicators)
IN Scope OUT
Team (Resources)
The Opukushi military camp is currently powered by diesel generators located in the camp about 400m from the AG booster station. Considering the excess power generation capacity at the booster station, the diesel generators at the camp can be eliminated by installing a power cable linking the military camp to the AG booster station power system.
An opportunity exists to eliminate the cost of having diesel generators at the Opukushi military camp by linking the camp to the booster station power system. Expected benefits from this initiative are:
Elimination of power generation costs which amount to N11.4 million at the military camp
Reduced GHG footprint
Reduced noise pollution at the military camp.
Q4 2021
Cost of power generation at military camp 0N
  Gas Engine Generators
  Power cable linking the military camp to the AG booster station
  Power distribution equipment
Start Finish
Detailed design, specification and approval 01/21 03/21
Cost estimation 01/21 03/21
Contracting and procurement 03/21 06/21
Implementation 06/21 01/22
  Project Champion: Adeleke Ngozi
  Project Team: Omoifo Onotie, Cost engineer
  BFM: Audu-Usman Isaac
Budget
Adequate cost estimation
Use of competent contractor
Sponsors: Maichibi Mesh
Steering Team: Busari Abiodun; Uduanochie Adanma;
Reporting: Monthly reporting to steering team on project plan, spend, saving estimates and resource consumption.
Cost Object(s) Impacted
O.NG.PCW.OKF.FAC.71300