## <READ ME FIRST>
AMS Asset Change Implementation Plan template
Template Guidance
AMS Asset Change Implementation Plan Template | The Asset Change Implementation plan Template provides a structure to be used by Assets to identify and aggregate the change interventions required at the Asset to successfully adopt the AMS change. It consists of the following tabs: 1. Asset Implementation Plan on a Page - Template for the Asset to use to provide a a high-level overview of the implementation timelines for activities in the Plan, Prepare, Implement and Monitor phase of the AMS Implementation Approach. 2. Asset Roll-out Plan - Provides a structure to aggregate the change interventions identified during the Change Impact Assessments.
Instructions | Please use this template together with the outcome of the Asset Change Impact Assessment to create the Change Implementation Plan for your asset.
To understand the end-to-end approach for developing the Asset Change Implementation plan, using the Health Check template and Change Impact Assessment template, please refer to PowerPoint 'Guide to AMS Change Impact Assessments' on the AMS deployment toolkit.

## Asset Impl. Plan on a Page
|  |  | Weeks: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90
1 | PLAN
1.1 | Setup | <person> | 10 days
1.2 | AMS Kick Off at Asset | <person> | 5 days
1.3 | Establish Local Governance | <person> | 5 days
1.4 | Appoint and Onboard Asset Change Team | <person> | 10 days
1.5 | Conduct Asset Change Impact Assessment | <person> | 10 days
1.6 | Create Asset Change Implementation Plan | <person> | 15 days
1.7 | Plan Initial Asset wide engagement | <person> | 10 days
1.8 | Set Up Measuring Implementation Progress | <person> | 5 days
1.9 | Complete Business Readiness Checklist | <person> | 5 days
2 | PREPARE
2.1 | Conduct Asset wide engagement | <person> | 30 days
2.2 | Training Asset Change Team | <person> | 15 days
2.3 | Localise / Preprare Key Communication from toolkit | <person> | 10 days
2.4 | Prepare KPI Reporting Mechanism | <person> | 30 days
2.5 | Complete Business Readiness Checklist | <person> | 5 days
3 | IMPLEMENT
3.1 | Execute Communication plan | <person> | Ongoing
3.2 | Deliver relevant training to impacted audiences | <person> | 60 days
3.3 | Rollout AMS Processes Batch 1 | <person> | See Roll-out Plan
3.3 | Rollout AMS Processes Batch 2 | <person> | See Roll-out Plan
3.3 | Rollout AMS Processes Batch 3 | <person> | See Roll-out Plan
3.4 | Update Local Management Systems | <person> | 75 weeks
3.5 | Execute KPI reporting mechanisms | <person> | Ongoing
3.6 | Evaluate complete eco-system (interfaces, effectiveness) - Only after final batch roll out | <person> | 40 days
3.7 | Complete Business Readiness Checklist | <person> | 1 day
4 | MONITOR
4.1 | Conduct Process Health Check | <person> | 20 days
4.2 | Implementation Closeout | <person> | 15 days

## SNEPCO Roll-out Plan
|  |  |  | 2018-09-01 |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  |  | 2021-01-01 |  |  |  |  | 2021-02-01
| Person | Weeks | Weeks: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127
ASSET LEADERSHIP CHANGE INITIATIVES |  |  | 9 weeks
DIRECTION SETTING
SNEPCO-LT-001: Develop transformation staircase. | Bayo Ojulari | No due date | 10 days
SNEPCO-LT-002: Engage staff via Asset Wide Engagements and Management Facility Engagements on the Process Changes and Identified benefits for the Asset and Business in General | Bayo Ojulari | No due date | 10days
SNEPCO-LT-003: Review Stakeholder engagement plans to reflect the spirit of Simplicity, Intent, Risk and Outcome focus | Bayo Ojulari | 15 weeks | 15days
SNEPCO-LT-004: Introduce business sensing or proactive engagements and monitoring in stakeholder engagements to boost reputation and external partnerships | Bayo Ojulari | 66 weeks
SNEPCO-LT-005: Continous engagement with steering committee for support | Bayo Ojulari | 66 weeks
GOVERNANCE / DECISION MAKING
SNEPCO-LT-006: Seek Derogation from EVP- LOB for High Effort/Cost v. High Complexity mandatory gap closure items | Bayo Ojulari | 15 weeks
SNEPCO-LT-007: Set up steering committee, deploy and implement governance strategy | Bayo Ojulari | 2 weeks | 10days
SNEPCO-LT-008: Drive Asset Performance Management and Operational Excellence via AMS KPI reporting at LT meetings | Bayo Ojulari | 123 weeks | 30 days
SNEPCO-LT-009: Accelerate AMS Health Checks for all mandatory processes to have full spectrum of the gaps that exist to 'Comply By'. 'Err on the side of caution or 'prudent overreaction' and mitigate risks to ALARP prioritized around Make-it-Safe, Make-it-Work and Make-it Grow. | Bayo Ojulari | 49 weeks
COMPLIANCE TO AMS
SNEPCO-LT-010: Continually engage staff via Asset Wide Engagements and Management Facility Engagementss on AMS ways of working. | Bayo Ojulari | 15 weeks
SNEPCO-LT-011: Hold regular accountability discussions against AMS practices on site | Bayo Ojulari | 15 weeks
SNEPCO-LT-012: Introduce AMS requirements in GPAs of all process practitioners and leaders throughout the organisation. | Bayo Ojulari | 23 weeks | 15 days
SNEPCO-LT-013: Hold regular performance review sessions around AMS compliance and change management | Bayo Ojulari | 23 weeks | 30 days
BEHAVIORS
SNEPCO-LT-014: Complete Intent based leadership training for JG5 and above | Bayo Ojulari | 123 weeks | 30 days
SNEPCO-LT-015: Develop LSW for all key leaders and at all facilities to JG3 | Bayo Ojulari | 123 weeks | 30 days
SNEPCO-LT-016: Update Visualization of Processes that Leaders use daily/weekly at facilities | Bayo Ojulari | 123 weeks | 30 days
SNEPCO-LT-017: Develop 'Go See' questions for leaders to use and test at locations. | Bayo Ojulari | 123 weeks | 30 days
SNEPCO-LT-018: Develop programme for Leaders to attend Go See's all year across all processes | Bayo Ojulari | 123 weeks | 30 days
SNEPCO-LT-019: Use Process Council engagements to share successes and replicate ideas | Bayo Ojulari | 123 weeks | 30 days
SNEPCO-LT-020: Introduce more Leader of Community type programmes for all staff at supervisory positions. | Bayo Ojulari | 123 weeks | 30 days
KPIs
SNEPCO-LT-021: Engage SNEPCO (Asset) LT on new KPI definitions and seek understanding | Bayo Ojulari | 15 weeks
SNEPCO-LT-022: Engage SNEPCO (Asset) LT on non-manadatory KPI definitions and seek understanding and adoption | Bayo Ojulari | 123 weeks | 30 days
CAPABILITY DEVELOPMENT
SNEPCO-LT-023: Ensure all staff handling safety or business critical roles in SNEPCO take the e-learning course on Work Process Management | Bayo Ojulari | 123 weeks | 30 days
SNEPCO-LT-024: Ensure all staff handling safety or business critical roles in SNEPCO take the e-learning course on Introduction to AMS | Bayo Ojulari | 123 weeks | 30 days
CA SPECIFIC CHANGE IMPLEMENTATION PLAN
OVERARCHING CHANGES |  |  | 9 weeks
DIRECTION SETTING
SNEPCO-OVE-001: Develop engagement packs on AMS in general and and share with the assets. In particular highlight that CA process covers activities with the intent to assure that the AMS and HSSE & SP requirements and controls are implemented and effective (CA, IAPS, ) | Elohor Aiboni | 11 weeks
SNEPCO-OVE-002: Review the AAP (ensure risk based and not frequency) with a view to optimize LOD 1,2&3 plan and minimizing duplication of efforts, also ensure alignment with asset risk register | Elohor Aiboni | 15 weeks
GOVERNANCE / DECISION MAKING
SNEPCO-OVE-003: Process Practioners to complete intent based training (CA,IAPS, ) | Elohor Aiboni | 13 weeks
SNEPCO-OVE-004: Line Managers in the business to support the new Process and develop assurance plans aligned with business risks | Elohor Aiboni | 13 weeks
SNEPCO-OVE-005: Review and update where necessary non-compliant deferral controls and procedures in the Local Management System | Elohor Aiboni | 15 weeks
KPIs
SNEPCO-OVE-006: SPO, Asset/Functional Managers to regularly communicate intent of applicable work process KPI's. | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-007: Develop engagement pack to share the applicable work process KPI's and clarify how they support the business delivery and what can influence them and how CI supports constant improvement to attain or beat the KPI. | Elohor Aiboni | 15 weeks | 5 days
CAPABILITY DEVELOPMENT
SNEPCO-OVE-008: SPO, Asset/Functional Managers to utilize appropriate existing forums (or create new ones) to regularly highlight key changes and impact on day to day work process execution | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-009: With reference to the recommended suite of applicable trainings/courses from the RP (see list below), check for those that are available locally and review adequacy. Make appriorate arrangements for update of existing local trainings as well as setting up of those courses/trainings not presently available (or equivalent) ---------------------------------------------------------------------------------------- (1) Auditing HSSE & SP Control Framework (5-day), or equivalent (BSI Lead Auditor, Lloyds, DNV, Veritas). (2) MS&E auditor training (2-day) (3) Shell Open University - Auditing HSSE&SP Control Framework Knowledge training course (CBL) (4) ISO-9000/14000 /19011 training given to Asset staff for the maintenance of their ISO certification (5) Asset-specific Internal Audit Training (6) Asset specific annual refresher training or communication for auditors (7) GPO or SPFP/PLA Coaching/Mentoring (8) Participate as observer on audits before becoming Auditor or Lead Auditor | Elohor Aiboni | 49 weeks | 5 days
IT SYSTEMS / TOOLS
SNEPCO-OVE-010: Adopt the global LOD 1 tracking tool for tracking LOD 1 findings | Elohor Aiboni | 40 weeks | 5 days
SNEPCO-OVE-011: Provide process practitioners access to AMS tool kit and other AMS associated SharePoint sites | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-012: Facilitate access to local and Global AMS connect meetings | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-013: Provide more trainings on use of Radar system | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-014: Ensure appropriate help-desk or 'hand-holding'resources are available to support process practitioners to leverage on IT facilities | Elohor Aiboni | 53 weeks | 5 days
PROCESS DRIVEN CHANGES
CA-ST-001: Include AMS LOD 1 process health checks into the annual assurance plan | Elohor Aiboni | 15 weeks | 5 days
CA-ST-002: Train and maintain a pool of competent auditors including how to rate assurance findings and develop a coaching plan for refreshers. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-003: SPO to assure that only competent lead auditors carrout LOD activities | Elohor Aiboni | 15 weeks | 5 days
CA-ST-004: Drive full implemetation of the annual assurance plan and raise an awaresnes on the use of non-conformance form when not practicable to complete LOD activities. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-005: Adopt the global LOD 1 tracking tool for tracking LOD 1 findings. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-006: Raise awareness on the requirement to manage changes to the assurance plan with the MOC process and complete MOCs for changes to the assurance plan. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-007: Agree a frequency and sustain the periodic review of corrective actions from LOD 1,2&3) findings and test their effectiveness in addressing the root cause identified. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-008: Develop and maintain a tracking system for LOD 1 Insights/low findings. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-009: Make AAP review an agenda into the QBPR for review of its business objective and incorporate learnings into the CA process improvement Plan | Elohor Aiboni | 15 weeks | 5 days
CA-ST-010: Review the AAP (risk based and not frequency) with a view to optimize LOD 1,2&3 plan and minimizing duplication of efforts. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-011: Track weekly, the status of LOD 1 plan and effectiveness of closure | Elohor Aiboni | 15 weeks | 5 days
IAPS SPECIFIC CHANGE IMPLEMENTATION PLAN
OVERARCHING CHANGES |  |  | 9 weeks
COMPLIANCE TO AMS
SNEPCO-OVE-015: Identify documentation that need localization and carry out reviews | Ibiyemi Asaolu | No due date | 15days
CAPABILITY DEVELOPMENT
SNEPCO-OVE-016: Facilitate CI e-learning and Training course locally | Ibiyemi Asaolu | 15 weeks | 5 days
PROCESS DRIVEN CHANGES
IAPS-ST-001: Establish IAPS Council and institute monthly meetings | Ibiyemi Asaolu | 27 weeks
IAPS-ST-002: SPO to ensure that activities are integrated based on planning/ resource constraints at MT level (Included in Updated SOP). | Ibiyemi Asaolu | 27 weeks
IAPS-ST-003: SPO to enforce change control process for activities in frozen window of MT and IS. Additionally SPO to increase awareness of frozen window duration and requirement for change control using CRET. | Ibiyemi Asaolu | 27 weeks
IAPS-ST-004: SPO to fastrack deployment/usage of IAPS portal as toolset activity monitoring in SNEPCo | Ibiyemi Asaolu | 27 weeks
IAPS-ST-005: SPO to ensure functional improvement plans are developed and visible as part of learnings from activity execution monitoring. | Ibiyemi Asaolu | 27 weeks
MTO SPECIFIC CHANGE IMPLEMENTATION PLAN
OVERARCHING CHANGES |  |  | 9 weeks
DIRECTION SETTING
SNEPCO-OVE-017: Carry out pre-engagment of SNEPCo LT on MTO | Elohor Aiboni | 7 weeks | 5 days
SNEPCO-OVE-018: Develop an MTO training pack and draw up a training plan to reach out to all relevant stakeholders | Elohor Aiboni | 11 weeks | 5 days
SNEPCO-OVE-019: MTO SPO and SPFP to attend MTO training webcast to learn from others in RDS | Elohor Aiboni | 7 weeks | 5 days
SNEPCO-OVE-020: Provide training to all stakeholders on MTO process and tool | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-021: Include actions to address MTO threats and opportunities in GPAs for threat owners and action parties | Elohor Aiboni | 23 weeks | 5 days
SNEPCO-OVE-022: Display MTO performance and KPIs on posters and screens across Bonga, BOI and Freeman House | Elohor Aiboni | 23 weeks | 5 days
SNEPCO-OVE-023: Reliability engineers to engage threat owners for low lying threats to ensure they are progressed. | Elohor Aiboni | 15 weeks | 5 days
GOVERNANCE / DECISION MAKING
SNEPCO-OVE-024: Develop an MTO onboarding pack | Elohor Aiboni | 15 weeks | 5 days
COMPLIANCE TO AMS
SNEPCO-OVE-025: Schedule periodic healtch checks against the process 'Shall' statements | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-026: MTO Steering Committee to review MTO process performance against KPI | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-027: Create a single point in Sharepoint to save and share MTO process guides and TORs | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-028: Schedule periodic review of MTO meeting TOR's and process governance document for SNEPCo | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-029: Create awareness on the need to stop POR process to move actions to Asset Engineering support only through MTO | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-030: Drive actions requiring Asset Engineering support through MTO only | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-031: Include all long term threats in MTO database and manage them only through MTO process | Elohor Aiboni | 15 weeks | 5 days
IT SYSTEMS / TOOLS
SNEPCO-OVE-032: Complete deployment of MTO and IAPS work processes SNEPCo | Elohor Aiboni | 40 weeks | 5 days
SNEPCO-OVE-033: Complete business cases related to the specific tools and complete actual deployments. | Elohor Aiboni | 92 weeks | 5 days
SNEPCO-OVE-034: Conduct Super-Users and 'Train-the-Trainer' sessions in line with deployments of tools | Elohor Aiboni | 92 weeks | 5 days
PROCESS DRIVEN CHANGES
MTO-ST-001 : Create a document that covers short term threats and Long term. | Elohor Aiboni | 27 weeks | 5 days
MTO-ST-002 : Constitute an MTO steering committee as per the mandatory requirements and recommended practice. | Elohor Aiboni | 15 weeks | 5 days
MTO-ST-003: Rollout causal learning training for all practitioners | Elohor Aiboni | 15 weeks | 5 days
MTO-ST-004: Engage WRFM leadership to deploy MTO process for the management of WRFM opportunities. | Elohor Aiboni | 15 weeks | 5 days
MTO-ST-005: Update monthly MTO meeting agenda to include effectivness review of threats closed YTD. | Elohor Aiboni | 27 weeks | 5 days
MTO-ST-006 : Reliability Engineers to make explicit link between MTO threats/opportunity closure results with unscheduled deferment. | Elohor Aiboni | 27 weeks | 5 days
MTO-ST-007 : Operations manager to validate MTO resuts during monthly MTO meetings. | Elohor Aiboni | 15 weeks | 5 days
MTO-ST-008 : Develop an overarching process governance and workflow to drive/manage all AMS processes interfacing with MTO. | Elohor Aiboni | 27 weeks
PERFORM WRFM SPECIFIC CHANGE IMPLEMENTATION PLAN
OVERARCHING CHANGES |  |  | 9 weeks
DIRECTION SETTING
SNEPCO-OVE-035: Implement buddy system with experienced staff taking (partial) responsibility for development of new staff | Ibiyemi Asaolu | 49 weeks | 5 days
IT SYSTEMS / TOOLS
SNEPCO-OVE-036: Deploy exception based surveillance | Ibiyemi Asaolu | No due date | 10days
PROCESS DRIVEN CHANGES
WRFM-ST-001: Develop an SOP for WRFM activities to feed into the MTO process | Ibiyemi Asaolu | 27 weeks
WRFM-ST-002: SOP to be developed to review progress on work execution with respect to scope requirements, costs versus budget, actual versus planned duration and actual versus planned yields. | Ibiyemi Asaolu | 11 weeks | 5 days
WRFM-ST-003: Explore and implement a work management system (e.g. SAP) that can make progress of each activity visible throughout the life of the field One that is used optimally and supports continuous improvement to Identify & address waste, drive down cost & timing through all parts funnel. (Groningen does use SAP to monitor progress of all activities) | Ibiyemi Asaolu | 27 weeks
WRFM-ST-004: Explore and implement a work management system (e.g. SAP) that can make progress of each activity visible throughout the life of the field One that is used optimally and supports continuous improvement to Identify & address waste, drive down cost & timing through all parts funnel. | Ibiyemi Asaolu | 27 weeks
WRFM-ST-005: The Asset to develop and implement an SOP/ system to review the cash flow effectiveness of all WRFM activities completed in the previous year. | Ibiyemi Asaolu | 27 weeks
WRFM-ST-006: Include trigger level for underperformance in the AAR TOR | Ibiyemi Asaolu | 27 weeks
ESP SPECIFIC CHANGE IMPLEMENTATION PLAN
OVERARCHING CHANGES |  |  | 9 weeks
DIRECTION SETTING
SNEPCO-OVE-037: Update FFF Communication Plan to include AMS | Osas Iduoriyekemwem | 11 weeks | 10days
SNEPCO-OVE-038: Deploy F2F knowledge sessions for ESP and develop coaching capabilities across process practitioner group | Osas Iduoriyekemwem | 11 weeks | 10days
GOVERNANCE / DECISION MAKING
SNEPCO-OVE-039: Identify all SHALL requirements in ESP that require derogation, and support for Bonga Asset Operations Manager to secure EVP DW LoB approval | Osas Iduoriyekemwem | 7 weeks | 10days
COMPLIANCE TO AMS
SNEPCO-OVE-040: Setup a team and review and align existing documentation to meet ESP requirements | Osas Iduoriyekemwem | 40 weeks | 10days
PROCESS DRIVEN CHANGES
ESP-ST-001: Complete close out of actions from review and update of VT based on ISU fast tool. | Osas Iduoriyekemwem | 15 weeks
ESP-ST-002: Implement a refresher training to the TCI team and other alarms management practitioneers on the need for MoC for master data changes | Osas Iduoriyekemwem | 11 weeks
ESP-ST- 003: Align DCS and VT with respect to priorities and limits | Osas Iduoriyekemwem | 15 weeks
ESP-ST-004: Deploy the ISU FAST Tool on Bonga for effective managment of alarms | Osas Iduoriyekemwem | 19 weeks
ESP-ST-005: Implement a formal bad actor review meeting with actionable items. Document minutes of meeting. | Osas Iduoriyekemwem | 40 weeks
ESP-ST-006: Implement a proactive monitoring plan for the Bonga console operators. | Osas Iduoriyekemwem | 11 weeks
ESP-ST-007: Appoint a PTM Plan Owner within the asset and train and coach to develop competence | Osas Iduoriyekemwem | 15 weeks
MEC SPECIFIC CHANGE IMPLEMENTATION PLAN
OVERARCHING CHANGES |  |  | 9 weeks
COMPLIANCE TO AMS
SNEPCO-OVE-041: Develop a compendium of current documents that support the execution of the MEC work processes | Jillis Van Duuren | 7 weeks | 10 days
PROCESS DRIVEN CHANGES
MEC-ST-001 : Complete PAV and Update CMMS (SAP) with complete equipment information (No BOMs included). | Jillis Van Duuren | 2 weeks | 5 days
MEC-ST-002 : Define boundaries and assign owners for all equipment | Jillis Van Duuren | 27 weeks
MEC-ST-003 : SPO to develop clear Maintenance Efficiency Index (MEI) and communicate to Engineering and documented in the Strategic Asset management plan | Jillis Van Duuren | 2 weeks
MEC-ST-004 : SPO to establish benchmarking for maintenance care competitive costs | Jillis Van Duuren | 66 weeks
MEC-ST-005 : Explore the use of CUI Consequence Assessment Model (CCAM) for Corrosion Under Insulation assessments | Jillis Van Duuren | 66 weeks
MEC-ST-006 : Use RCM methodology for Risk Based assessment of all other failure modes including SIF components | Jillis Van Duuren | 40 weeks
MEC-ST-007 : Include cost for all tasks generated | Jillis Van Duuren | 118 weeks | 5 days
MEC-ST-008 : The Asset Engineering Manager to use the Maintenance Efficiency Index (MEI) threshold to ensure the selection of the remaining scope grouped as Turnarounds, Non-Turnaround Maintenance, Ensure Safe Production and Inspector tasks. | Jillis Van Duuren | 66 weeks
MEC-ST-009 : Report all safe and dangerous failures to the relevant process focal points (SIF, RCM, RBI) and investigate the cause. | Jillis Van Duuren | 15 weeks
MEC-ST-010 : Develop a process for carrying out cumulative risk management for the Asset. | Jillis Van Duuren | 27 weeks | 5 days
MEC-ST-011 : Adopt the key work process interfaces as specified in Continuous Improvement recommended practices (section 3) | Jillis Van Duuren | 49 weeks | 5 days

## CA Roll-out Plan
|  |  |  | 2018-09-01 |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  |  | 2021-01-01 |  |  |  |  | 2021-02-01
| Person | Weeks | Weeks: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127
CA SPECIFIC CHANGE IMPLEMENTATION PLAN
OVERARCHING CHANGES |  |  | 9 weeks
DIRECTION SETTING
SNEPCO-OVE-001: Develop engagement packs on AMS in general and and share with the assets. In particular highlight that CA process covers activities with the intent to assure that the AMS and HSSE & SP requirements and controls are implemented and effective (CA, IAPS, ) | Elohor Aiboni | 11 weeks
SNEPCO-OVE-002: Review the AAP (ensure risk based and not frequency) with a view to optimize LOD 1,2&3 plan and minimizing duplication of efforts, also ensure alignment with asset risk register | Elohor Aiboni | 15 weeks
GOVERNANCE / DECISION MAKING
SNEPCO-OVE-003: Process Practioners to complete intent based training (CA,IAPS, ) | Elohor Aiboni | 13 weeks
SNEPCO-OVE-004: Line Managers in the business to support the new Process and develop assurance plans aligned with business risks | Elohor Aiboni | 13 weeks
SNEPCO-OVE-005: Review and update where necessary non-compliant deferral controls and procedures in the Local Management System | Elohor Aiboni | 15 weeks
KPIs
SNEPCO-OVE-006: SPO, Asset/Functional Managers to regularly communicate intent of applicable work process KPI's. | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-007: Develop engagement pack to share the applicable work process KPI's and clarify how they support the business delivery and what can influence them and how CI supports constant improvement to attain or beat the KPI. | Elohor Aiboni | 15 weeks | 5 days
CAPABILITY DEVELOPMENT
SNEPCO-OVE-008: SPO, Asset/Functional Managers to utilize appropriate existing forums (or create new ones) to regularly highlight key changes and impact on day to day work process execution | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-009: With reference to the recommended suite of applicable trainings/courses from the RP (see list below), check for those that are available locally and review adequacy. Make appriorate arrangements for update of existing local trainings as well as setting up of those courses/trainings not presently available (or equivalent) ---------------------------------------------------------------------------------------- (1) Auditing HSSE & SP Control Framework (5-day), or equivalent (BSI Lead Auditor, Lloyds, DNV, Veritas). (2) MS&E auditor training (2-day) (3) Shell Open University - Auditing HSSE&SP Control Framework Knowledge training course (CBL) (4) ISO-9000/14000 /19011 training given to Asset staff for the maintenance of their ISO certification (5) Asset-specific Internal Audit Training (6) Asset specific annual refresher training or communication for auditors (7) GPO or SPFP/PLA Coaching/Mentoring (8) Participate as observer on audits before becoming Auditor or Lead Auditor | Elohor Aiboni | 49 weeks | 5 days
IT SYSTEMS / TOOLS
SNEPCO-OVE-010: Adopt the global LOD 1 tracking tool for tracking LOD 1 findings | Elohor Aiboni | 40 weeks | 5 days
SNEPCO-OVE-011: Provide process practitioners access to AMS tool kit and other AMS associated SharePoint sites | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-012: Facilitate access to local and Global AMS connect meetings | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-013: Provide more trainings on use of Radar system | Elohor Aiboni | 15 weeks | 5 days
SNEPCO-OVE-014: Ensure appropriate help-desk or 'hand-holding'resources are available to support process practitioners to leverage on IT facilities | Elohor Aiboni | 53 weeks | 5 days
PROCESS DRIVEN CHANGES
CA-ST-001: Include AMS LOD 1 process health checks into the annual assurance plan | Elohor Aiboni | 15 weeks | 5 days
CA-ST-002: Train and maintain a pool of competent auditors including how to rate assurance findings and develop a coaching plan for refreshers. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-003: SPO to assure that only competent lead auditors carrout LOD activities | Elohor Aiboni | 15 weeks | 5 days
CA-ST-004: Drive full implemetation of the annual assurance plan and raise an awaresnes on the use of non-conformance form when not practicable to complete LOD activities. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-005: Adopt the global LOD 1 tracking tool for tracking LOD 1 findings. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-006: Raise awareness on the requirement to manage changes to the assurance plan with the MOC process and complete MOCs for changes to the assurance plan. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-007: Agree a frequency and sustain the periodic review of corrective actions from LOD 1,2&3) findings and test their effectiveness in addressing the root cause identified. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-008: Develop and maintain a tracking system for LOD 1 Insights/low findings. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-009: Make AAP review an agenda into the QBPR for review of its business objective and incorporate learnings into the CA process improvement Plan | Elohor Aiboni | 15 weeks | 5 days
CA-ST-010: Review the AAP (risk based and not frequency) with a view to optimize LOD 1,2&3 plan and minimizing duplication of efforts. | Elohor Aiboni | 15 weeks | 5 days
CA-ST-011: Track weekly, the status of LOD 1 plan and effectiveness of closure | Elohor Aiboni | 15 weeks | 5 days

## ESP Roll-out Plan
|  |  |  | 2018-09-01 |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  |  | 2021-01-01 |  |  |  |  | 2021-02-01
| Person | Weeks | Weeks: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127
ESP SPECIFIC CHANGE IMPLEMENTATION PLAN
OVERARCHING CHANGES |  |  | 9 weeks
DIRECTION SETTING
SNEPCO-OVE-037: Update FFF Communication Plan to include AMS | Osas Iduoriyekemwem | 11 weeks | 10days
SNEPCO-OVE-038: Deploy F2F knowledge sessions for ESP and develop coaching capabilities across process practitioner group | Osas Iduoriyekemwem | 11 weeks | 10days
GOVERNANCE / DECISION MAKING
SNEPCO-OVE-039: Identify all SHALL requirements in ESP that require derogation, and support for Bonga Asset Operations Manager to secure EVP DW LoB approval | Osas Iduoriyekemwem | 7 weeks | 10days
COMPLIANCE TO AMS
SNEPCO-OVE-040: Setup a team and review and align existing documentation to meet ESP requirements | Osas Iduoriyekemwem | 40 weeks | 10days
PROCESS DRIVEN CHANGES
ESP-ST-001: Complete close out of actions from review and update of VT based on ISU fast tool. | Osas Iduoriyekemwem | 15 weeks
ESP-ST-002: Implement a refresher training to the TCI team and other alarms management practitioneers on the need for MoC for master data changes | Osas Iduoriyekemwem | 11 weeks
ESP-ST- 003: Align DCS and VT with respect to priorities and limits | Osas Iduoriyekemwem | 15 weeks
ESP-ST-004: Deploy the ISU FAST Tool on Bonga for effective managment of alarms | Osas Iduoriyekemwem | 19 weeks
ESP-ST-005: Implement a formal bad actor review meeting with actionable items. Document minutes of meeting. | Osas Iduoriyekemwem | 40 weeks
ESP-ST-006: Implement a proactive monitoring plan for the Bonga console operators. | Osas Iduoriyekemwem | 11 weeks
ESP-ST-007: Appoint a PTM Plan Owner within the asset and train and coach to develop competence | Osas Iduoriyekemwem | 15 weeks