## FORC_Offshore (2)
TOP EVENT: POSSIBLE FIRE OUTBREAK / OIL SPILL
UWI | Traffic Light Status | AC | Name | WFM Type | Well Status | Reasons | People | Asset | Community | Environment | Overal Risk | Current Mitigations in Place | General Comments | Mitigation Actions | Action Party | Action Party | Expected Closure Date | Recommendation
400000001635 | R | 9 | FOCY135 | LP | Closed in | LS: SSSV, SS: LMV2, SSSV2, | C3 | C3 | C3 | C3 | Medium | 1. LS can not flow naturally and currently closed-in. All Xmas tree valves functional. 2. SS redundant valve tested and integral (SV / FWV). 3. Xmas tree cap integral and available. | SS: Well (PBU) currently flowing with 1 barrier. Stepwise approach is required to restore integrity as quickly as possible | SS 1. Carry-out special OPSWIT on SS 2. Grease failed valves with grease guns. 3. Carry out daily surveillance on well. 4. Carry out SLM on ScSSV & other failed valves for both LS & SS. | 1. 31/03/2020 2. 31/03/2020 3. Daily 4. 30/05/2020 | 1. Opns - Tunde Akinro 2. Opns - Tunde Akinro. 3. Opns - Tunde Akinro 4. CWI - Ricky / Pius | 1. 14th Feb 2020. 2. 14th Feb 2020. 3. Daily. 4. 30th Mar 2020 | 1. Leave LS closed-in. 2. leave SS Flowing.
400000001631 | R | 9 | FOCY047S1 | LP | Completed | LS: SV, SSSV | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage. 3. LS redundant valve tested and integral (MV / FWV ). 3. Xmas tree cap integral and available.. 4. SS integral (no issues) | Step wise approach is required to restore integrity as quickly as possible. | LS: 1. Grease failed valves with grease guns. 2. Carry-out special OPSWIT on LS 3. Carry out daily surveillance on well. 4. Carry out SLM on ScSSV & SV | 1. 30/03/2020 2. 30/03/2020. 3. Daily 4. 30/05/2020 | 1. Opns - Tunde Akinro 2. Opns - Tunde Akinro. 3. Opns - Tunde Akinro 4. CWI - Ricky / Pius |  | Leave FORC047L/S Flowing
400000001377 | R | 9 | FOCY122 | LP | Flowing | LS: SSV, SS: LMV2, SSSV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage. 2. LS can not flow naturally and currently closed-in. All Xmas tree valves functional. 3. SS redundant valve tested and integral (SV / FWV). 4. Xmas tree cap integral and available. | Step wise approach is required to restore integrity as quickly as possible. | SS: 1. Grease failed valves with grease guns 2. Carry out special OPSWIT on SS 3. Carry out daily surveillance on well. 4. Carry out SLM if valves fail. | 1. 30/03/2020 2. 30/03/2020. 3. Daily 4. 30/05/2020 | 1. Opns - Tunde Akinro 2. Opns - Tunde Akinro. 3. Opns - Tunde Akinro 4. CWI - Ricky / Pius |  | leave FORC122L/S Flowing
400000001362 | R | 9 | FOCY028 | LP | Completed | LS:SSSV SS: UMV2, FWVI2, SSSV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage. 2. LS MV, SV & WV integral (All Xmas tree valves functional). 3. SS redundant valve tested and integral (SV), WV did not fail current test (was not tested - but last WIT confirmed pass). 4. Xmas tree cap integral and available. | Well currently producing . It will be challenging to shut in the well in this condition and a well kill could be required. There is 1 barrier available. | SS: 1. Grease failed valves. 2. Carry out special OPSWIT on SS 3. Carry out daily surveillance on well. 4. Carry out SLM if valves still fails. | 1. 30/03/2020 2. 30/03/2020. 3. Daily 4. 30/05/2020 | 1. Opns - Tunde Akinro 2. Opns - Tunde Akinro. 3. Opns - Tunde Akinro 4. CWI - Ricky / Pius |  | Leave FORC028L/S Flowing

## AC09_Today
2348070232858
TOP EVENT: POSSIBLE FIRE OUTBREAK / OIL SPILL
UWI | Traffic Light Status | Cluster | AC | Well Name | WFM Type | Well Status | Reasons | People | Asset | Community | Environment | Overal Risk | Current Mitigations in Place | General Comments | Mitigation Actions | Action Timeline | Action Party | Expected Closure Date | Recommendation
400000001640 | R | Cluster 95 | 9 | FOCY102 | LP | Closed in | LS: FWVI SS: SSSV2, SSV2, SV2, UMV2, | C2 | C3 | C3 | C3 | Medium | 1. Wellhead caged. 2. SS: Not a flowing conduit - quit production. 3. LS valve tested and integral (MV, SV and SSSV functional). 3. Xmas tree cap integral and available. | SS: The measured CITHP is 48 bar. No functional barrier. LS: FWV is the only failure in LS. | SS: 1. Well should remain closed-in 2. Prod Ops to measure current CITHP and confirm. 3. Grease failed valves with grease guns. 4. If greasing fails, well to be suspended with a downhole plug (Securing proposal signed off). LS: 1. Routine Surveillance to be carried out on the LS & SS. 2. Grease failed valves with grease guns and carry out a repeat WIT. 3. Change out the FWV for LS. | SS 1. 05/08/2021. 2. 05/08/2021. 3. 05/08/2021 4. 30/04/2022. LS 1. Daily 2. 05/08/2021. 3. 30/04/2022.. | SS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. Opns - Femi / Dapiriye. 4. CWI - Chinedu LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu |  | 1. Leave SS closed-in 2. Leave FORC102L Flowing
400000001378 | R | FODPA | 9 | FOCY123 | LP | Flowing | LS: SSSV, SV SS: SSSV2, LMV2, SV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead IDS cage available but deactivated. 2. LS valves tested and integral (MV, SSV and FWV) 3. SS valves teated and integral (FWV and SSV). 3. Xmas tree cap integral and available. | SS: The measured CITHP is 10 bar. No functional barrier. LS:The measured CITHP is 17 bar. The well is an intermittent producer (PBU) well | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC123L/S flowing. Leave FORC123S flowing as PBU
400000001377 | R |  | 9 | FOCY122 | LP | Flowing | LS: SSV, SS: LMV2, SSSV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead IDS cage available but deactivated. 2. LS can not flow naturally and currently closed-in. All Xmas tree valves functional. 2. LS valves tested and integral (SCSSSV, MV, SV and FWV) 3. SS valve tested and integral (SV / FWV). 4. Xmas tree cap integral and available. | SS: The measured CITHP is 34 bar. Only 1 functional barrier. LS:The measured CITHP is 38 bar. | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | leave FORC122L/S Flowing
400000001638 | R | Cluster 95 | 9 | FOCY100 | LP | Closed in | LS: SSSV, SV SS: LMV2, SSSV2,, SV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage. 2. LS MV & WV integral. 3. SS valves teated and integral (FWV and SSV). 4. Xmas tree cap integral and available. | SS: The measured CITHP is 40bar. No functional barrier. LS:The measured CITHP is 65 bar. | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave both arms closed-in
400000001635 | R | Cluster JA | 9 | FOCY135 | LP | Flowing | LS: SSV, LMV SS: SSV2, LMV2, SSSV2 | C3 | C3 | C3 | C3 | Medium | 1. No wellhead vage 2. LS can not flow naturally and currently closed-in. 3. LS SCSSSV, SV & WV integral. 4. SS valves tested and integral (SV / FWV). 5. Xmas tree cap integral and available. | SS: Well (PBU) currently flowing with 1 barrier. CITHP = 18 barg LS: Quit production. CITHP = 13 barg | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu | 1. 14th Feb 2020. 2. 14th Feb 2020. 3. Daily. 4. 30th Mar 2020 | 1. Leave LS closed-in. 2. leave SS Flowing.
400000001631 | R | Cluster 20 | 9 | FOCY047S1 | LP | Flowing | LS: SSSV, SV | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage. 3. LS valves tested and integral (MV / FWV ). 3. Xmas tree cap integral and available.. 4. SS integral (no issues) | LS:The measured CITHP is 15 barg. SS: Integral with no failures | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC047L/S Flowing
400000001362 | R | Cluster 2 | 9 | FOCY028 | LP | Flowing | LS: SSSV, SS: SSSV2, UMV2 FWVI2, | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage. 2. LS MV, SV & WV integral (All Xmas tree valves functional). 3. SS valve tested and integral (SV). 4. Xmas tree cap integral and available. | LS:The measured CITHP is 45 barg. SS: The measured CITHP is 28 barg. | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | LS/SS 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | LS 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC028L/S Flowing
|  | Standalone Yokri Land | 9 | FOCY127S1 | GL | Flowing | T: SSSV, SV | C4 | C2 | C4 | C2 | Medium | 1. Valve tested and ok (MV & WV) 2. Xmas tree cap. 3. Standalone Yokri Land well | The well is in close proximity to people in the community and it is a concern. | 1. Grease valves with grease guns. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC127T well Flowing
|  | Cluster 5A | 9 | FOCY131 | LP | Flowing | LS: SSV2 SS: SSSV2 | C2 | C3 | C3 | C3 | Medium | 1. Wellhead cage and fence 2. XMT tree cap integral and available 3. Valves tested ok (MV, SV & FWV). | The well is in Estuary (Offshore). LS: Producing. CITHP = 28 barg SS: Closed-in. CITHP = 20 barg SSV stuck in open position. | 1. Obtain grease/grease guns and grease failed valve (Ops) 2. Carry out daily surveillance on the well. 3. Carry out SLM on ScSSV & failed valves. 3. Change out ScSSV if CM is unsuccessful. | 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | 1. Leave LS flowing. 2. Leave SS Closed-in.
|  | Cluster 9 | 9 | FOCY056 | LP | Closed in | LS: SSSV, SSV. SS: SSV2 | C2 | C3 | C3 | C3 | Medium | 1. IDS Wellhead cage dismantled and not functional. 3. LS redundant tested and integral (SV / FWV / SSV ). 4. SS valves integral (SV, FWV, MV & SSSV) 3. Xmas tree cap integral and available.. | The well is in Estuary (Offshore). LS: CITHP = 100 barg SS: Closed-in. CITHP = 10 barg | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | 1. 05/08/2021 2. Daily 3. 30/04/2022. 4. 30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Leave FORC056L/S closed-in
|  | Cluster 51 | 9 | FOCY072S1 | LP | Closed in | T: SSSV, SSV | C2 | C3 | C3 | C3 | Medium | 1. No wellhead cage. 3. Valve tested and integral (SV / MV / FWV ). 3. Xmas tree cap integral and available. | Well CITHP = 165 barg. Only closed-in for Rig activity on FORC073 | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | 1. 05/08/2021 2. Daily 3.30/04/2022. 4.30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | Fix failed valves and open-up well after rig demob
|  | Cluster JA | 9 | FOCY134 | LP | Flowing | LS: SV SS: SSV2, SSSV2, | C2 | C3 | C3 | C3 | Medium | 1. No Wellhead cage. 3. LS valve tested and integral (MV / FWV / SSV and SSSV). 4. SS valves tested and integral (SV/LMV /FWV) 3. Xmas tree cap integral and available.. | SS Closed-in: CITHP = . | LS/SS 1. Grease failed valves with grease gun. 2. Carry out daily surveillance on well 3. Carry out SLM on ScSSV & failed valves. 4. Change out the ScSSV if SLM unsuccessful. | 1. 05/08/2021 2. Daily 3.30/04/2022. 4.30/04/2022. | 1. Opns - Femi / Dapiriye 2. Opns - Femi / Dapiriye 3. CWI - Chinedu 4. CWI - Chinedu |  | 1. Leave LS flowing. 2. Leave SS Closed-in.

## YOKRI_FOCY111 (hidden)
TOP EVENT: POSSIBLE FIRE OUTBREAK
General
UWI | Traffic Light Status | AC | Action due to TR | Name | WFM Type | Well Status | Reasons | People | Asset | Community | Environment | Overal Risk | Current Mitigations in Place | General Comments | Mitigating Actions | Timeline | Action Party | Expected Closure Date | Recommendation
400000001295 | R | 9 | false | FOCY111 | GL | Flowing | T: SSSV, CTRL, SV | C2 | C3 | C3 | C2 | Medium | 1. Wellhead cage. 2. Location fence intact. 2. Redundant valve tested and integral (MV & FWV). 3. Well can not flow naturally | Only one barrier is integral. A Step wise approach is required to restore integrity as quickly as possible. | T: 1. Grease failed valves with grease guns 2. Carry out special OPSWIT on SS 3. Carry out daily surveillance on well. 4. Carry out SLM if valves fail. 5. Change out the ScSSV if SLM unsuccessful (FMT to prepare proposal) | 1. 31/03/2020 2. 31/03/2020 3. Daily 4. 30/05/2020 5. 29/06/2020. | 1. Opns - Tunde Akinro. 2. Opns - Tunde Akinro. 3. Opns - Tunde Akinro. 4. CWI - Ricky / Pius. 5. CWI / FMT - Ricky / Pius/Elias |  | Leave FORC111T Flowing

## ESCB_Land (hidden)
TOP EVENT: POSSIBLE FIRE OUTBREAK
General
| AC | Action due to TR | Name | WFM Type | Well Status | Reasons | People | Asset | Community | Environment | Overal Risk | Current Mitigations in Place | General Comments | Mitigating Actions |  | Action Party | Expected Closure Date | Recommendation
| 9 | false | ESCB011 | LP | Flowing | LS: SSSV, SV SS: SSSV2, UMV2, SV2 | C2 | C3 | C3 | C2 | Medium | 1. Wellhead cage and fenced. 2. LS redundant valve tested and integral (MV / FWV ). 3. SS: only WV integral 4. Xmas tree cap. | Step wise approach is required to restore integrity as quickly as possible. | LS/SS: 1. Grease failed valves with grease guns. 2. Carry-out special OPSWIT on LS 3. Carry out daily surveillance on well. 4. Carry out SLM on SCSSSV amd failed valves. | 1. 31/03/2020 2. 31/03/2020 3. Daily 4. 30/05/2020 | 1. Opns - Tunde Akinro. 2. Opns - Tunde Akinro. 3. Opns - Tunde Akinro. 4. CWI - Ricky / Pius. |  | Leave ESCB011 Closed-in
| 9 | false | ESCB013 | LP | Closed in | LS: FWVI, SV, LMV. SS: UMV2, SSSV2, LMV2, SV2 | C2 | C3 | C3 | C2 | Medium | 1. Wellhead cage and fenced. 2. LS: SCSSSV integral. 3. SS: Only WV integral 4. Xmas tree cap. | Step wise approach is required to restore integrity as quickly as possible. | LS/SS: 1. Grease failed valves with grease guns. 2. Carry-out special OPSWIT on LS 3. Carry out daily surveillance on well. 4. Carry out SLM on SCSSSV amd failed valves | 1. 31/03/2020 2. 31/03/2020 3. Daily 4. 30/05/2020 | 1. Opns - Tunde Akinro. 2. Opns - Tunde Akinro. 3. Opns - Tunde Akinro. 4. CWI - Ricky / Pius. |  | Leave ESCB013 Closed-in