## Well Integrity Overview (hidden)
General | [10 empty] | Risk Assessment |  |  |  |  | Assurance task data | [13 empty] | THP Readings |  |  | A Annulus |  |  |  |  | B Annulus
UWI | Action Code | Risk Level | Reportable | Name | WFM Type | WFM Configuration | Production Status | Lift Type | Field | Reasons | Deviation Class | People | Asset | Community | Environment | Last routine WIT | WIT Due date | Sub Code | Last routine SIT | SIT Due Date | Last Ann. Inv. | Nr of Notifications | Goes Red On | Goes Red Reason | Remark/General Comments | Mitigating Actions and General Comments | Action Party | Expected Closure Date | Leak Controlled | Long String [bar] | Short String [bar] | Recording date | MAASP [bar] | MAWOP [bar] | Trigger [bar] | Actual reading [bar] | Recording date | MAASP [bar] | MAWOP [bar] | Trigger [bar] | Actual reading [bar] | Recording date
400000000699 | 0 | Low |  | AFRE004 | LP | DUAL_TREE | Flowing | No lift | AFREMO | APM - B O/due. | [5 empty] | 2018-11-09 | 2019-05-11 | Ops_WIT | 2015-06-18 |  |  | 1 | 2018-04-23 | APM - B due date. | [6 empty] | 80 | 2018-11-09 | 224 | 179 | 168 | 0 | 2019-02-24 | 30 | 24 | 22 | 0 | 2018-03-24
400000000703 | 6 | Low |  | AFRE008 | LP | DUAL_TREE | Closed in | No lift | AFREMO | SSV, APM - B O/due., SSV2 | [5 empty] | 2018-11-09 | 2019-05-11 | Ops_WIT | 2015-06-18 |  |  | 3 | 2017-11-11 | SSV - Failure Due Date | [8 empty] | 187 | 150 | 140 | 0 | 2019-02-24 | 11 | 9 | 8 | 0 | 2018-11-09
400000000720 | 6 | Low |  | AFRE009 | LP | DUAL_TREE | Closed in | No lift | AFREMO | CTRL2, CTRL | [5 empty] | 2018-10-31 | 2019-05-02 | Ops_WIT | 2015-06-18 |  |  | 2 | 2018-12-30 | CTRL2 - Failure Due Date, CTRL - Failure Due Date |  | • Change action code to 6 and plan to secure well (TR) | [6 empty] | 171 | 137 | 128 | 0 | 2019-02-24 | 10 | 8 | 7 | 0 | 2019-02-24
400000000705 | 7 | Low |  | AFRE011 | LP | DUAL_TREE | Closed in | No lift | AFREMO | LMV, SSV, SSV2, LMV2 | [5 empty] | 2018-11-09 | 2019-05-11 | Ops_WIT | 2015-06-25 |  |  | 4 | 2018-04-04 | LMV - Failure Due Date, LMV2 - Failure Due Date | [8 empty] | 186 | 149 | 139 | 0 | 2019-02-24 | 7 | 6 | 5 | 2 | 2019-02-24
400000000902 | 0 | Low |  | AKON001 | LP | DUAL_TREE | Closed in | No lift | AKONO | Cmb_WITSIT O/due, Ops_WIT O/due | [5 empty] | 2018-08-04 | 2016-05-08 | Cmb_WITSIT | 2012-11-27 |  |  | 0 | 2016-05-08 | Cmb_WITSIT due date | [6 empty] | 0 | 2018-08-04 | 70 | 56 | 52 | 0 | 2019-03-10 | 39 | 31 | 29 | 0 | 2019-03-10
400000000903 | 6 | Low |  | BENS001 | LP | DUAL_TREE | Closed in | No lift | BENISEDE | SSSV2, SSSV | [5 empty] | 2019-02-28 | 2019-08-30 | Ops_WIT | 2014-02-21 |  |  | 2 | 2018-11-17 | SSSV2 - Failure Due Date, SSSV - Failure Due Date | [6 empty] | 0 | 2019-02-28 | 115 | 92 | 86 | 26 | 2019-03-10 | 21 | 17 | 16 | 0 | 2019-03-10
400000000907 | 0 | Low |  | BENS002S1 | LP | SINGLE_TREE | Closed in | No lift | BENISEDE | Cmb_WITSIT O/due, Ops_WIT O/due | [5 empty] | 2018-06-11 | 2016-04-30 | Cmb_WITSIT | 2014-02-21 |  |  | 0 | 2016-04-30 | Cmb_WITSIT due date | [8 empty] | 75 | 60 | 56 | 0 | 2019-02-22 | 29 | 23 | 22 | 0 | 2019-02-22
400000000904 | 6 | Low |  | BENS003 | LP | SINGLE_TREE | Flowing | No lift | BENISEDE | FWVI, SV, SSV | [5 empty] | 2019-03-05 | 2019-09-10 | Ops_WIT | 2014-02-28 |  |  | 3 | 2018-11-09 | FWVI - Failure Due Date, SV - Failure Due Date, SSV - Failure Due Date | [8 empty] | 119 | 95 | 89 | 0 | 2019-03-10 | 22 | 18 | 16 | 0 | 2019-03-10
400000000908 | 6 | Low |  | BENS004 | LP | DUAL_TREE | Closed in | No lift | BENISEDE | SV2, FWVI, FWVI2, LMV2, SV | [5 empty] | 2019-03-05 | 2019-09-07 | Ops_WIT | 2014-02-27 |  | 2016-11-11 | 7 | 2017-05-23 | SV2 - Failure Due Date, SV - Failure Due Date |  | Plan for SLM once spares are available. (TR) |  |  |  |  | 0 | 2019-03-05 | 118 | 94 | 88 | 32 | 2019-03-10 | 38 | 30 | 28 | 0 | 2019-03-10
400000000909 | 0 | Low |  | BENS005 | LP | SINGLE_TREE | Flowing | No lift | BENISEDE | Ops_WIT freq. | [5 empty] | 2018-09-09 | 2019-03-11 | Ops_WIT | 2014-02-26 |  |  | 0 | 2019-03-11 | Ops_WIT due date |  | ScSSSV change out aborted due to fish in hole (Lower part of ScSSSV parted during retrieval and is stuck in hole). Fishing tentatively planned in Q1 2014. Budget constriant highlighted as possible blocker, however accoutnt to charge has been provided by Asset Mgr. | [6 empty] | 132 | 106 | 99 | 0 | 2019-02-22 | 17 | 14 | 13 | 0 | 2019-02-22
400000000913 | 4 | Low |  | BENS011 | LP | DUAL_TREE | Closed in | No lift | BENISEDE | FWVI, Ops_WIT freq. | [5 empty] | 2018-09-07 | 2019-03-08 | Ops_WIT | 2014-02-26 |  |  | 1 | 2019-03-06 | FWVI - Failure Due Date | [8 empty] | 131 | 105 | 98 | 0 | 2019-03-10 | 10 | 8 | 7 | 0 | 2019-03-10
400000000914 | 6 | Low |  | BENS013 | LP | SINGLE_TREE | Flowing | No lift | BENISEDE | SSV, SV, FWVO, KWV, FWVI | [5 empty] | 2019-03-05 | 2019-09-11 | Ops_WIT | 2014-02-20 |  |  | 5 | 2017-06-29 | SSV - Failure Due Date | [8 empty] | 121 | 97 | 91 | 0 | 2019-03-10 | 28 | 22 | 21 | 0 | 2019-03-10
400000000921 | 0 | Low |  | BENS020 | LP | SINGLE_TREE | Flowing | No lift | BENISEDE | APM - A O/due., APM - B O/due. | [5 empty] | 2018-09-21 | 2019-03-23 | Ops_WIT | 2014-02-28 |  |  | 2 | 2018-12-10 | APM - A due date., APM - B due date. | [8 empty] | 129 | 103 | 97 | 0 | 2018-11-10 | 8 | 6 | 6 | 0 | 2018-11-10
400000000922 | 6 | Low |  | BENS021 | LP | DUAL_TREE | Flowing | No lift | BENISEDE | SSSV, Cmb_WITSIT O/due, Ops_WIT freq. | [5 empty] | 2017-09-21 | 2018-03-24 | Ops_WIT | 2014-02-26 |  |  | 1 | 2017-11-20 | SSSV - Failure Due Date | [6 empty] | 15 | 2017-09-21 | 150 | 120 | 112 | 0 | 2019-03-10 | 8 | 6 | 6 | 0 | 2019-03-10
400000000923 | 7 | Low |  | BENS022S1 | LP | SINGLE_TREE | Flowing | No lift | BENISEDE | UMV, LMV | [5 empty] | 2019-03-05 | 2019-09-16 | Ops_WIT | 2014-02-28 |  |  | 2 | 2017-06-12 | UMV - Failure Due Date | [6 empty] | 0 | 2019-03-05 | 106 | 85 | 79 | 0 | 2019-03-10 | 16 | 13 | 12 | 0 | 2019-03-10
400000001514 | 1 | Low |  | EA031S1 | OFF_NF | SINGLE_TREE | Flowing | No lift | EA-B | CTRL | [5 empty] | 2019-02-24 | 2019-08-26 | WIT | 2018-03-21 | 2019-03-22 |  | 1 | 2019-03-22 | SIT due date |  | CTRL line failure (TR) | [6 empty] | 69 | 55 | 52 | 1 | 2019-03-13 | 40 | 32 | 30 | 9 | 2019-03-13
400000000717 | 6 | Low |  | ESCB001 | LP | DUAL_TREE | Flowing | No lift | ESCRAVOS BEACH | LMV, SV2, SV | [5 empty] | 2019-02-20 | 2019-08-25 | Ops_WIT | 2014-04-11 |  |  | 3 | 2018-10-24 | LMV - Failure Due Date, SV2 - Failure Due Date, SV - Failure Due Date | [6 empty] | 40 | 2019-02-20 | 256 | 205 | 192 | 0 | 2019-03-05 | 4 | 3 | 3 | 0 | 2019-03-05
400000000719 | 6 | Low |  | ESCB003 | LP | SINGLE_TREE | Closed in | No lift | ESCRAVOS BEACH | SV, LMV | [5 empty] | 2019-02-19 | 2019-08-21 | Ops_WIT | 2014-04-11 |  | 2011-04-08 | 2 | 2019-04-20 | SV - Failure Due Date, LMV - Failure Due Date | [8 empty] | 169 | 135 | 127 | 0 | 2019-03-05 | 29 | 23 | 22 | 0 | 2019-03-05
400000000709 | 0 | Low |  | ESCB005 | LP | DUAL_TREE | Closed in | No lift | ESCRAVOS BEACH | Cmb_WITSIT freq., Ops_WIT freq., APM - A O/due., APM - B O/due. | [5 empty] | 2018-06-04 | 2018-07-04 | Cmb_WITSIT | 2014-04-11 |  |  | 2 | 2018-07-04 | Cmb_WITSIT due date | [6 empty] | 0 | 2018-06-04 | 97 | 78 | 73 | 0 | 2018-09-05 | 26 | 21 | 19 | 0 | 2018-09-05
400000000711 | 0 | Low |  | ESCB007 | LP | DUAL_TREE | Closed in | No lift | ESCRAVOS BEACH | APM - A O/due., Ops_WIT O/due, Cmb_WITSIT O/due, APM - B O/due. | [5 empty] | 2018-03-02 | 2018-07-04 | Cmb_WITSIT | 2014-04-11 |  |  | 2 | 2017-06-04 | APM - A due date., APM - B due date. | [8 empty] | 180 | 144 | 135 | 0 | 2017-05-05 | 10 | 8 | 7 | 0 | 2017-05-05
400000000714 | 9 | Medium |  | ESCB011 | LP | DUAL_TREE | Flowing | No lift | ESCRAVOS BEACH | SSSV2, SV, UMV2, SV2, SSSV | [5 empty] | 2019-02-19 | 2019-08-21 | Ops_WIT | 2014-04-11 |  |  | 5 | 2018-03-31 | SSSV2 - Failure Due Date, SSSV - Failure Due Date | [6 empty] | 10 | 2019-02-19 | 236 | 189 | 177 | 0 | 2019-03-04 | 16 | 13 | 12 | 0 | 2019-03-04
400000000715 | 9 | Medium |  | ESCB013 | LP | DUAL_TREE | Closed in | No lift | ESCRAVOS BEACH | LMV2, SSSV2, UMV2, LMV, FWVI, SV2, SV | [5 empty] | 2019-02-21 | 2019-08-25 | Ops_WIT | 2014-04-11 |  |  | 7 | 2017-09-21 | LMV2 - Failure Due Date |  | • Change action code to 6 based on WFM recommendation CWI to carry out Second Line Maintenance (TR) |  |  |  |  | 0 | 2019-02-21 | 238 | 190 | 178 | 0 | 2019-03-05 | 6 | 5 | 4 | 0 | 2019-03-05
400000007782 | 0 | Medium |  | FCSW002 | LP | SUSP_FLANGE | Suspended | No lift | FORCADOS SOUTH WEST | Cmb_WITSIT O/due | Medium | B2 | B2 | C3 | C3 |  | 2017-12-20 | Cmb_WITSIT |  |  |  | 0 | 2016-01-27 | Cmb_WITSIT due date |  | Well not perforated. Drilled and suspended with suspension cap.
400000001354 | 0 | Low |  | FOCR002 | LP | SUSP_FLANGE | Completed | No lift | YOKRI | APM - A O/due., Ops_WIT O/due, Cmb_WITSIT O/due, APM - B O/due. | [5 empty] | 2017-02-15 | 2017-07-16 | Cmb_WITSIT | 2013-05-22 |  |  | 2 | 2015-06-08 | APM - A due date., APM - B due date. | [8 empty] | 27 | 21 | 21 | 0 | 2015-05-09 | 31 | 24 | 24 | 0 | 2015-05-09
400000002552 | 0 | Low |  | FOCY003 | LP | DUAL_TREE | Suspended | No lift | FORCADOS YOKRI | Cmb_WITSIT freq. | [5 empty] | 2015-04-25 | 2018-11-22 | Cmb_WITSIT |  |  |  | 0 | 2018-11-22 | Cmb_WITSIT due date | [8 empty] | 175 | 140 | 131 | 0 | 2019-02-24 | 31 | 25 | 23 | 0 | 2019-02-24
400000001356 | 7 | Low |  | FOCY005 | LP | DUAL_TREE | Flowing | No lift | FORCADOS YOKRI | SSV2, Ops_WIT freq., SV, LMV | [5 empty] | 2018-07-10 | 2019-01-08 | Ops_WIT | 2015-07-29 |  |  | 3 | 2017-09-09 | SSV2 - Failure Due Date |  | Changed A annulus to 128 bbls. | [6 empty] | 189 | 151 | 142 | 0 | 2019-02-24 | 29 | 23 | 22 | 0 | 2019-02-24
400000001641 | 6 | Low |  | FOCY020S1 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | SV2, Ops_WIT freq., LMV, FWVI2 | [5 empty] | 2018-08-22 | 2019-02-21 | Ops_WIT | 2013-05-22 |  |  | 3 | 2018-10-21 | SV2 - Failure Due Date, FWVI2 - Failure Due Date | [8 empty] | 180 | 144 | 135 | 0 | 2019-02-24 | 4 | 3 | 3 | 0 | 2019-02-24
400000001360 | 4 | Low |  | FOCY024S1 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | FWVI2 | [5 empty] | 2018-09-27 | 2019-03-29 | Ops_WIT | 2015-07-29 |  |  | 1 | 2017-12-09 | FWVI2 - Failure Due Date | [8 empty] | 196 | 157 | 147 | 7 | 2019-02-24 | 9 | 7 | 7 | 5 | 2019-02-24
400000001361 | 6 | Low |  | FOCY027 | LP | DUAL_TREE | Flowing | No lift | FORCADOS YOKRI | SSV, Ops_WIT freq., SSV2, FWVI2, SV | [5 empty] | 2018-08-28 | 2019-02-27 | Ops_WIT | 2015-07-29 |  | 2018-09-13 | 4 | 2018-10-27 | SSV - Failure Due Date, SSV2 - Failure Due Date, FWVI2 - Failure Due Date, SV - Failure Due Date | [6 empty] | 14 | 2018-08-28 | 206 | 165 | 154 | 0 | 2019-02-24 | 4 | 3 | 3 | 0 | 2019-02-24
400000001642 | 0 | Low |  | FOCY031 | LP | DUAL_TREE | Flowing | No lift | FORCADOS YOKRI | APM - A O/due. | [5 empty] | 2018-12-23 | 2019-06-24 | Ops_WIT | 2013-05-22 |  |  | 1 | 2018-06-15 | APM - A due date. | [8 empty] | 186 | 149 | 139 | 0 | 2018-05-16 | 7 | 6 | 5 | 0 | 2019-02-24
400000001365 | 0 | Medium |  | FOCY032 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | Cmb_WITSIT freq., Ops_WIT freq. dev., APM - A Dev., APM - B Dev. | Medium | C2 | D3 | C3 | C4 | 2017-06-12 | 2015-07-15 | Cmb_WITSIT | 2013-05-07 |  |  | 2 | 2015-07-15 | Cmb_WITSIT due date | [8 empty] | 192 | 154 | 144 | 0 | 2017-06-12 | 6 | 5 | 4 | 0 | 2017-06-12
400000001366 | 0 | Medium |  | FOCY033 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | Cmb_WITSIT freq., Ops_WIT freq. dev., APM - B Dev., APM - A Dev. | Medium | C2 | D3 | C3 | C4 | 2017-06-12 | 2015-07-15 | Cmb_WITSIT | 2013-05-07 |  |  | 2 | 2015-07-15 | Cmb_WITSIT due date | [8 empty] | 189 | 151 | 142 | 14 | 2017-06-12 | 6 | 5 | 4 | 0 | 2017-06-12
400000001367 | 0 | Medium |  | FOCY034 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | Cmb_WITSIT freq., Ops_WIT freq. dev., APM - B Dev., APM - A Dev. | Medium | C2 | D3 | C3 | C4 | 2017-06-12 | 2015-07-15 | Cmb_WITSIT | 2013-05-07 |  |  | 2 | 2015-07-15 | Cmb_WITSIT due date | [8 empty] | 181 | 145 | 136 | 0 | 2017-06-12 | 6 | 5 | 4 | 0 | 2017-06-12
400000001892 | 0 | Low |  | FOCY040 | OFF_NF | DEBRIS_CAP | Awaiting Abandonment | No lift | FORCADOS YOKRI | SIT freq. | [5 empty] | 2018-01-26 |  |  |  | 2012-03-31 |  | 0 | 2012-03-31 | SIT due date |  | Well not perforated. Drilled and suspended with multiple cement plug and debris cap.
400000001643 | 0 | Medium |  | FOCY042 | LP | SINGLE_TREE | Completed | No lift | FORCADOS YOKRI | Cmb_WITSIT O/due, APM - A Dev., APM - B Dev., Ops_WIT dev. | Medium | C2 | D3 | C3 | C4 | 2017-08-09 | 2019-11-09 | Ops_WIT | 2013-05-22 |  |  | 2 | 2019-03-04 | Cmb_WITSIT due date | [8 empty] | 189 | 151 | 142 | 0 | 2017-09-05 | 9 | 7 | 7 | 1 | 2017-09-05
400000001646 | 4 | Low |  | FOCY048S1 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | LMV | [5 empty] | 2019-02-22 | 2019-08-24 | Ops_WIT | 2013-05-22 |  |  | 1 | 2019-01-08 | LMV - Failure Due Date | [6 empty] | 0 | 2019-02-22 | 179 | 143 | 134 | 0 | 2019-02-24 | 7 | 6 | 5 | 0 | 2019-02-24
400000001275 | 0 | Low |  | FOCY051 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | Ops_WIT O/due, APM - A O/due., APM - B O/due. | [5 empty] | 2017-08-11 | 2017-09-07 | Ops_WIT | 2013-05-23 |  |  | 2 | 2017-09-07 | Ops_WIT due date | [8 empty] | 188 | 150 | 141 | 0 | 2017-08-11 | 2 | 2 | 1 | 0 | 2017-08-11
400000001650 | 0 | Medium |  | FOCY054 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | Cmb_WITSIT freq., APM - B Dev., APM - A Dev., Ops_WIT dev. | Medium | C2 | D3 | C3 | C4 | 2017-03-21 | 2019-11-09 | Ops_WIT | 2013-05-22 |  |  | 2 | 2019-03-12 | Cmb_WITSIT due date | [8 empty] | 263 | 210 | 197 | 0 | 2017-03-21 | 3 | 2 | 2 | 0 | 2017-09-06
400000001651 | 0 | Medium |  | FOCY055 | LP | SINGLE_TREE | Completed | No lift | FORCADOS YOKRI | Cmb_WITSIT O/due, APM - B Dev., APM - A Dev., Ops_WIT dev. | Medium | C2 | D3 | C3 | C4 | 2017-08-09 | 2019-11-09 | Ops_WIT | 2015-07-15 |  |  | 2 | 2019-03-04 | Cmb_WITSIT due date | [8 empty] | 188 | 150 | 141 | 0 | 2017-09-05 | 5 | 4 | 4 | 0 | 2017-09-05
400000001654 | 0 | Medium |  | FOCY062 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | Cmb_WITSIT O/due, APM - B Dev., APM - A Dev., Ops_WIT dev. | Medium | C2 | D3 | C3 | C4 | 2017-08-09 | 2019-11-09 | Ops_WIT | 2015-05-25 |  |  | 2 | 2019-03-04 | Cmb_WITSIT due date | [8 empty] | 194 | 155 | 145 | 0 | 2017-09-06 | 2 | 2 | 1 | 0 | 2017-09-06
400000001395 | 6 | Low |  | FOCY066 | LP | DUAL_TREE | Flowing | No lift | FORCADOS YOKRI | Ops_WIT freq., APM - A O/due., CTRL2, CTRL | [5 empty] | 2017-04-26 | 2013-11-13 | Ops_WIT | 2013-05-15 |  |  | 3 | 2013-11-13 | Ops_WIT due date |  | • CWI to carry out Second Line Maintenance. (Flush the CTRL or install PBV) (TR) | [6 empty] | 187 | 150 | 140 | 61 | 2018-10-04 | 7 | 6 | 5 | 0 | 2019-02-24
400000001276 | 0 | Low |  | FOCY072S1 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | Ops_WIT O/due, APM - B O/due., APM - A O/due. | [5 empty] | 2017-08-09 | 2017-09-07 | Ops_WIT | 2013-05-23 |  |  | 2 | 2017-09-07 | Ops_WIT due date | [8 empty] | 186 | 149 | 139 | 0 | 2017-08-09 | 9 | 7 | 7 | 0 | 2017-08-09
400000001277 | 0 | Low |  | FOCY073 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | APM - A O/due., Ops_WIT O/due, APM - B O/due. | [5 empty] | 2017-08-09 | 2018-02-07 | Ops_WIT | 2013-05-23 |  |  | 2 | 2017-09-08 | APM - A due date., APM - B due date. | [6 empty] | 0 | 2017-08-09 | 188 | 150 | 141 | 0 | 2017-08-09 | 2 | 2 | 1 | 0 | 2017-08-09
400000001278 | 9 | Medium |  | FOCY074 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | LMV, SSSV | Medium | C3 | C3 | C3 | C4 | 2018-09-14 | 2019-03-16 | Ops_WIT | 2015-07-28 |  |  | 2 | 2019-03-16 | Ops_WIT due date | [8 empty] | 185 | 148 | 139 | 55 | 2019-02-28 | 39 | 31 | 29 | 0 | 2019-02-28
400000001279 | 4 | Low |  | FOCY075 | LP | SINGLE_TREE | Flowing | No lift | FORCADOS YOKRI | LMV, Ops_WIT O/due | [5 empty] | 2018-05-17 | 2018-11-16 | Ops_WIT | 2015-07-28 |  |  | 1 | 2018-11-13 | LMV - Failure Due Date | [8 empty] | 267 | 214 | 200 | 53 | 2019-02-28 | 3 | 2 | 2 | 0 | 2019-02-28
400000001282 | 0 | Low |  | FOCY079 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | APM - A O/due., Cmb_WITSIT O/due, Ops_WIT freq., APM - B O/due. | [5 empty] | 2015-07-28 | 2016-02-15 | Ops_WIT | 2015-07-28 |  |  | 2 | 2015-08-27 | APM - A due date., APM - B due date. | [8 empty] | 254 | 203 | 190 | 0 | 2015-07-28 | 8 | 6 | 6 | 0 | 2015-07-28
400000001396 | 0 | Low |  | FOCY081 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | APM - B O/due., Ops_WIT O/due | [5 empty] | 2018-01-21 | 2018-08-03 | Ops_WIT | 2015-07-29 |  |  | 1 | 2017-09-02 | APM - B due date. | [6 empty] | 0 | 2018-01-21 | 239 | 191 | 179 | 0 | 2019-02-24 | 7 | 6 | 5 | 0 | 2017-08-03
400000001283 | 0 | Low |  | FOCY084 | LP | DUAL_TREE | Flowing | No lift | FORCADOS YOKRI | APM - A O/due., APM - B O/due. | [5 empty] | 2018-12-06 | 2019-06-07 | Ops_WIT | 2015-07-28 |  |  | 2 | 2019-03-05 | APM - A due date., APM - B due date. | [6 empty] | 7 | 2018-12-06 | 183 | 146 | 137 | 43 | 2019-02-03 | 17 | 14 | 13 | 0 | 2019-02-03
400000001284 | 0 | Low |  | FOCY085 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | APM - B O/due., Ops_WIT freq. | [5 empty] | 2017-06-18 | 2017-12-17 | Ops_WIT | 2013-05-20 |  |  | 1 | 2017-07-18 | APM - B due date. | [8 empty] | 231 | 185 | 173 | 0 | 2019-02-21 | 8 | 6 | 6 | 0 | 2017-06-18
400000001289 | 0 | Low |  | FOCY090 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | Ops_WIT O/due, APM - A O/due., APM - B O/due. | [5 empty] | 2017-08-03 | 2015-11-22 | Ops_WIT | 2015-05-04 |  |  | 2 | 2015-11-22 | Ops_WIT due date | [8 empty] | 187 | 150 | 140 | 3 | 2017-08-03 | 16 | 13 | 12 | 0 | 2017-08-03
400000001662 | 0 | Medium |  | FOCY093 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | APM - B O/due., APM - A Dev., Ops_WIT dev. | Medium | C2 | D3 | C3 | C4 | 2017-08-03 | 2019-11-09 | Ops_WIT | 2015-05-25 |  |  | 2 | 2017-09-02 | APM - B due date. | [8 empty] | 345 | 276 | 259 | 0 | 2017-08-03 | 8 | 6 | 6 | 0 | 2017-08-03
400000001664 | 7 | Low |  | FOCY095 | LP | SINGLE_TREE | Closed in | No lift | FORCADOS YOKRI | LMV, SSV | [5 empty] | 2019-02-22 | 2019-08-24 | Ops_WIT | 2015-07-15 |  |  | 1 | 2018-01-30 | LMV - Failure Due Date | [8 empty] | 177 | 142 | 133 | 0 | 2019-02-24 | 9 | 7 | 7 | 0 | 2019-02-24
400000001638 | 6 | Low |  | FOCY100 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | SSSV, LMV2 | [5 empty] | 2019-02-22 | 2019-08-24 | Ops_WIT | 2015-07-15 |  |  | 2 | 2018-09-29 | SSSV - Failure Due Date | [6 empty] | 0 | 2019-02-22 | 177 | 142 | 133 | 0 | 2019-02-24 | 5 | 4 | 4 | 0 | 2019-02-24
400000001640 | 1 | Low |  | FOCY102 | LP | DUAL_TREE | Flowing | No lift | FORCADOS YOKRI | SV, SV2 | [5 empty] | 2018-10-04 | 2019-04-05 | Ops_WIT | 2015-05-25 |  |  | 1 | 2019-04-05 | Ops_WIT due date |  | Repair SV for both strings (TR) |  |  |  |  | 9 | 2018-10-04 | 192 | 154 | 144 | 0 | 2019-02-24 | 18 | 14 | 13 | 0 | 2019-02-24
400000001293 | 3 | Low |  | FOCY109 | GL | SINGLE_TREE | Flowing | Gas Lift | FORCADOS YOKRI | APM - B O/due., SV, SSV, Ops_WIT freq., APM - A O/due. | [5 empty] | 2018-09-10 | 2019-03-12 | Ops_WIT | 2015-07-28 |  |  | 4 | 2019-03-05 | APM - B due date., APM - A due date. | [8 empty] | 265 | 212 | 199 | 62 | 2019-02-03 | 3 | 2 | 2 | 0 | 2019-02-03
400000001294 | 3 | Low |  | FOCY110 | GL | SINGLE_TREE | Flowing | Gas Lift | FORCADOS YOKRI | SSV, Ops_WIT freq., FWVI | [5 empty] | 2017-04-17 | 2018-08-24 | Ops_WIT | 2015-07-28 |  |  | 2 | 2018-07-02 | SSV - Failure Due Date | [8 empty] | 255 | 204 | 191 | 58 | 2019-02-28 | 5 | 4 | 4 | 0 | 2019-02-28
400000001295 | 6 | Low |  | FOCY111 | GL | SINGLE_TREE | Flowing | Gas Lift | FORCADOS YOKRI | CTRL, Ops_WIT freq. | [5 empty] | 2017-11-12 | 2018-05-17 | Ops_WIT | 2015-07-28 |  |  | 1 | 2018-01-11 | CTRL - Failure Due Date | [8 empty] | 233 | 186 | 175 | 46 | 2019-02-28 | 8 | 6 | 6 | 1 | 2019-02-28
400000001296 | 6 | Low |  | FOCY112 | GL | SINGLE_TREE | Flowing | Gas Lift | FORCADOS YOKRI | CTRL, Cmb_WITSIT O/due, Ops_WIT freq. | [5 empty] | 2017-11-12 | 2018-05-14 | Ops_WIT | 2015-07-28 |  |  | 1 | 2018-01-11 | CTRL - Failure Due Date |  | • CWI to carry out Second Line Maintenance. (Flush the CTRL or install PBV) • Change action code to 6. (TR) | [6 empty] | 207 | 166 | 155 | 56 | 2019-02-28 | 6 | 5 | 4 | 0 | 2019-02-28
400000001297 | 6 | Low |  | FOCY113 | GL | SINGLE_TREE | Flowing | Gas Lift | FORCADOS YOKRI | TAW, Ops_WIT freq., SSV | [5 empty] | 2018-09-10 | 2019-03-12 | Ops_WIT | 2015-07-28 |  |  | 2 | 2017-10-02 | TAW - Failure Due Date |  | • CWI to carry out Second Line Maintenance. • Multiple surface failure • Change action code to 7. (TR) CWI to carry out a retest of FORC113 tubing to A annulus seal. If confirmed failed carry out plastic pack. (TR) | [6 empty] | 255 | 204 | 191 | 60 | 2019-02-28 | 8 | 6 | 6 | 0 | 2019-02-28
400000001298 | 3 | Low |  | FOCY114 | GL | DUAL_TREE | Closed in | Gas Lift | FORCADOS YOKRI | APM - B O/due., SSSV2, SSV | [5 empty] | 2019-03-09 | 2019-09-08 | Ops_WIT | 2015-07-28 |  |  | 3 | 2019-02-01 | APM - B due date. | [6 empty] | 0 | 2019-03-09 | 252 | 202 | 189 | 62 | 2019-03-09 | 6 | 5 | 4 | 0 | 2019-01-02
400000001397 | 0 | Low |  | FOCY119 | GL | DUAL_TREE | Closed in | Gas Lift | FORCADOS YOKRI | APM - B O/due., Ops_WIT O/due, Cmb_WITSIT O/due, APM - A O/due. | [5 empty] | 2017-03-23 | 2017-07-28 | Cmb_WITSIT | 2015-07-29 |  |  | 2 | 2017-04-22 | APM - B due date., APM - A due date. | [6 empty] | 0 | 2017-03-23 | 191 | 153 | 143 | 0 | 2017-03-23 | 10 | 8 | 7 | 0 | 2017-03-23
400000001378 | 9 | Medium |  | FOCY123 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | SSV2, CTRL, LMV2, SSSV2 | [5 empty] | 2018-10-22 | 2019-04-23 | Ops_WIT | 2015-07-29 |  |  | 3 | 2018-10-21 | SSV2 - Failure Due Date, LMV2 - Failure Due Date, SSSV2 - Failure Due Date |  | CWI to repair CTRL on the next CMB_WITSIT (TR) | [6 empty] | 197 | 158 | 148 | 10 | 2019-02-24 | 28 | 22 | 21 | 0 | 2019-02-24
400000001399 | 6 | Low |  | FOCY126S2 | LP | DUAL_TREE | Flowing | No lift | FORCADOS YOKRI | LMV2, Ops_WIT O/due, Cmb_WITSIT O/due, LMV, SV2, SV | [5 empty] | 2017-05-24 | 2017-08-03 | Cmb_WITSIT | 2013-05-24 |  |  | 4 | 2017-04-16 | LMV2 - Failure Due Date, SV2 - Failure Due Date, SV - Failure Due Date | [6 empty] | 14 | 2017-05-24 | 116 | 93 | 87 | 0 | 2019-02-24 | 44 | 35 | 33 | 0 | 2019-02-24
400000001301 | 3 | Low |  | FOCY127S1 | GL | SINGLE_TREE | Flowing | Gas Lift | FORCADOS YOKRI | TTC, SSV, Ops_WIT freq., overdue interim control action | [5 empty] | 2018-08-20 | 2019-02-19 | Ops_WIT | 2013-05-20 |  |  | 2 | 2018-12-02 | TTC - Failure Due Date |  | CWI to visit well FORC127 re-test and energize seal on tubing head to flange connection as required and fix SSV failure. (TR) CWI to visit well and re-test and repair leak on Tubing head to flange connection. (TR) | [6 empty] | 186 | 149 | 139 | 52 | 2019-03-09 | 7 | 6 | 5 | 0 | 2019-03-09
400000001380 | 0 | Low |  | FOCY128S1 | LP | SUSP_FLANGE | Suspended | No lift | FORCADOS YOKRI | Cmb_WITSIT O/due | [6 empty] | 2018-04-27 | Cmb_WITSIT |  |  |  | 0 | 2018-04-27 | Cmb_WITSIT due date |  | Well was drilled and suspended. | [6 empty] | 31 | 25 | 23 |  |  | 27 | 22 | 20
400000001635 | 0 | Low |  | FOCY135 | LP | DUAL_TREE | Closed in | No lift | FORCADOS YOKRI | AI req. | [5 empty] | 2019-03-09 | 2019-06-24 | Cmb_WITSIT | 2013-05-22 |  |  | 0 | 2019-03-18 | AI due date. | [6 empty] | 0 | 2019-03-09 | 192 | 154 | 144 | 12 | 2019-03-09 | 23 | 18 | 17 | 0 | 2019-03-09
400000002808 | 1 | Low |  | FOCY152 | GL | SINGLE_TREE | Flowing | Gas Lift | FORCADOS YOKRI | APM - B O/due., KWV | [5 empty] | 2019-03-04 | 2019-09-03 | Ops_WIT | 2013-05-20 |  |  | 1 | 2019-03-05 | APM - B due date. | [8 empty] | 163 | 130 | 122 | 1 | 2019-03-04 | 19 | 15 | 14 | 0 | 2019-02-03
400000002766 | 0 | Low |  | FORE017 | LP | SINGLE_TREE | Suspended | No lift | FORCADOS SOUTH WEST | Cmb_WITSIT freq. | [6 empty] | 2018-11-22 | Cmb_WITSIT |  |  |  | 0 | 2018-11-22 | Cmb_WITSIT due date |  | B annulus is cemented to surface and thus not present for management. A is unmanaged. | [6 empty] | 27
400000000889 | 6 | Low |  | KANB002 | LP | SINGLE_TREE | Closed in | No lift | KANBO | SSV | [5 empty] | 2019-01-19 | 2019-07-21 | Ops_WIT | 2014-09-02 |  |  | 1 | 2018-07-14 | SSV - Failure Due Date | [8 empty] | 114 | 91 | 85 | 0 | 2019-03-10 | 33 | 26 | 25 | 0 | 2019-03-10
400000000888 | 6 | Low |  | KANB003 | LP | DUAL_TREE | Flowing | No lift | KANBO | SSV2 | [5 empty] | 2019-02-28 | 2019-08-30 | Ops_WIT | 2014-09-02 |  |  | 4 | 2018-10-29 | SSV2 - Failure Due Date | [6 empty] | 0 | 2019-02-28 | 121 | 97 | 91 | 0 | 2019-03-10 | 89 | 71 | 67 | 0 | 2019-03-10
400000000890 | 7 | Low |  | KANB005 | LP | DUAL_TREE | Closed in | No lift | KANBO | LMV, overdue interim control action, LMV2, SSV2, FWVI | [5 empty] | 2018-10-24 | 2019-04-25 | Ops_WIT | 2014-07-01 |  | 2014-10-15 | 8 | 2017-01-14 | LMV - Failure Due Date |  | a. Carry-out surveillance of Well to monitor &amp; record annulus pressures and report same in EC and to FMT Team - Ops (Once every 2 days). b. Bleed down B-Annulus pressure in a stepwise manner. If fluid is recovered from the annulus, do not continue bleed down. c. Sample any recovered annulus effluent and send to PC lab for Geochemical Fingerprinting. d. Assign an action code in eWIMS that aligns with AF plan to repair faulty Long String SCSSSV and Christmas Tree valves. e. Carry-out a Risk Assessment and assign a Risk assessment rating based on the observed pressure in the B-Annulus (493 psig). (TR) Carryout Risk assessment and assign appropriate Risk rating. (TR) | [6 empty] | 161 | 129 | 121 | 43 | 2019-03-10 | 64 | 51 | 48 | 23 | 2019-03-10
400000002473 | 0 | Low |  | KANB009 | LP | SINGLE_TREE | Flowing | No lift | KANBO | Cmb_WITSIT freq., Ops_WIT freq. | [5 empty] | 2018-01-22 | 2016-11-25 | Cmb_WITSIT | 2014-07-01 |  |  | 0 | 2016-11-25 | Cmb_WITSIT due date |  | EDM data shows well has only A annulus | [6 empty] | 144 | 91 | 85 | 0 | 2019-03-10
400000002472 | 0 | Low |  | KANB010S1 | LP | SINGLE_TREE | Closed in | No lift | KANBO | Cmb_WITSIT freq., Ops_WIT freq. | [5 empty] | 2018-07-25 | 2018-08-25 | Cmb_WITSIT | 2014-07-01 |  |  | 0 | 2018-08-25 | Cmb_WITSIT due date |  | EDM Profile shows that the well has only A-annulus | [6 empty] | 239 | 191 | 179 | 0 | 2019-03-10
400000002409 | 0 | Medium |  | OFONI-001 | LP | SUSP_FLANGE | Suspended | No lift | OFONI | Cmb_WITSIT O/due, Missing corrosion data [SurfaceCasing] | Medium | C2 | C3 | D2 | C3 |  | 2018-11-30 | Cmb_WITSIT |  |  |  | 0 | 2018-11-30 | Cmb_WITSIT due date
400000002815 | 6 | Low |  | OGBO005 | LP | SINGLE_TREE | Flowing | No lift | OGBOTOBO | UMV | [5 empty] | 2018-10-05 | 2019-04-09 | Ops_WIT |  |  |  | 1 | 2018-12-04 | UMV - Failure Due Date | [8 empty] | 207 | 166 | 155 | 0 | 2019-03-10 | 27 | 22 | 20 | 0 | 2019-03-10
400000000843 | 0 | Low |  | OPKN001 | LP | SINGLE_TREE | Completed | No lift | OPUKUSHI NORTH | APM - B O/due., Ops_WIT O/due, Cmb_WITSIT O/due, APM - A O/due. | [5 empty] | 2018-05-06 | 2018-07-20 | Cmb_WITSIT | 2014-04-13 |  |  | 2 | 2016-06-11 | APM - B due date., APM - A due date. | [8 empty] | 133 | 106 | 100 | 0 | 2016-05-12 | 7 | 6 | 5 | 0 | 2016-05-12
400000000845 | 0 | Low |  | OPKN003 | LP | DUAL_TREE | Closed in | No lift | OPUKUSHI NORTH | Cmb_WITSIT O/due | [5 empty] | 2017-09-28 | 2018-07-20 | Cmb_WITSIT | 2014-04-13 |  |  | 0 | 2018-07-20 | Cmb_WITSIT due date | [8 empty] | 112 | 90 | 84 | 7 | 2019-03-10 | 43 | 34 | 32 | 0 | 2019-03-10
400000000847 | 2 | Low |  | OPKN021 | LP | SINGLE_TREE | Completed | No lift | OPUKUSHI NORTH | APM - B O/due., SV, PRB, APM - A O/due. | [5 empty] | 2019-01-22 | 2019-07-24 | Ops_WIT | 2014-04-13 |  | 2012-01-03 | 3 | 2018-03-24 | APM - B due date. |  | Install a retrofit to read Annulus B pressure (TR) CM could not be carried out due to lack of spares. Current plan is to replace the entire valve before expiration of deviation. OPUK021 &amp; OPKN021 are the same well. Data reconciliation process ongoing to resolve duplication in eWIMS &amp; other databases | [6 empty] | 218 | 174 | 163 | 70 | 2019-01-22 | 40 | 32 | 30 | 0 | 2018-02-22
400000000884 | 0 | Low |  | OPNO030 | LP | DUAL_TREE | Completed | No lift | OPUKUSHI | APM - A O/due., APM - B O/due. | [5 empty] | 2018-12-04 | 2019-06-05 | Ops_WIT | 2014-04-13 |  |  | 2 | 2018-05-19 | APM - A due date., APM - B due date. | [5 empty] | 0 | 0 | 2018-12-04 | 116 | 93 | 87 | 0 | 2018-04-19 | 26 | 21 | 19 | 0 | 2018-04-19
400000000905 | 7 | Medium |  | OPOM001 | LP | DUAL_TREE | Flowing | No lift | OPOMOYO | SV, Ops_WIT freq., SSV2, Cmb_WITSIT O/due, LMV, LMV2, UMV2, UMV, SV2 | Medium | B2 | C3 | D3 | D3 | 2018-05-16 | 2018-05-18 | Cmb_WITSIT | 2014-03-01 |  |  | 7 | 2016-11-06 | SV - Failure Due Date, UMV2 - Failure Due Date, UMV - Failure Due Date, SV2 - Failure Due Date | [6 empty] | 77 | 2018-05-16 | 59 | 47 | 44 | 0 | 2019-02-22 | 35 | 28 | 26 | 0 | 2019-02-22
400000000863 | 0 | Low |  | OPUK006S2 | LP | DUAL_TREE | Closed in | No lift | OPUKUSHI | APM - A O/due., APM - B O/due. | [5 empty] | 2019-01-20 | 2019-07-22 | Ops_WIT | 2014-04-13 |  | 2013-03-25 | 2 | 2018-08-08 | APM - A due date., APM - B due date. |  | Expert revoew (CR) |  |  |  |  | 0 | 2019-01-20 | 153 | 122 | 115 | 0 | 2018-07-09 | 35 | 28 | 26 | 0 | 2018-07-09
400000000864 | 4 | Low |  | OPUK007S1 | LP | DUAL_TREE | Flowing | No lift | OPUKUSHI | FWVI2 | [5 empty] | 2018-12-12 | 2019-06-13 | Ops_WIT | 2014-04-11 |  | 2012-09-20 | 1 | 2018-12-05 | FWVI2 - Failure Due Date | [6 empty] | 0 | 2018-12-12 | 122 | 98 | 91 | 0 | 2019-03-10 | 34 | 27 | 25 | 0 | 2019-03-10
400000000865 | 0 | Low |  | OPUK008 | LP | SINGLE_TREE | Closed in | No lift | OPUKUSHI | APM - A O/due., Ops_WIT freq., Cmb_WITSIT freq., APM - B O/due. | [5 empty] | 2018-08-22 | 2018-07-28 | Cmb_WITSIT | 2014-04-13 |  |  | 2 | 2016-10-20 | APM - A due date., APM - B due date. | [6 empty] | 0 | 2018-08-22 | 112 | 90 | 84 | 0 | 2016-09-20 | 31 | 25 | 23 | 0 | 2016-09-20
400000000867 | 7 | Medium |  | OPUK010 | LP | DUAL_TREE | Flowing | No lift | OPUKUSHI | SSV2, SSSV |  | C2 | C2 | C3 | C3 | 2018-12-04 | 2019-06-05 | Ops_WIT | 2014-04-11 |  |  | 2 | 2018-07-02 | SSV2 - Failure Due Date | [6 empty] | 0 | 2018-12-04 | 106 | 85 | 79 | 0 | 2019-03-10 | 18 | 14 | 13 | 0 | 2019-03-10
400000000870 | 6 | Low |  | OPUK013 | LP | DUAL_TREE | Closed in | No lift | OPUKUSHI | FWVI, SV, FWVI2 | [5 empty] | 2018-10-15 | 2019-04-19 | Ops_WIT | 2014-05-16 |  |  | 3 | 2018-12-14 | FWVI - Failure Due Date, SV - Failure Due Date, FWVI2 - Failure Due Date | [6 empty] | 0 | 2018-10-15 | 110 | 88 | 82 | 0 | 2019-03-10 | 10 | 8 | 7 | 0 | 2019-03-10
400000000873 | 0 | Low |  | OPUK016 | LP | SINGLE_TREE | Closed in | No lift | OPUKUSHI | APM - B O/due., APM - A O/due. | [5 empty] | 2019-01-20 | 2019-07-22 | Ops_WIT | 2014-04-13 |  |  | 2 | 2018-08-08 | APM - B due date., APM - A due date. | [8 empty] | 295 | 236 | 221 | 0 | 2018-07-09 | 52 | 42 | 39 | 0 | 2018-07-09
400000000874 | 0 | Low |  | OPUK017 | LP | DUAL_TREE | Closed in | No lift | OPUKUSHI | APM - B O/due. | [5 empty] | 2018-11-12 | 2019-05-14 | Ops_WIT | 2014-05-16 |  |  | 1 | 2018-05-22 | APM - B due date. | [6 empty] | 0 | 2018-11-12 | 102 | 82 | 76 | 0 | 2019-03-10 | 25 | 20 | 19 | 0 | 2018-04-22
400000000875 | 2 | Low |  | OPUK018 | LP | DUAL_TREE | Closed in | No lift | OPUKUSHI | APM - B O/due., PRB | [5 empty] | 2018-12-24 | 2019-07-06 | Ops_WIT | 2014-04-11 |  |  | 2 | 2018-04-21 | APM - B due date. |  | CWI to mobilize and carry out B annulus valves retrofit (TR) |  |  |  |  | 0 | 2018-12-24 | 118 | 94 | 88 | 0 | 2019-03-10 | 23 | 18 | 17 | 0 | 2018-03-22
400000000881 | 0 | Low |  | OPUK027 | LP | SINGLE_TREE | Closed in | No lift | OPUKUSHI | AI O/due. | [5 empty] | 2019-02-26 | 2019-08-28 | Ops_WIT | 2014-05-16 |  | 2017-11-06 | 3 | 2019-02-15 | AI due date. | [8 empty] | 104 | 83 | 78 | 0 | 2019-02-26 | 5 | 4 | 4 | 20 | 2019-03-10
400000000882 | 4 | Low |  | OPUK028S1 | LP | SINGLE_TREE | Completed | No lift | OPUKUSHI | APM - B O/due., LMV, APM - A O/due. | [5 empty] | 2019-01-22 | 2019-07-24 | Ops_WIT | 2014-04-13 |  |  | 3 | 2019-02-21 | APM - B due date., APM - A due date. | [5 empty] | 0 |  |  | 173 | 138 | 130 | 0 | 2019-01-22 | 42 | 34 | 31 | 0 | 2019-01-22
400000000883 | 4 | Low |  | OPUK029S1 | LP | SINGLE_TREE | Suspended | No lift | OPUKUSHI | LMV, overdue interim control action, FWVI, SV | [5 empty] | 2018-05-05 | 2020-07-09 | Cmb_WITSIT | 2014-04-13 |  |  | 3 | 2018-11-01 | LMV - Failure Due Date, FWVI - Failure Due Date, SV - Failure Due Date |  | Check if valves freewheeling is due to dowel pin removal (TR) Retrieve valuables from the Xmas trees and close out all failure notifications (TR) |  |  |  | 0 |  |  | 138 | 110 | 103 | 0 | 2016-05-12 | 70 | 56 | 52 | 0 | 2016-05-12
400000000886 | 6 | Low |  | OPUK033 | LP | DUAL_TREE | Closed in | No lift | OPUKUSHI | SSSV | [5 empty] | 2018-12-04 | 2019-06-05 | Ops_WIT | 2014-05-16 |  | 2012-10-12 | 1 | 2018-08-01 | SSSV - Failure Due Date | [6 empty] | 0 | 2018-12-04 | 162 | 130 | 121 | 61 | 2019-03-10 | 52 | 42 | 39 | 0 | 2019-03-10
400000000887 | 7 | Medium |  | OPUK034 | HP | SINGLE_TREE | Closed in | No lift | OPUKUSHI | FWVI, overdue interim control action, TTC, SV, SSV | [5 empty] | 2018-11-12 | 2019-05-14 | Ops_WIT | 2014-05-16 |  | 2017-11-06 | 4 | 2018-04-09 | FWVI - Failure Due Date, TTC - Failure Due Date, SV - Failure Due Date, SSV - Failure Due Date |  | EDM report of Well head maintenance prior to annulus investigation should be updated and entered. (TR) Execute well kill in 1 year and secure well pending W/O recompletion. (TR) | [6 empty] | 145 | 116 | 109 | 129 | 2019-03-10 | 96 | 77 | 72 | 0 | 2019-03-10
400000000855 | 9 | Medium |  | OPUK036 | LP | SINGLE_TREE | Flowing | No lift | OPUKUSHI | SSSV, SV, UMV | Medium | C2 | C2 | C3 | C3 | 2018-12-12 | 2019-06-13 | Ops_WIT | 2014-05-16 |  |  | 3 | 2019-03-30 | Overdue Interim Control |  | Carry Out Second Line Maintenance when spares become available. CWI – March 2019 (TR) | [6 empty] | 162 | 130 | 121 | 0 | 2019-03-10 | 25 | 20 | 19 | 0 | 2019-03-10
400000000524 | 6 | Low |  | OTUM002S1 | LP | DUAL_TREE | Flowing | No lift | OTUMARA | FWVI2, SV, LMV | [5 empty] | 2019-01-25 | 2019-07-30 | Ops_WIT | 2015-06-08 |  |  | 3 | 2019-01-23 | FWVI2 - Failure Due Date, LMV - Failure Due Date | [8 empty] | 132 | 106 | 99 | 59 | 2019-02-16 | 47 | 38 | 35 | 0 | 2019-02-16
400000000527 | 0 | Low |  | OTUM006 | LP | DUAL_TREE | Closed in | No lift | OTUMARA | Cmb_WITSIT O/due | [5 empty] | 2018-05-21 | 2019-02-10 | Cmb_WITSIT | 2015-05-19 |  |  | 0 | 2019-02-10 | Cmb_WITSIT due date | [8 empty] | 199 | 159 | 149 | 0 | 2019-02-16 | 35 | 28 | 26 | 0 | 2019-02-16
400000000529 | 5 | Low |  | OTUM008 | GL | DUAL_TREE | Flowing | Gas Lift | OTUMARA | SSV2, SV2 | [5 empty] | 2019-01-21 | 2019-08-03 | Ops_WIT | 2015-06-08 |  |  | 2 | 2018-10-16 | SSV2 - Failure Due Date | [8 empty] | 93 | 74 | 70 | 60 | 2019-02-16 | 25 | 20 | 19 | 0 | 2019-02-16
400000000530 | 3 | Low |  | OTUM009 | GL | SINGLE_TREE | Flowing | Gas Lift | OTUMARA | LMV, SV | [5 empty] | 2018-08-12 | 2019-04-29 | Cmb_WITSIT | 2015-05-27 |  |  | 2 | 2019-04-29 | Cmb_WITSIT due date | [8 empty] | 118 | 94 | 88 | 64 | 2019-02-16 | 24 | 19 | 18 | 0 | 2019-02-16
400000000531 | 1 | Low |  | OTUM010 | GL | DUAL_TREE | Flowing | Gas Lift | OTUMARA | SV2, SV | [5 empty] | 2018-07-23 | 2019-04-08 | Cmb_WITSIT | 2015-05-19 |  |  | 1 | 2019-04-08 | Cmb_WITSIT due date |  | Repair SVs (TR) • CWI to carry out Second Line Maintenance. • Retain action code 1 (TR) | [6 empty] | 150 | 120 | 112 | 64 | 2019-02-16 | 27 | 22 | 20 | 0 | 2019-02-16
400000000532 | 6 | Low |  | OTUM011 | LP | SINGLE_TREE | Closed in | No lift | OTUMARA | CTRL | [5 empty] | 2018-11-26 | 2019-06-09 | Ops_WIT | 2015-06-01 |  |  | 1 | 2018-08-07 | CTRL - Failure Due Date |  | • CWI to carry out Second Line Maintenance. (Flush the CTRL or install PBV) • Change action code to 6. (TR) | [6 empty] | 163 | 130 | 122 | 41 | 2019-02-16 | 17 | 14 | 13 | 0 | 2019-02-16
400000000533 | 7 | Low |  | OTUM012 | GL | DUAL_TREE | Flowing | Gas Lift | OTUMARA | UMV, SV2, LMV | [5 empty] | 2019-02-16 | 2019-08-06 | Cmb_WITSIT | 2015-06-08 |  |  | 2 | 2018-09-06 | UMV - Failure Due Date, LMV - Failure Due Date | [8 empty] | 175 | 140 | 131 | 35 | 2019-02-16 | 11 | 9 | 8 | 0 | 2019-02-16
400000000535 | 1 | Low |  | OTUM014 | LP | SINGLE_TREE | Completed | No lift | OTUMARA | SV | [5 empty] | 2018-08-07 | 2019-04-22 | Cmb_WITSIT | 2015-06-08 |  |  | 0 | 2019-04-22 | Cmb_WITSIT due date | [8 empty] | 245 | 196 | 184 | 1 | 2019-02-16 | 9 | 7 | 7 | 0 | 2019-02-16
400000000536 | 4 | Low |  | OTUM015 | GL | DUAL_TREE | Closed in | Gas Lift | OTUMARA | BPF | [5 empty] | 2018-11-26 | 2019-05-28 | Ops_WIT | 2015-06-01 |  | 2019-01-22 | 2 | 2019-04-30 | AI due date. |  | CWI to carry out investigation of the HCHP and repair the leak source. Change to action code 4 (TR) | [6 empty] | 204 | 163 | 153 | 64 | 2019-02-16 | 7 | 6 | 5 | 52 | 2019-02-16
400000000537 | 0 | Low |  | OTUM016 | GL | SINGLE_TREE | Flowing | Gas Lift | OTUMARA | [6 empty] | 2018-07-10 | 2019-03-25 | Cmb_WITSIT | 2015-06-01 |  |  | 1 | 2019-03-25 | Cmb_WITSIT due date | [8 empty] | 207 | 166 | 155 | 62 | 2019-03-06 | 2 | 2 | 1 | 0 | 2019-03-06
400000000538 | 0 | Low |  | OTUM017 | LP | SINGLE_TREE | Flowing | No lift | OTUMARA | [6 empty] | 2018-07-10 | 2019-03-25 | Cmb_WITSIT | 2015-06-01 |  |  | 1 | 2019-03-25 | Cmb_WITSIT due date | [8 empty] | 201 | 161 | 151 | 50 | 2019-03-06 | 4 | 3 | 3 | 0 | 2019-03-06
400000000539 | 3 | Low |  | OTUM018 | GL | SINGLE_TREE | Flowing | Gas Lift | OTUMARA | SSSV | [5 empty] | 2018-08-06 | 2019-04-22 | Cmb_WITSIT | 2015-06-08 |  |  | 2 | 2019-04-22 | Cmb_WITSIT due date | [8 empty] | 198 | 158 | 148 | 63 | 2019-03-06 | 1 | 1 | 1 | 0 | 2019-03-06
400000000542 | 6 | Low |  | OTUM021 | LP | DUAL_TREE | Closed in | No lift | OTUMARA | CTRL, CTRL2, SSSV2, SV, SSV, FWVI, overdue interim control action | [5 empty] | 2019-01-31 | 2019-07-24 | Cmb_WITSIT | 2015-05-26 |  |  | 6 | 2017-09-19 | CTRL - Failure Due Date |  | • Prepare a securing proposal to secure the Long string with downhole plug. • CWI already in Otumara for intervention and maintenance activities. CWI to carry out Second Line Maintenance. • Change action code to 6. (TR) CWI to carry out SLM and repair all failed valves and change out downhole safety valves for both strings. (TR) |  |  |  |  | 0 | 2019-01-31 | 195 | 156 | 146 | 74 | 2019-02-16 | 10 | 8 | 7 | 0 | 2019-02-16
400000000547 | 1 | Low |  | OTUM028 | LP | DUAL_TREE | Closed in | No lift | OTUMARA | SV | [5 empty] | 2019-02-18 | 2019-07-24 | Cmb_WITSIT | 2015-05-26 |  |  | 0 | 2019-03-21 | B Annulus approaching deadline., A Annulus approaching deadline. | [6 empty] | 0 | 2019-02-18 | 172 | 138 | 129 | 63 | 2019-02-18 | 5 | 4 | 4 | 0 | 2019-02-18
400000000549 | 5 | Low |  | OTUM030 | GL | DUAL_TREE | Flowing | Gas Lift | OTUMARA | SSV2, SV2, CTRL, SSV | [5 empty] | 2018-08-29 | 2019-05-31 | Cmb_WITSIT | 2015-05-06 |  |  | 4 | 2018-11-27 | SSV2 - Failure Due Date |  | • Change action code to 5 and plan to secure well • CWI to investigate Control line failure and prepare to go with SCSSV during the planned SLM activity in Q2 2019. (TR) |  |  |  |  | 15 | 2019-02-20 | 172 | 138 | 129 | 64 | 2019-02-20 | 42 | 34 | 31 | 0 | 2019-02-20
400000000551 | 6 | Low |  | OTUM032 | LP | DUAL_TREE | Closed in | No lift | OTUMARA | CTRL2 | [5 empty] | 2018-12-27 | 2019-08-06 | Cmb_WITSIT | 2015-06-08 |  |  | 1 | 2019-02-25 | CTRL2 - Failure Due Date |  | • Change action code to 6 based on WFM recommendation • CWI to carry out Second Line Maintenance and change downhole safety valve. • And finally, secure with downhole plugs (TR) | [6 empty] | 133 | 106 | 100 | 0 | 2019-02-16 | 33 | 26 | 25 | 0 | 2019-02-16
400000000554 | 7 | Low |  | OTUM035 | LP | DUAL_TREE | Flowing | No lift | OTUMARA | APM - B O/due., SSV, SSV2 | [5 empty] | 2019-02-16 | 2019-08-06 | Cmb_WITSIT | 2015-06-08 |  |  | 3 | 2018-03-09 | APM - B due date. | [8 empty] | 205 | 164 | 154 | 50 | 2019-02-16 | 13 | 10 | 10 | 0 | 2018-02-07
400000000555 | 6 | Low |  | OTUM036 | LP | DUAL_TREE | Flowing | No lift | OTUMARA | SSV | [5 empty] | 2019-01-21 | 2019-07-19 | Cmb_WITSIT | 2015-05-19 |  |  | 1 | 2018-09-16 | SSV - Failure Due Date | [8 empty] | 197 | 158 | 148 | 7 | 2019-02-16 | 11 | 9 | 8 | 0 | 2019-02-16
400000000556 | 3 | Low |  | OTUM037 | GL | DUAL_TREE | Closed in | Gas Lift | OTUMARA | SSV | [5 empty] | 2018-10-13 | 2019-04-14 | Ops_WIT | 2015-05-19 |  |  | 1 | 2019-03-13 | SSV - Failure Due Date | [8 empty] | 197 | 158 | 148 | 64 | 2019-02-16 | 26 | 21 | 19 | 0 | 2019-02-16
400000000557 | 9 | Medium |  | OTUM038 | LP | DUAL_TREE | Flowing | No lift | OTUMARA | APM - B O/due., SSV2, SSSV2, LMV | Medium | B2 | C2 | C4 | C3 | 2018-08-29 | 2019-05-14 | Cmb_WITSIT | 2015-05-04 |  |  | 4 | 2017-08-15 | APM - B due date. | [8 empty] | 187 | 150 | 140 | 6 | 2019-02-16 | 25 | 20 | 19 | 0 | 2017-07-16
400000000558 | 7 | Low |  | OTUM039 | LP | DUAL_TREE | Closed in | No lift | OTUMARA | SSV2 | [5 empty] | 2018-08-29 | 2019-05-30 | Cmb_WITSIT | 2015-06-08 |  |  | 1 | 2018-09-28 | SSV2 - Failure Due Date | [6 empty] | 8 | 2019-02-20 | 200 | 160 | 150 | 2 | 2019-02-20 | 15 | 12 | 11 | 0 | 2019-02-20
400000000559 | 6 | Low |  | OTUM040 | LP | SINGLE_TREE | Flowing | No lift | OTUMARA | SSV | [5 empty] | 2018-12-29 | 2019-07-18 | Ops_WIT | 2015-05-19 |  | 2014-11-20 | 1 | 2019-02-27 | SSV - Failure Due Date | [8 empty] | 197 | 158 | 148 | 66 | 2019-02-16 | 11 | 9 | 8 | 10 | 2019-02-16
400000000562 | 3 | Low |  | OTUM043 | GL | DUAL_TREE | Closed in | Gas Lift | OTUMARA | APM - B O/due., CTRL, SSV | [5 empty] | 2018-10-05 | 2019-04-06 | Ops_WIT | 2015-04-29 |  |  | 3 | 2017-08-03 | APM - B due date. |  | • CWI to carry out Second Line Maintenance. • Change action code to 3. (TR) | [6 empty] | 197 | 158 | 148 | 63 | 2019-02-16 | 10 | 8 | 7 | 0 | 2017-07-04
400000000564 | 0 | Low |  | OTUM045 | LP | DUAL_TREE | Closed in | No lift | OTUMARA | APM - B O/due. | [5 empty] | 2019-03-12 | 2019-06-29 | Cmb_WITSIT | 2015-06-08 |  |  | 1 | 2017-09-15 | APM - B due date. |  | EDM Profile shows that the production casing is cemented to surface. |  |  |  | 0 | 0 | 2019-03-12 | 194 | 155 | 145 | 130 | 2019-03-12 | 16 | 13 | 12 | 0 | 2017-08-16
400000000565 | 0 | Low |  | OTUM046 | LP | DUAL_TREE | Flowing | No lift | OTUMARA | Ops_WIT freq. | [5 empty] | 2018-09-10 | 2019-03-12 | Ops_WIT | 2015-06-08 |  |  | 0 | 2019-03-12 | Ops_WIT due date |  | EDM Profile shows Intermediate casing is cemented to surface | [6 empty] | 131 | 105 | 98 | 0 | 2019-02-16
400000000567 | 6 | Low |  | OTUM048S1 | LP | SINGLE_TREE | Closed in | No lift | OTUMARA | UMV | [5 empty] | 2019-02-18 | 2019-08-20 | Ops_WIT | 2015-06-08 |  |  | 1 | 2019-03-21 | A Annulus approaching deadline. | [8 empty] | 162 | 130 | 121 | 0 | 2019-02-18 |  | 0 | 0 | 0 | 2015-10-01
400000000569 | 6 | Low |  | OTUM050S1 | LP | SINGLE_TREE | Flowing | No lift | OTUMARA | SSV, UMV, APM - B O/due. | [5 empty] | 2018-11-08 | 2019-05-26 | Ops_WIT | 2015-06-08 |  |  | 3 | 2017-08-13 | SSV - Failure Due Date | [8 empty] | 216 | 173 | 162 | 62 | 2019-02-16 | 1 | 1 | 1 | 0 | 2018-05-25
400000000570 | 6 | Low |  | OTUM051 | LP | SINGLE_TREE | Closed in | No lift | OTUMARA | SSV | [5 empty] | 2018-08-06 | 2019-04-22 | Cmb_WITSIT | 2015-05-22 |  |  | 1 | 2018-05-01 | SSV - Failure Due Date | [8 empty] | 199 | 159 | 149 | 17 | 2019-02-16
400000000572 | 6 | Low |  | OTUM053 | LP | SINGLE_TREE | Flowing | No lift | OTUMARA | SSV, Cmb_WITSIT O/due | [5 empty] | 2018-03-06 | 2018-12-19 | Cmb_WITSIT | 2015-05-27 |  |  | 1 | 2018-05-05 | SSV - Failure Due Date | [8 empty] | 168 | 134 | 126 | 1 | 2019-02-16
400000000573 | 6 | Low |  | OTUM054 | LP | SINGLE_TREE | Flowing | No lift | OTUMARA | SSV | [5 empty] | 2018-08-06 | 2019-04-22 | Cmb_WITSIT | 2015-06-01 |  |  | 1 | 2018-05-04 | SSV - Failure Due Date | [8 empty] | 163 | 130 | 122 | 56 | 2019-02-16
400000000575 | 6 | Low |  | OTUM056 | LP | SINGLE_TREE | Closed in | No lift | OTUMARA | CTRL, overdue interim control action | [5 empty] | 2018-11-01 | 2019-05-19 | Ops_WIT | 2015-07-15 |  |  | 1 | 2017-09-26 | CTRL - Failure Due Date |  | CWI to carry out Second Line Maintenance. • Change action code to 6. • Prepare a securing proposal to secure the Long string with downhole plug. (TR) | [6 empty] | 123 | 98 | 92 | 3 | 2019-02-16 | 7 | 6 | 5 | 0 | 2019-02-16
400000000822 | 7 | Low |  | SAGR002 | LP | DUAL_TREE | Closed in | No lift | SAGHARA | UMV2 | [5 empty] | 2018-11-01 | 2019-06-04 | Ops_WIT | 2014-04-02 |  | 2013-11-19 | 1 | 2018-12-01 | UMV2 - Failure Due Date | [8 empty] | 166 | 133 | 124 | 22 | 2019-02-16 | 19 | 15 | 14 | 0 | 2019-02-16
400000000823 | 7 | Low |  | SAGR003 | LP | DUAL_TREE | Closed in | No lift | SAGHARA | SSV2, SV2, UMV2, SSV | [5 empty] | 2018-10-30 | 2019-04-30 | Ops_WIT | 2014-04-01 |  |  | 4 | 2018-11-29 | SSV2 - Failure Due Date, UMV2 - Failure Due Date, SSV - Failure Due Date | [8 empty] | 237 | 190 | 178 | 17 | 2019-02-16 | 4 | 3 | 3 | 0 | 2019-02-16
400000000824 | 9 | High | Yes | SAGR005 | LP | DUAL_TREE | Closed in | No lift | SAGHARA | SSV, SSSV, LMV, SSV2, SV, SSSV2 | High | B5 | C2 | C3 | C3 | 2018-10-29 | 2019-04-29 | Ops_WIT | 2014-04-01 |  |  | 6 | 2019-04-29 | Ops_WIT due date | [8 empty] | 204 | 163 | 153 | 0 | 2019-02-16 | 6 | 5 | 4 | 0 | 2019-02-16
400000000893 | 6 | Medium |  | TUNU001 | LP | DUAL_TREE | Closed in | No lift | TUNU | SSV, SSV2 |  | C2 | C2 | C3 | C3 | 2018-10-24 | 2019-04-26 | Ops_WIT | 2014-07-02 |  |  | 2 | 2018-06-25 | SSV - Failure Due Date, SSV2 - Failure Due Date | [8 empty] | 66 | 53 | 49 | 0 | 2019-03-10 | 59 | 47 | 44 | 0 | 2019-03-10
400000000895 | 7 | Low |  | TUNU003 | LP | SINGLE_TREE | Closed in | No lift | TUNU | SSV, overdue interim control action, SV, LMV, UMV, CTRL | [5 empty] | 2018-10-04 | 2019-04-05 | Ops_WIT | 2014-07-02 |  |  | 5 | 2017-05-22 | SSV - Failure Due Date |  | a. Check if Well has NRV installed. PT b. Confirm the scheduled date for Corrective Maintenance and assign an Action Code in eWIMS to align with same date. PT Well Integrity Focal Point c. Carry out SLM to repair the reported failures and restore the Well’s integrity. (TR) Carry out SLM to repair the reported failure and restore normalcy. (TR) Check if NRV is installed in Well. (TR) | [6 empty] | 110 | 88 | 82 | 0 | 2019-03-10 | 56 | 45 | 42 | 0 | 2019-02-22
400000000896 | 9 | High | Yes | TUNU004 | HP | DUAL_TREE | Flowing | No lift | TUNU | Cmb_WITSIT freq., ARGV, APM - B Dev., APT | High | E4 | E0 | E3 | E3 | 2019-03-05 | 2018-08-25 | Cmb_WITSIT | 2014-07-02 |  |  | 3 | 2018-08-25 | Cmb_WITSIT due date | [6 empty] | 0 | 2019-03-05 | 142 | 114 | 106 | 93 | 2019-03-10 | 83 | 66 | 62 | 0 | 2019-01-06
400000000898 | 4 | Low |  | TUNU006 | LP | SINGLE_TREE | Closed in | No lift | TUNU | FWVI | [5 empty] | 2019-01-18 | 2019-07-20 | Ops_WIT | 2014-07-02 |  |  | 1 | 2019-01-08 | FWVI - Failure Due Date | [8 empty] | 162 | 130 | 121 | 65 | 2019-03-10 | 91 | 73 | 68 | 0 | 2019-03-10
400000001616 | 6 | Low |  | TUNU009 | LP | SINGLE_TREE | Closed in | No lift | TUNU | SSV |  | C2 | C2 | C2 | C2 | 2018-10-24 | 2019-04-25 | Ops_WIT | 2014-07-02 |  |  | 1 | 2018-06-24 | SSV - Failure Due Date |  | B does not have B annulus | [6 empty] | 190 | 152 | 142 | 0 | 2019-03-10
400000001618 | 6 | Low |  | TUNU011S1 | LP | SINGLE_TREE | Flowing | No lift | TUNU | SSV, APM - B O/due. | [5 empty] | 2018-10-24 | 2019-04-26 | Ops_WIT | 2014-06-30 |  |  | 2 | 2018-06-25 | SSV - Failure Due Date | [8 empty] | 140 | 112 | 105 | 0 | 2019-03-10 | 6 | 5 | 4 | 0 | 2018-08-10
400000000901 | 6 | Low |  | TUNU013S1 | LP | DUAL_TREE | Closed in | No lift | TUNU | SSV | [5 empty] | 2018-10-24 | 2019-04-26 | Ops_WIT | 2014-07-02 |  |  | 1 | 2018-06-25 | SSV - Failure Due Date | [8 empty] | 128 | 102 | 96 | 0 | 2019-03-10 | 9 | 7 | 7 | 0 | 2019-03-10

## ESCB005_007
General | [7 empty] | Risk Assessment
UWI | Action Code | Name | WFM Type | WFM Configuration | Production Status | Field | Reasons | Deviation Class | People | Asset | Community | Environment | Deviation Group | Remark/General Comments | Mitigating Actions and General Comments | Action Party | Expected Closure Date | Attendees
400000000699 | 0 | AFRE004 | LP | DUAL_TREE | Flowing | AFREMO | APM - B O/due. | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is producing. * B annulus APM is overdue and not managed. Annulus B point is inaccessible due to no lower deck platform constructed within the wellhead * It is protected by an instrusive cage * AFRE004 is in an offshore location. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Outstanding B annulus APM pressure data is managed by regular surveillance to the wellhead location. 3) Well is flowing with functional and tested ScSSSV on auto. 4) A protective instrusive cage is installed on the XMAS Tree. 5) Retrofit is to be installed to facilitate the acquisition of B annulus pressure data. 6) Well has XMAS Tree valves tested and integral. | 2) Production Operations: Akinro, Udoh. Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000703 | 6 | AFRE008 | LP | DUAL_TREE | Closed in | AFREMO | SSV, APM - B O/due., SSV2 | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is closed in, flushed based on performance of AFRE014,& 010 completed more crestal on the structure and produced much longer at HBSW post closure of AFRE008L/Sand and not capable of natural flow. * Well has SSV failures and APM B is not managed because it has no lower deck platform constructed within the wellhead * Well is on a platform in an offshore location * Well is not protected by an intrusive cage | 1) Well has other XMAS Tree valves tested and integral 2) Failure is managed by regular surveillance to the wellhead location 3) Well is tripped closed with tested and integral ScSSSV 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) A retrofit will be installed to aid the acquisition of B annulus pressure data. 6) Well securing proposal is to be prepared and CWI are to mobilize and secure well with downhole plugs. | 2) Production Operations: Akinro, Udoh, Oyebode & Usin 4) Production Operations: Akinro, Udoh, Oyebode & Usin 5) CWI: Onuoha Chinedu 6) VDM PT & CWI: Somtochukwu Odumodu & Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000720 | 6 | AFRE009 | LP | DUAL_TREE | Closed in | AFREMO | CTRL2, CTRL | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is currently closed. * Well has control line failure. * It is not protected by an instrusive cage * AFRE009 is in an offshore location. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) There is a plan to sign off a securing proposal and thereafter secure the well. 4) A protective instrusive cage is to be installed on the XMAS Tree until the well is secured. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2 & 4) Production Operations: Oyebode & Usin 3) PT & CWI: Somtochukwu Odumodu & Chinedu Onuoha 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000705 | 7 | AFRE011 | LP | DUAL_TREE | Closed in | AFREMO | LMV, SSV, SSV2, LMV2 | Medium (HiPo) | P=C3 | A=C3 | C=C4 | E=C4 | P=C3A=C3C=C4E=C4 | * Well is closed in (both strings perforation intervals are flushed). * Well has Master Valve and SSV failures. * It is not protected by an intrusive cage, * AFRE011 is situated in an offshore location. | 1) Well has tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location 3) There is plan to repair failed valves 4) There is a plan to generate securing proposals and thereafter for CWI to secure the well (both intervals). | 2) Production Operations: Akinro, Udoh. Oyebode & Usin 3 & 5B) CWI: Onuoha Chinedu 5A) PT: Somtochukwu Odumodu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000717 | 6 | ESCB001 | LP | DUAL_TREE | Flowing | ESCRAVOS BEACH | LMV, SV2, SV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is prodcuing * Well has MV, SV failures. * It is not protected by an instrusive cage * ESCB001 is in an amphibious location. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Valves failure is managed by regular surveillance to the wellhead location. 3) Well is flowing with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Well has XMAS Tree valves tested and integral. 6) There is a plan to repair the failed master valves. | 2) Production Operations: Oyebode & Usin 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000719 | 6 | ESCB003 | LP | SINGLE_TREE | Closed in | ESCRAVOS BEACH | SV, LMV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is closed in. (But there is a plan to restorfe production via STOG activity) * * Well has MV, SV failures. * It is not protected by an instrusive cage * ESCB003 is in an amphibious location. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Valves failure is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Well has XMAS Tree valves tested and integral. 6)There is a plan to repair the failed master valves. | 2 & 4) Production Operations: Oyebode & Usin 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000709 | 0 | ESCB005 | LP | DUAL_TREE | Closed in | ESCRAVOS BEACH | Cmb_WITSIT freq., Ops_WIT freq., APM - A O/due., APM - B O/due. | Medium (HiPo) | P=C3 | A=C3 | C=C4 | E=C4 | P=C3A=C3C=C4E=C4 | * Well is closed in and secured with NRV. (Both Strings) * A&B annulus APM are overdue and not managed because the measurement points are not accessible. The XMAS Tree was dynamited in 2015. * Regular visits around the well location indicated no external leaks or spills which suggests that the installed NRVs are still intact. * ESCB005 is in an amphibous location (Land) and not close to nearby settlement. | 1) They are closed in and secured with NRV. 2) There is a plan abandon the well. Well abandonment proposal generation is ongoing. 3) Outstanding B annulus APM pressure data is managed by regular surveillance to the wellhead location. 4) There is a -plan to visit the well for CMB WIT/SIT. | 2) PT & CWI: Somtochukwu Odumodu & Chinedu Onuoha 3) Production Operations: Oyebode & Usin 4) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000711 | 0 | ESCB007 | LP | DUAL_TREE | Closed in | ESCRAVOS BEACH | APM - A O/due., Ops_WIT O/due, Cmb_WITSIT O/due, APM - B O/due. | Medium (HiPo) | P=C3 | A=C3 | C=C4 | E=C4 | P=C3A=C3C=C4E=C4 | * Well is closed in and secured with NRV. (Both Strings) * A&B annulus APM are overdue and not managed because the measurement points are not accessible. The XMAS Tree was dynamited in 2015. * Regular visits around the well location indicated no external leaks or spills which suggests that the installed NRVs are still intact. * ESCB007 is in an amphibous location (Land) and not close to nearby settlement. * ESCB007 existing perforation intervals are considered flushed. | 1) They are closed in and secured with NRV. 2) There is a plan abandon the well. Well abandonment proposal generation is ongoing. 3) Outstanding B annulus APM pressure data is managed by regular surveillance to the wellhead location. 4) There is a -plan to visit the well for CMB WIT/SIT. | 2) PT & CWI: Somtochukwu Odumodu & Chinedu Onuoha 3) Production Operations: Oyebode & Usin 4) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000524 | 6 | OTUM002S1 | LP | DUAL_TREE | Flowing | OTUMARA | FWVI2, SV, LMV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is a producing well. * Well has MV, SV & FWV failures. * It is protected by an instrusive cage * OTUM002 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Valves failure is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) There is a plan to repair the failed master valves. | 2) Production Operations: Oyebode & Usin 4) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000529 | 5 | OTUM008 | GL | DUAL_TREE | Flowing | OTUMARA | SSV2, SV2 | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is producing (Both Strings) * Well has SSV & SV failures. * It is protected by an instrusive cage * OTUM008 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is installed on the XMAS Tree. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000530 | 3 | OTUM009 | GL | SINGLE_TREE | Flowing | OTUMARA | LMV, SV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is flowing. * Well has MV, SV failures. * It is not protected by an instrusive cage * OTUM009 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Valves failure is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Well has XMAS Tree valves tested and integral. 6) There is a plan to repair the failed master valves. | 2 & 4) Production Operations: Oyebode & Usin 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000532 | 6 | OTUM011 | LP | SINGLE_TREE | Closed in | OTUMARA | CTRL | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is currently closed. * Well has control line failure. * It is not protected by an instrusive cage * OTUM011 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) There is a plan to sign off a securing proposal and thereafter secure the well. 4) A protective instrusive cage is to be installed on the XMAS Tree until the well is secured. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2 & 4) Production Operations: Oyebode & Usin 3) PT & CWI: Somtochukwu Odumodu & Chinedu Onuoha 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000533 | 7 | OTUM012 | GL | DUAL_TREE | Flowing | OTUMARA | UMV, SV2, LMV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is producing. * Well has MV, SV failures * It is not protected by an instrusive cage * OTUM012 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Valves failure is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Well has XMAS Tree valves tested and integral. 6) There is a plan to repair the failed master valves. | 2 & 4) Production Operations: Oyebode & Usin 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000536 | 4 | OTUM015 | GL | DUAL_TREE | Closed in | OTUMARA | BPF | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is closed in. * It have B annulus pressure MAASP excursion. * It is not protected by an instrusive cage * OTUM015 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) HCHP (B annulus) is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Well has XMAS Tree valves tested and integral. 6) There is a plan to fix the HCHP post investigation. | 2 & 4) Production Operations: Oyebode & Usin 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000537 | 0 | OTUM016 | GL | SINGLE_TREE | Flowing | OTUMARA | Cmb_WITSIT due date | Low | P=B2 | A=B2 | C=B3 | E=B3 | P=B2A=B2C=B3E=B3 | * Well is producing. * Well has outstanding CMB WIT/SIT * It is not protected by an instrusive cage * OTUM016 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Outstanding CMB WIT/SIT is managed by regular surveillance to the wellhead location and OPS WIT. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000538 | 0 | OTUM017 | LP | SINGLE_TREE | Flowing | OTUMARA | Cmb_WITSIT due date | Low | P=B2 | A=B2 | C=B3 | E=B3 | P=B2A=B2C=B3E=B3 | * Well is producing. * Well has outstanding CMB WIT/SIT * It is not protected by an instrusive cage * OTUM016 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Outstanding CMB WIT/SIT is managed by regular surveillance to the wellhead location and OPS WIT. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000539 | 3 | OTUM018 | GL | SINGLE_TREE | Flowing | OTUMARA | SSSV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is producing * Well has SCSSSV failure. * It is not protected by an instrusive cage * OTUM018 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Valve failure is managed by regular surveillance to the wellhead location. 3) A protective instrusive cage is to be installed on the XMAS Tree. 4) Well has XMAS Tree valves tested and integral. 5) There is a plan to repair the failed master valves. | 2 & 4) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000542 | 6 | OTUM021 | LP | DUAL_TREE | Closed in | OTUMARA | CTRL, CTRL2, SSSV2, SV, SSV, FWVI, overdue interim control action | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is closed in. * Well has SCSSV, CTRL, FWV, SSV SV failures. * It is not protected by an instrusive cage * OTUM021 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Valves failure is managed by regular surveillance to the wellhead location. 3) A protective instrusive cage is to be installed on the XMAS Tree. 4) Well has MV tested and integral. 5) There is a plan to repair the failed master valves. | 2 & 4) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000549 | 5 | OTUM030 | GL | DUAL_TREE | Flowing | OTUMARA | SSV2, SV2, CTRL, SSV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is producing. *Well has SSV, control line & SV failures. * It is not protected by an instrusive cage * OTUM030 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Valves failure is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Well has XMAS Tree valves tested and integral. 6) There is a plan to repair the failed master valves. | 2) Production Operations: Oyebode & Usin 5 & 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000551 | 6 | OTUM032 | LP | DUAL_TREE | Closed in | OTUMARA | CTRL2 | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is currently closed. * Well has control line failure. * It is not protected by an instrusive cage * OTUM032 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) There is a plan to sign off a securing proposal and thereafter secure the well. 4) A protective instrusive cage is to be installed on the XMAS Tree until the well is secured. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2 & 4) Production Operations: Oyebode & Usin 3) PT & CWI: Somtochukwu Odumodu & Chinedu Onuoha 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000554 | 7 | OTUM035 | LP | DUAL_TREE | Flowing | OTUMARA | APM - B O/due., SSV, SSV2 | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is producing (Both Strings) * Well has SSV failures. (Both Strings) * It is protected by an instrusive cage * OTUM035 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failures and outstanding B annulus APM pressure data are managed by regular surveillance to the wellhead location. 3) Well is flowing with functional and tested ScSSSV on auto. 4) A protective instrusive cage is installed on the XMAS Tree. 5) Retrofit is to be installed to facilitate the acquisition of B annulus pressure data. 6) Well has XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000555 | 6 | OTUM036 | LP | DUAL_TREE | Flowing | OTUMARA | SSV | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is producing (Long String) * Well has SSV failure. (Long String) * It is protected by an instrusive cage * OTUM036 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is installed on the XMAS Tree. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000556 | 3 | OTUM037 | GL | DUAL_TREE | Closed in | OTUMARA | SSV | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is currently closed in (Both String) but the two interval have planned restoration activities. OTUM037S is STOG activity will be executed in Q2 2019. * Well has SSV failure. (Long String) * It is protected by an instrusive cage * OTUM037 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is installed on the XMAS Tree. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000557 | 9 | OTUM038 | LP | DUAL_TREE | Flowing | OTUMARA | APM - B O/due., SSV2, SSSV2, LMV | Medium (HiPo) | P=C3 | A=C3 | C=C4 | E=C4 | P=C3A=C3C=C4E=C4 | * Well is producing. * B annulus APM is overdue and not managed. Annulus B point is inaccessible due to no lower deck platform constructed within the wellhead * Well has SSV, MV & SCSSSV failures * It is not protected by an instrusive cage * OTUM038 is located in the Swamp and about 50m - 100m away from nearby settlement. | 1) There is an immediate plan to close in the well due to the high action code. 2) Outstanding B annulus APM pressure data and the valves failures is managed by regular surveillance to the wellhead location. 3) There is low history of vandalization is the location 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Retrofit is to be installed to facilitate the acquisition of B annulus pressure data. 6) There is a plan to go and repair the failed valves. | 1) PT and Production operations: Somtochukwu Odumodu, Usin & Oyebode 2 & 3) Production Operations: Oyebode & Usin 5 & 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000558 | 7 | OTUM039 | LP | DUAL_TREE | Flowing | OTUMARA | SSV2 | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is producing (Long String) but the producing string has no failure * Well has SSV failure. (Short String) * It is protected by an instrusive cage * OTUM039 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is installed on the XMAS Tree. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000559 | 6 | OTUM040 | LP | SINGLE_TREE | Flowing | OTUMARA | SSV | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is producing * Well has SSV failure. (Short String) * It is protected by an instrusive cage * OTUM040 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is installed on the XMAS Tree. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2) Production Operations: Akinro, Udoh, Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000562 | 3 | OTUM043 | GL | DUAL_TREE | Flowing | OTUMARA | APM - B O/due., CTRL, SSV | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is producing (Short String) * Well has SSV & Control line failure. (Long String). APM B is not managed because it has no lower deck platform constructed within the wellhead * It is not protected by an instrusive cage * OTUM040 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) A protective instrusive cage is to be installed on the XMAS Tree. 4) A retrofit will be installed to aid the acquisition of B annulus pressure data. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2 & 3) Production Operations: Oyebode & Usin 4 & 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000564 | 0 | OTUM045 | LP | DUAL_TREE | Closed in | OTUMARA | APM - B O/due. | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is closed in. (Both Strings) * B annulus APM is overdue and not managed. Annulus B point is inaccessible due to no lower deck platform constructed within the wellhead * It is not protected by an instrusive cage * OTUM045 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Outstanding B annulus APM pressure data is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Retrofit is to be installed to facilitate the acquisition of B annulus pressure data. 6) Well has XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000565 | 9 | OTUM046 | LP | DUAL_TREE | Flowing | OTUMARA | SSV2, CTRL, LMV2, FWV12, SSSV2, SSV, UMV2 | Medium (HiPo) | P=C3 | A=C3 | C=C4 | E=C4 | P=C3A=C3C=C4E=C4 | * Well is producing. (Short String) * Well has SSV, MV, SSV, FWV & SCSSSV failures. * It is not protected by an instrusive cage * OTUM038 is located in the Swamp and about 50m - 100m away from nearby settlement. | 1) There is an immediate plan to close in the well due to the high action code. 2) Valves failures is managed by regular surveillance to the wellhead location. 3) There is low history of vandalization is the location 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Retrofit is to be installed to facilitate the acquisition of B annulus pressure data. 6) There is a plan to go and repair the failed valves. | 1) PT and Production operations: Somtochukwu Odumodu, Usin & Oyebode 2 & 3) Production Operations: Oyebode & Usin 5 & 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000567 | 6 | OTUM048S1 | LP | SINGLE_TREE | Closed in | OTUMARA | UMV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is currently closed. (But here is a plan to restore production via STOG activity in 2019). * Well has master valve (MV) failure. * It is not protected by an instrusive cage * OTUM048 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) A protective instrusive cage is to be installed on the XMAS Tree. 4) There is a plan to repair the failed valves. 5) Well has other XMAS Tree valves tested and integral. | 2 & 3) Production Operations: Oyebode & Usin 4) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000569 | 6 | OTUM050S1 | LP | SINGLE_TREE | Flowing | OTUMARA | SSV, UMV, APM - B O/due. | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is producing. * Well has MV, SSV failures and Overdue B annulus APM * It is not protected by an instrusive cage * OTUM050 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Outstanding B annulus APM pressure data and valves failure is managed by regular surveillance to the wellhead location. 3) Well is producing with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Well has XMAS Tree valves tested and integral. 6) There is a plan to repair the failed master valves. | 2 & 4) Production Operations: Oyebode & Usin 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000570 | 6 | OTUM051 | LP | SINGLE_TREE | Closed in | OTUMARA | SSV | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is currently closed. * Well has SSV failure. * It is not protected by an instrusive cage * OTUM051 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) Well has integral and tested ScSSSV on auto. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2 & 4) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000572 | 6 | OTUM053 | LP | SINGLE_TREE | Flowing | OTUMARA | SSV, Cmb_WITSIT O/due | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is producing. * Well has SSV failure and over CWI combined WIT/SIT. * It is protected not by an instrusive cage * OTUM053 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) There is a plan to repair the failed valve and carry out the combined WIT/SIT . 6) Well has other XMAS Tree valves tested and integral. | 2 & 4) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000573 | 6 | OTUM054 | LP | SINGLE_TREE | Flowing | OTUMARA | SSV | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is producing. * Well has SSV failure. * It is protected by an instrusive cage * OTUM054 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) Well is flowing with integral and tested ScSSSV on auto. 4) A protective instrusive cage is installed on the XMAS Tree. 5) There is a plan to repair the failed valve. 6) Well has other XMAS Tree valves tested and integral. | 2) Production Operations: Oyebode & Usin 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000575 | 6 | OTUM056 | LP | SINGLE_TREE | Closed in | OTUMARA | CTRL, overdue interim control action | Low | P=C2 | A=C2 | C=C2 | E=C2 | P=C2A=C2C=C2E=C2 | * Well is currently closed. * Well has control line failure. * It is not protected by an instrusive cage * OTUM056 is located in the Swamp location and about 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Failure is managed by regular surveillance to the wellhead location. 3) There is a plan to sign off a securing proposal and thereafter secure the well. 4) A protective instrusive cage is to be installed on the XMAS Tree until the well is secured. 5) There is a plan to repair the failed valves. 6) Well has other XMAS Tree valves tested and integral. | 2 & 4) Production Operations: Oyebode & Usin 3) PT & CWI: Somtochukwu Odumodu & Chinedu Onuoha 5) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000822 | 7 | SAGR002 | LP | DUAL_TREE | Closed in | SAGHARA | UMV2 | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is closed in and not capable of flowing. * Well has Master Valve failure * It is not protected by an instrusive cage * It is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) Master Valve failure is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree until th well is secured. 5) Well has XMAS Tree valves tested and integral. 6) There is a plan to repair the failed master valves. 7) There is a plan to generate securing proposal and thereafter secure well. | 2) Production Operations: Oyebode & Usin 6) CWI: Onuoha Chinedu 7) PT & CWI: Somtochukwu Odumodu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)
400000000823 | 7 | SAGR003 | LP | DUAL_TREE | Closed in | SAGHARA | SSV2, SV2, UMV2, SSV | Medium | P=C3 | A=C2 | C=C3 | E=C3 | P=C3A=C2C=C3E=C3 | * Well is closed in. (But capable of natural flow; interval will be reopened post routing .of the flowline to Otumara Flowstation) * Well has SSV, SSV & MV failures * It is not protected by an instrusive cage * SAGR003 is located in Swamp location. About 50m / 100m away from nearby settlement. | 1) Well has other XMAS Tree valves tested and functional ScSSSV. 2) valves failure is managed by regular surveillance to the wellhead location. 3) Well is closed in with functional and tested ScSSSV. 4) A protective instrusive cage is to be installed on the XMAS Tree. 5) Well has XMAS Tree valves tested and integral. 6) There is a plan to repair the failed master valves. | 2) Production Operations: Oyebode & Usin 5 & 6) CWI: Onuoha Chinedu | 2020-03-01 | DATE: 23rd March 2019 1. Ajaraogu Benjamin (TA 2 Well Integrity) 2. Igben Pius (Snr CWI) 3. Odumdou Somtochukwu (Well integrity FP) 4. Egurindu Paul (Operations Supervisor ESCB) 6. Uzuegbu Chinazom (Operations Supervisor Forc)

## Sheet1
AFRE008 | AFRE004
AFRE009 | ESCB001
OTUM008 | ESCB003
OTUM011 | OTUM002S1
OTUM016 | OTUM009
OTUM017 | OTUM012
OTUM032 | OTUM015
OTUM035 | OTUM018
OTUM036 | OTUM021
OTUM037 | OTUM030
OTUM039 | OTUM045
OTUM040 | OTUM048S1
OTUM043 | OTUM050S1
OTUM051 | SAGR002
OTUM053 | SAGR003
OTUM054
OTUM056