## Contents
| S/N | Locations | Total Actions | Total Closed Actions | Total Variance | RAG | REMARKS | Perf
| 1 | Gbaran - Ubie | 52 | 10 | 42 |  | 7 Close out actions included in 2018 Budget, 18 included in 2019 Budget | 19.23%
| 2 | Kolocreek FS | 15 | 3 | 12 |  | 3 Close out action included in 2018 Budget and 1 is open. | 20%
| 3 | Etelebou FS | 16 | 5 | 11 |  | 5 Close out actions included in 2018 Budget and 2 is open | 31.25%
| 4 | Adibawa FS | 14 | 4 | 10 |  | 1 Close out actions included in 2018 Budget and 1 is open | 28.57%
| 5 | Ubie FS | 5 | 5 | 0 |  |  | 100%
| 6 | Mbiama Microwave | 9 | 0 | 9 |  |  | 0%
| 7 | Diebu Creek | 6 | 1 | 5 |  | 1 Close out actions included in 2018 Budget | 16.67%
| 8 | Nun River | 13 | 3 | 10 |  | 3 Close out actions included in 2018 Budget and 2 is open | 23.08%
| 9 | Soku FS | 30 | 4 | 26 |  |  | 13.33%
| 10 | Soku GP | 6 | 1 | 5 |  |  | 16.67%
| 11 | Belema GP | 34 | 5 | 29 |  |  | 14.71%
| 12 | Belema FS | 33 | 0 | 33 |  |  | 0%
| 13 | Oloma | 17 | 0 | 17 |  |  | 0%
| 14 | BOGT | 22 | 6 | 16 |  |  | 27.27%
| 15 | BOGT NAG | 0 | 0 | 0 |  |  | #DIV/0!
| 16 | BOGT CLP | 0 | 0 | 0 |  |  | #DIV/0!
| 17 | BOGT FPSO | 22 | 0 | 22 |  |  | 0%
|  | Total | 294 | 47 | 247
Performance Legend
0 - 40 % |  | LOW
41 - 60% |  | MEDIUM
61 - 100% |  | HIGH

## Gbaran - Ubie
Action Tracker
|  | HOME | Inspection Report |  |  |  |  | SAP / ORIP / CIMS / FOUNTAIN ENTRY / Engr Work Request EWR
| S/N | Inspection Activity | Date inspected | Findings | Recommended Remedial Action | CMPT/Risk Ranking ( H, M , L) | Report Reference | Close out tracking method e.g. SAP, CIMS, FOUNTAIN, ORIP | Notification / Fountain / WO | LAFD/Target Date | Execution party | Status | Other Remarks
Statutory Inspection | 1 | 2Y Onplot Piping Inspection | 2016-07-01 | 1. Corroded drain valves in the Oil Test Separators Unit 50. | Carry out spot repair coating on the corroded drain valves. | L | GBU/VESSTANKPP/004 |  |  |  |  | NOT DONE | ADOPT HUMIDOR
| 2 | 1Y Lifting Equipment PM Inspections | 2017-07-03 | GANTRY INSIDE MECHANICAL WORKSHOP: 1. G -1846 : Defective stanchion out from base, missing bolts and nuts. 2. G - 1847: Defective Hydraulic Mechanism GANTRY AT THE JETY NEAR FIRE WATER: Faulty electrical system | GANTRY INSIDE MECHANICAL WORKSHOP 1. Fix stanchion base, load test before use. 2. Carry out servicing of the hydraulic mechanism. GANTRY AT THE JETTY NEAR FIRE WATER Repair electrical system and call for inspection. | M | GBA1. LAP.CO.1707001 | SAP | G1846- 11595574 G1847- 11595581 |  |  | CLOSED | Remedial action to be carried out before end 2017.
| 3 | 6M Lifting Accessories PM Inspections | 2017-07-03 | A total of 114 tackles were inspected. 112 was accepted and 2 rejected. | The rejected ones were removed and given to Assest Team for distruction. | L | GBU1. LAC.CO.1707001 |  |  |  |  | CLOSED
| 4 | 30M RV Inspections & Changeout
| 5 | 30M PV Inspection | 2014-09-01 | 1. Leaking Lean Rich Glycol Heat Exchanger Tr.1 (1-E-4104) 2. Faded coating condition of entire CPF | 1. Repair the leaking lean/rich glycol heat exchanger, 1-E04104. 2. Carry out maintenance painting of the facility to forestall corrosion. | M | GBRG1.VSR.WC.1409008 |  |  |  |  | CLOSED.
| 6 | 6M Ligament Valves Inspections
FIMS | 7 | Flowline coating inspection
| 8 | 2Y Flowline Inspection | 2017-02-05 | Low CP potentials for W10T, W17T, W19T, W11T & W13T | Carry out UT type 2 | L | 2016 FIMS integrity Report | SAP | 22468885 | 2017-07-25 |  | CLOSED.
CM | 9 | 1M Vibration Analysis
| 10 | 1M Lube Oil Sampling
| 1 | 2Y Assessments of Helipad
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR GBARAN HELIPAD (W/O No. 2257594) | 2017-03-04 | * Mild paint peel off on concrete bay | • Remove peeled off paint and re-paint surface with approved paint | M | SPDC-2017-06-00000110 | SAP | 11595518 | 2018-10-07 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 2 | 3Y Assessments of WellHead Platforms
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF GBARAN WELLS 20/21 PLATFORMS (WORK ORDER NO 22366703) | 2017-03-04 | * Degraded road paving's at approach and inside location * Failed section of fence, * Pot holes, deteriorated asphalt pavement * No gratings around wellhead. Timber logs used * Failed & degraded bituminous/Concrete paved surface and scoured area around drain and fence | • Reconstruct degraded road pavings • Reconstruct failed section of fence • Replace timber around wellhead with steel gratings • Fill up scoured area and reconstruct paved surface | H | SPDC-2017-06-00000110 | SAP | 11595538 | 2018-10-07 | ASSET ENGINEERING | Asset team makes budget available for execution
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF GBARAN WELLS 23/25/26 PLATFORMS (WORK ORDER NO 22366703) | 2017-03-04 | * Failed fence column and ground beam section- gully behind fence * Missing gratings at some sections in the well head platform .Timber used on top of wellhead platform | • Fill up the eroded section and reconstruct failed section of fence • Replace missing gratings .Replace timber with galvanized gratings | H | SPDC-2017-06-00000110 | SAP | 11595538 | 2018-10-07
|  | CIVILSTRUCT ASSET INTEGRITY for GBARAN WELL 14 PLATFORM AND LOCATION (W/O No. 22366703) | 2017-03-04 | * Undulating isolated craters of pot holes just before entrance | • Cut off the degraded area and repair with hot mixed asphalt | M | SPDC-2017-06-00000110 | SAP | 11595538 | 2018-10-07
|  | CIVILSTRUCT ASSET INTEGRITY FOR GBARAN WELL 10 PLATFORM AND LOCATION (W/O No. 22366703) | 2017-03-04 | * Broken portion of fence in the location * Visible longitudinal crack on walls * Eroded sections on road shoulders in access road | • Repair broken portion of fence * Repair crack on the walls * Fill up eroded section of road shoulders and surface with Hot Rolled Asphalt | M | SPDC-2017-06-00000110 | SAP | 11595538 | 2018-10-07
|  | CIVILSTRUCT ASSET INTEGRITY FOR GBARAN WELL 17 PLATFORM AND LOCATION (22366703) | 2017-03-04 | * No existing personnel access platform * No hard barrier around the cellar pit | • Provide mobile personnel access platform around the wellhead • Construct hard barrier around the cellar pit to prevent falls into the pit | M | SPDC-2017-06-00000110 | SAP | 11595538 | 2018-10-07
| 3 | 1 YR Assessments of Topside of Onshore Steel Structure | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 4 | 2Y Assessments of Onshore Concrete Structures | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR ZARAMA OIL MANIFOLD CONCRETE PLINTHS AND CITADEL FENCE | 2017-06-04 | • Scoured area underneath concrete pipe supports .Severe wash out by storm water .Severe subsidence caused by storm water | • Fill up the scoured area and resurfaed with concrete .Source for topsoil and compact to a thicknes of 100mm .Same recommendations as above. Area= 20m by 5m. | M | SPDC-2017-06-00000110 | SAP | 11595774 | 2018-10-07 | ASSET ENGINEERING | Asset team makes budget available for execution
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR ETELEBOU OIL MANIFOLD PIPELINE CONCRETE SUPPORTS | 2017-04-04 | • Pipeline pulled out of concrete supports | • Demolish pulled out support, fabricate pre-cast concrete slabs and place under the pipeline. Fix clamp into the top slab | M | SPDC-2017-06-00000110 | SAP | 11595774 | 2018-10-07
| 5 | 3Y Inspection of Telecom Tower/Mast | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 6 | 5Y Structural Integrity Assessment of Jetty underwater structures | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | CIVILSTRUCT ASSET INTEGRITY FOR GBARAN JETTY STEEL SHEET PILES | 2017-03-04 | * Mild coating failure on the piles | • Remove degraded coating and re-coat with approved paint | L | SPDC-2017-06-00000110 | SAP | 11595771 | 2018-10-07 | ASSET ENGINEERING | CLOSED
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR GBARAN JETTY FENDERS | 2017-03-04 | * Pulled out fenders | • Replace pulled out fenders | L | SPDC-2017-06-00000110 | SAP | 11595771 | 2018-10-07 |  | CLOSED
| 7 | 1Y Asset Integrity Verification | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 8 | 4Y Structural Integrity Assessment of FLBs | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 9 | 4Y Structural Integrity Assessment of Buildings | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | 4Y Structural Integrity Assessment of Buildings | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR ETELEBOU MANIFOLD GUARD HUT | 2017-04-04 | • Deteriorated/missing ceiling boards | • Replace deteriorated and missing ceiling boards | M | SPDC-2017-06-00000110 | SAP | 11595774 | 2018-10-07 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 10 | 4Y Structural Integrity Assessments of Structural Foundation | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | 1Y Structural Integrity Assessments of Fence | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR ETELEBOU MANIFOLD CITADEL FENCE | 2017-04-04 | • Scoured area around citadel fence | • Fill scoured area and re-surface with concrete | M | SPDC-2017-06-00000110 | SAP | 11595774 | 2018-10-07
| 11 | Integrity Assessment of Elevated Water tank | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 12 | 1Y Structural Assessment of Bridges (Superstructure) | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 13 | 3Y Assessment of Bridges (Substructure) | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR OGBOLOMA MAIN ACCESS BRIDGES (W/O No. 22473314) | 2017-07-17 | * Scouring at abutment | • Fill the scoured area with eartfill materials and cover with rib-rap | L | SPDC-2017-09-00000142 | SAP | 11595774 | 2018-10-07 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR OKOLOIBIRI MAIN ACCESS BRIDGE 1 (W/O No. 22473313) | 2017-07-18 | * Moderate corrosion on Steel Casing Piles and Sheet Piles | • Prepare surface of piers and recoat with approved paint | L | SPDC-2017-09-00000142 | SAP | 11595774 | 2018-10-07
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR OKOLOIBIRI MAIN ACCESS BRIDGE 2 (W/O No. 22473321) | 2017-07-18 | * Moderately corroded railings. * Severe colour coating loss with early signs of corrosion setting in | • Prepare surfaces and recoat with approved paint | L | SPDC-2017-09-00000142 | SAP | 11595774 | 2018-10-07
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR OGBUNAGHA MAIN ACCESS BRIDGE 1 KOROAMA (W/O No. 22473320) | 2017-07-18 | * Coating loss with early signs of corrosion * Moderate corrosion on steel case piles and sheet piles | • Prepare surfaces and recoat with approved paint | L | SPDC-2017-09-00000142 | SAP | 11595774 | 2018-10-07
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR POLAKU MAIN ACCESS BRIDGE 1 KOROAMA (W/O No. 22534303) | 2017-07-18 | * Coating loss with early signs of corrosion setting in the railings | • Prepare surfaces of railings and recoat with approved paint | L | SPDC-2017-09-00000142 | SAP | 11595774 | 2018-10-07
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR POLAKU MAIN ACCESS BRIDGE 2 KOROAMA (W/O No. 22534303) | 18/7/2017 | * Coating loss with early signs of corrosion * Loose Handrail Post | • Prepare surfaces of railings and recoat with approved paint • Provide C30 concrete and use to cast arount loose Handrail Post | M | SPDC-2017-09-00000142 | SAP | 11595774
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR POLAKU MAIN ACCESS BRIDGE 2 KOROAMA (W/O No. 22534303) | 2017-07-18 | * Coating loss with early signs of corrosion * Loose Handrail Post | • Prepare surfaces of railings and recoat with approved paint • Provide C30 concrete and use to cast arount loose Handrail Post | L | SPDC-2017-09-00000142 | SAP | 11595774 | 2018-10-07
| 14 | 1 Y Integrity Assesment of Access Roads | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | Koroama NAG Manifold Facility erosion threat and severely failed road section of Gbaran-Etelebou link road |  | Koroama NAG manifold shoreline receded by0.5m from 2016 to 2018. Shore protection works urgently required. Degraded asphalt thickness, clustered and isolated potholes on the section of road stretch, heavy water ponding on roads, no shoulders Asphalt surface deteriorated, deep gullies | Disposal will include all refuse dumps along road section and shoulder. 400m length and 6m width. Supply sharp river sand, spread and compact evenly to required depth as directed by shell. | H | SPDC-2018-04-00000027 | SAP | 11636947 | 2019-04-07 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR GBARAN OIL AND NAG MANIFOLD ROAD APPROACH |  | Moderate clustered potholes and gradually deteriorated asphalt pavings | Full-depth patching for the potholes, 1. Excavate locally down into fill / poorly compacted subgrade around pothole. area should extend at least one foot into the good pavement surrounding the patching area 2. Provide, spread and compact sharp sand to 100% MDD/WASC 3. Provide, spread, wet and compact 0- 50mm mixed granite materials to 100% MDD/WASC and to 150mm 4. Apply prime coat using MC1 @ 1.2litres/m2, including blinding with sharp sand over area to be specified 5. Provide, lay asphaltic concrete wearing course to a compacted thickness of 50mm over new base. Length=40 metres, Width=6 metres | M | SPDC-2018-04-00000027 | SAP | 11636947 | 2019-04-07
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR ZARAMA NAG ACCESS ROAD | 2017-06-04 | • Severely eroded road section | • Fill up the eroded section and reconctruct with 0-50mm mixed granite base course and HRA surfacing | M | SPDC-2017-06-00000110 | SAP | 11595774 | 2018-10-07
| 15 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR ZARAMA NAG MANIFOLD | 2017-06-04 | • Scoured area at the far left area on approach, surfaced dressed section wearing off | • Fill up the scoured area and resurfaed the worn out section of the surface | M | SPDC-2017-06-00000110 | SAP | 11595774 | 2018-10-08
| 16 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT FOR KOROAMA NAG MANIFOLD | 2017-05-04 | • Pot holes, ponding and deteriorated asphalt on approach • Bundwall with broken edges-(though not in use) and exposed rebar strands • Mild Coating loss on handrails | • Patch pot holes on the approach and replace deteriorated asphalt • Repair broken bundwall • Remove degraded coating and re-caot with approved apint | M | SPDC-2017-06-00000110 | SAP | 11595774 | 2018-10-07
| 17 | 2Y Control room buildings | NIL
| 27 | Underwater Mtce Services
Underwater insp | 28 | 5 Y Underwater inspection | 2012-12-20 | 1. Pile sections from splash zone up to the concrete deck were corroding freely 2. Handrails are damaged and some missing along the west and south edges of the ramp | 1. Blast clean and apply coatings on sheet piles. 2. Replace missing handrails; repair damaged handrails | M | GBAR/1/12/RPT | SAP | 11593692 | 1905-07-09 |  | CLOSED
| 29 | 1 Y Underdeck inspection | NIL
Asset Engr | 31 | Remedial Works
Cathodic Protection | 32 | 6M CP Mtce
| 33 | 1Yrly CP Survey
| 34 | GBARW001LFLN, P12948 |  | No cp survey | Carry out cp survey & rectify anomalies
| 35 | GBARW001SFLN, P12949 |  | No cp survey | Carry out cp survey & rectify anomalies
| 36 | GBARW022TFLN(E1), P10905 |  | No cp survey | Carry out cp survey & rectify anomalies; carry out UT1,UT2 & coating survey
| 32 | GBARW023TFLN |  | No cp survey | Carry out cp survey & rectify anomalies; carry out UT1,UT2 & coating survey
| 33 | GBARW014TFLN(E2a), P10851 |  | No cp survey | Carry out cp survey & rectify anomalies
| 34 | GBARW015TFLN(E4a), P10861 |  | No cp survey | Carry out cp survey & rectify anomalies
| 35 | GBARW025TFLN |  | No cp survey | Carry out cp survey & rectify anomalies
| 36 | GBARW012TFLN |  | No cp survey | Carry out cp survey & rectify anomalies; carry out UT1,UT2 & coating survey
HIGH
MEDIUM
LOW

## Kolocreek FS
Action Tracker
|  | HOME | Inspection Report |  |  |  |  | SAP / ORIP / CIMS / FOUNTAIN ENTRY / Engr Work Request EWR
| S/N | Inspection Activity | Date inspected | Findings | Recommended Remedial Action | CMPT/Risk Ranking ( H, M , L) | Report Reference | Close out tracking method e.g. SAP, CIMS, FOUNTAIN, ORIP | Notification / Fountain / WO | LAFD/Target Date | Execution party | Status | Other Remarks
| 1 | 2Y Onplot Piping Inspection | 2017-05-01 | Issues and findings raised in the 2015 inspection cycle have been closed. | Facility was recently painted and the corrosion defects highlighted have been repaired by coating. | L | KOCR/VESSTANKPP/05 | SAP | 22293941 | 2018-12-01 |  | CLOSED
| 2 | 1Y Lifting Equipment PM Inspections | 2016-07-01 | Gantries over the pressure vessels not fit for use. | Gantries have been marked ''Do not Use" | L | KOLCR.F1.LAP.1607002 | SAP | 22530487 | 2017-11-01 |  | OPEN | The faulty gantries are out of use. Mobile crane is used in lifting the RVs on the vessels.
| 3 | 6M Lifting Accessories PM Inspections
| 4 | 30M RV Inspections & Changeout | 2014-03-01 | NO ISSUES | NONE | NIL | KOLOFL.RVS.KO.14003001 | SAP | 21729334 |  |  | CLOSED | RVs due for certification March 2024
| 5 | 30M PV Inspection | 2014-03-01 | NO ISSUES | NONE | NIL | KOLF1.VSR.KO.1404001 | SAP | 21729334 |  |  | CLOSED | Vessels fit for purpose until Jan 2020.
| 6 | 6M Ligament Valves Inspections
| 7 | Flowline coating inspection
| 8 | 2Y Flowline Inspection
| 9 | 1M Vibration Analysis
| 10 | 1M Lube Oil Sampling
| 11 | 2Y Assessment of Flare & Tank Bundwalls | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 12 | 2Y Assessments of Helipad & Helidecks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 13 | 3Y Assessments of WellHead Platforms | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 14 | 1 YR Assessments of Topside of Onshore Steel Structure | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 15 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK INLET MANIFOLD | 2016-11-25 | Damaged concrete section Cracks propagating near inlet flowlines (25mm crack width) Missing bolts on base plate of staircase Unstable handrail on staircase Uneven/unstable gratings Dilapidated grating frame Missing clips on gratings Gantry in good condition | *Prepare surface, supply grade C20/25 concrete and use to reconstruct failed concrete section *Open up cracks to about 45mm wide, supply grade C20/25 concrete and use to fill up opened area. *Provide bracing | M | SPDC-2016-12-00000243 | SAP | 22575844/11600619 | 2018-11-16 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 16 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK XHP SEPARATOR | 2016-11-25 | Failed concrete section between XHP Separator and Surge Vessel 2 | Prepare concrete surface, supply and use grade C20/25 concrete to repair failed sections. | M | SPDC-2016-12-00000251 | SAP | 22575844/11600619 | 2018-11-16
| 17 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK ENGINE NOSE | 2016-11-25 | Water ponding as a result of silted drain pipe | Desilt drain pipe and slope bundwall area with dimension 2m x2m | L | SPDC-2016-12-00000252 | SAP | 22575844/11600619 | 2018-11-16
| 18 | 3Y Assessments of Topside Concrete/Steel Structure (Swamp) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 19 | 3Y Inspection of Telecom Tower/Mast | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 20 | 5Y Structural Integrity Assessment of Jetty | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 21 | 1Y Asset Integrity Verification | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 22 | 4Y Structural Integrity Assessment of FLBs | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 23 | 4Y Structural Integrity Assessment of Buildings | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| 24 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK GUARD HUT(22217678) | 2016-11-25 | *Mild Paint Loss on the walls *Missing/Degraded Ceiling Board | *Remove degraded paints with hand tools. *Replace missing/degraded ceiling boards with new 600mm x 600mm acoustic fibreboard ceiling tiles or other approved ceiling panels, complete with other accessories (0.75x0.5)m x 4Nos | L | SPDC-2016-12-00000238 | SAP | 22575844/11600619 | 2018-11-16 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 25 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK FIRE HUT | 2016-11-25 | Crack on ramp (crack width 0.025mm) | Prepare concrete surface, seal crack with epoxy bonding materials | M | SPDC-2016-12-00000240 | SAP | 22575844/11600619 | 2018-11-16
| 26 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK CHEMICAL INJECTION SHED | 2017-11-25 | Moderate corrosion on roof gutter support Degraded roof drain pipe Bundwall in good condition | Replace corroded roof gutter support 50x50x10mm equal angle section 6Nos, each 1m long Replace 3” diameter drain pipe No action | M | SPDC-2016-12-00000244 | SAP | 22575844/11600619 | 2018-11-16
| 27 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK TELECOM HUT | 2017-11-25 | Cracks propagating on concrete base(25mm crack width) | Open up cracks to about 45mm wide, supply grade C20/25 concrete and use to fill up opened area | M | SPDC-2016-12-00000246 | SAP | 22575844/11600619 | 2018-11-16
| 28 | 4Y Structural Integrity Assessments of Structural Foundation
|  | 4Y Structural Integrity Assessments of Structural Foundation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 29 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK MAIN ENTRANCE WALKWAY (22445719) | 2017-11-25 | Degarded concrete pavement | Scarify existing concrete surface and clean out debris. | M | SPDC-2016-12-00000239 | SAP | 22575844/11600619 | 2018-11-16
| 30 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK METERING SKID AREA | 2017-11-25 | Failed concrete section | Prepare surface, supply grade C20/25 concrete and use to reconstruct failed concrete section | M | SPDC-2016-12-00000241 | SAP | 22575844/11600619 | 2018-11-16
| 31 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK ROBERT SHAW PANEL | 2017-11-25 | Missing concrete slab | Replace missing concrete slab with pre-cast slab of grade C35 concrete | M | SPDC-2016-12-00000242 | SAP | 22575844/11600619 | 2018-11-16
| 32 | CIVILSTRCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK PUMP BAY | 2017-11-25 | *Water ponding as a result of silted drain pipe *Failed concrete sections behind Pump Bay 1 & 2 and between Pump Bay 5 & 7 | Break concrete section to unearth 1” drain pipe. *Prepare concrete surface, supply and use grade C20/25 concrete to repair failed sections | M | SPDC-2016-12-00000250 | SAP | 22575844/11600619 | 2018-11-16
Integrity Assessment of Elevated Water tank
Integrity Assessment of Elevated Water tank
| 33 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KOLO CREEK WATER TANK | 2017-11-25 | Moderately corroded support stanchions, access ladders, braces, handrails, primary and secondary support frame for grating | Remove corrosion by power brushing; prepare surface and apply 2 coats of Aluminium Epoxy Ester or other approved coating materials on the prepared surface.. | M | SPDC-2016-12-00000245 | SAP | 22575844/11600619 | 2018-11-16 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 34 | 1Y Structural Assessment of Bridges (Superstructure)
| 35 | 3Y Assessment of Bridges (Substructure)
| 36 | 1 Y Integrity Assesment of Access Roads
| 37 | 2Y Control room buildings
| 38 | Underwater Mtce Services
Underwater insp | 39 | 5 Y Underwater inspection
| 40 | 1 Y Underdeck inspection
Asset Engr | 41 | Remedial Works
Cathodic Protection | 42 | 6M CP Mtce
| 43 | 1Yrly CP Survey
| 44 | KOLOW039TFLN |  | No cp survey | Carry out cp survey & rectify anomalies
| 45 | KOLOW040TFLN |  | No cp survey | Carry out cp survey & rectify anomalies
HIGH
MEDIUM
LOW

## Etelebou FS
Action Tracker
|  | HOME | Inspection Report |  |  |  |  | SAP / ORIP / CIMS / FOUNTAIN ENTRY / Engr Work Request EWR
| S/N | Inspection Activity | Date inspected | Findings | Recommended Remedial Action | CMPT/Risk Ranking ( H, M , L) | Report Reference | Close out tracking method e.g. SAP, CIMS, FOUNTAIN, ORIP | Notification / Fountain / WO | LAFD/Target Date | Execution party | Status | Other Remarks
Statutory Inspection | 1 | 2Y Onplot Piping Inspection | 2016-06-01 | 1. Oil stain at the metering skid 2.Damaged polykene wrap at the soil to air interface of the inlet manifold and the metering skid. | 1. Wash and clean off oil stain. 2. Replace damaged protective wrap | L | ETELF/VESSTANKPP/003 | SAP | 22311168 | 2018-02-01 |  | 1. CLOSED 2. OPEN | No external corrosion on the exposed parts of the pipe.
| 2 | 1Y Lifting Equipment PM Inspections | 2016-07-01 | Gantries over the pressure vessels not fit for use. | Gantries have been marked ''Do not Use" | L | ETEF1.LAP.EO.1607002 | SAP | 22527349 | 2018-08-01 |  | OPEN | The faulty gantries are out of use. Mobile crane is used in lifting the RVs on the vessels.
| 3 | 6M Lifting Accessories PM Inspections
| 4 | 30M RV Inspections & Changeout | 2016-01-01 | No issues. | Certify the relief valves when due. | L | ETEF1.RV.EO.1601001 | SAP | 22339595 | 2018-06-01 |  | Closed | RVs certified fit for purpose by RBI until Jan 2024.
| 5 | 30M PV Inspection | 2016-01-01 | No corrosion issues, coating condition of the facility is satisfactory. However, there is no nameplate on the FLKO. | Source the design data of the FLKO and document for inspection history. | L | ETEF1.VSR.EO.1601001 | SAP/CIMMS | 22339595 | 2018-08-01 |  | Closed | Design data to be sourced from As-built drawing of the FLKO.
| 6 | 6M Ligament Valves Inspections
FIMS | 7 | Flowline coating inspection
| 8 | 2Y Flowline Inspection |  | Low CP potentials for 2S,3L,7L,7S,11T,12T,13T,14T,15L,HP OIL BULK | Carry out UT type 2 | L | 2016 FIMS integrity Report | SAP | 22468892 | 2017-07-25 |  | Closed | NIL
CM | 9 | 1M Vibration Analysis
| 10 | 1M Lube Oil Sampling
Civil / Structural Asset Int. Inspection & Mtce | 11 | 2Y Assessment of Flare & Tank Bundwalls
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ETELEBUO FS FLARE STRUCTURES (22445723) | 2017-05-12 | Mild to moderate corrosion and contamination of handrails and support stanchions | Remove corrosion by power brushing, prepare surface and apply 2 coats of Aluminium Epoxy Ester or other approved coating materials on the prepared surface of handrails and support stanchions. | L | SPDC-2017-06-00000100 | SAP | 22445723 | 2018-10-23 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 12 | 2Y Assessments of Helipad & Helidecks
| 13 | 3Y Assessments of WellHead Platforms
| 14 | 2Y Assessments of Topside Concrete/Steel Structure (Land)
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ETELEBUO FS OUTSIDE MAIN ENTRANCE BY CITADEL FENCE | 2017-05-05 | Moderate coating loss and contamination of guardrails | Remove degraded coating and contamination by power brushing, prepare surface and apply 2 coats of Aluminium Epoxy Ester or other approved coating materials to the prepared surface of guardrails to full film thickness. Dimensions: 70mm dia., CHS., 100m length | L | SPDC-2017-06-00000093 | SAP | 22419536 | 2018-10-23 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ETELEBUO FS INLET MANIFOLD/HP SEPARATOR 1 | 2017-05-08 | *Moderate coating loss of grating frame along section of walkway *Degraded concrete plinths supporting LP and HP 6” Gas To Flare lines | *Remove corrosion by power brushing, prepare surface and apply 2 coats of Aluminium Epoxy Ester or other approved coating materials to the prepared surface of grating frame. *Prepare formwork, provide grade C30 concrete to cast degraded concrete plinths( | L | SPDC-2017-06-00000096 | SAP | 22445723 | 2018-10-23
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ETELEBUO FS PUMP HOUSE | 2017-05-09 | Degraded concrete base supporting steel stanchion on base plate | Prepare formwork, provide grade C30 concrete to cast degraded concrete base | L | SPDC-2017-06-00000097 | SAP | 22445723 | 2018-10-23
|  | CIVILSTRUCT ASSET INTEGRITY OF ETELEBUO FS FLKO VESSELS | 2017-05-10 | Mild coating loss on handrails, toe board, personnel access ladder | Remove degraded coating by power brushing, prepare surface and apply 2 coats of Aluminium Epoxy Ester or other approved coating materials to the prepared surface of handrails, toe board, personnel access ladder. | L | SPDC-2017-06-00000098 | SAP | 22486371 | 2018-10-23
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ETELEBUO FS CONCRETE SLABS | 2017-05-13 | Misaligned and broken/damaged concrete slabs | Properly align concrete slabs. Prepare formwork, provide grade C30 concrete to cast broken/degraded concrete slabs( | L | SPDC-2017-06-00000101 | SAP | 22445723 | 2018-10-23
| 15 | 3Y Assessments of Topside Concrete/Steel Structure (Swamp) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 16 | 3Y Inspection of Telecom Tower/Mast | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 17 | 5Y Structural Integrity Assessment of Jetty | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 18 | 1Y Asset Integrity Verification | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 19 | 4Y Structural Integrity Assessment of FLBs | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 20 | 4Y Structural Integrity Assessment of Buildings | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ETELEBUO FS FIRE HUT | 2017-05-06 | Mild paint loss on walls | Remove degraded paint with hand tools. Prepare surface and apply 2 coats of approved paint on walls to full film thickness with dimensions: 2.96m length, 2.12m width, 2.64m height | L | SPDC-2017-06-00000094 | SAP | 22217677 | 2018-10-23 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ETELEBUO TELECOM BUILDING/METERING SKID 22217677 | 2017-05-07 | *Mild paint loss on walls *Unstable/Uneven gratings | *Remove degraded paint with hand tools. Prepare surface and apply 2 coats of approved paint on walls to full film thickness *Replace uneven gratings and provide grating clips | L | SPDC-2017-06-00000095 | SAP | 22217677 | 2018-10-23
| 21 | 1Y Structural Integrity Assessments of Fence | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ETELEBUO FS GUARD HUT SUPERVISOR'S OFFICE | 2017-05-04 | Moderate paint loss on walls | Remove degraded paint with hand tools. Prepare surface and apply 2 coats of approved paint on walls to full film thickness with dimensions: | L | SPDC-2017-06-00000092 | SAP | 22217677 | 2018-10-23 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 22 | Integrity Assessment of Elevated Water tank | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | Integrity Assessment of Elevated Water tank | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | CIVILSTRUCT INTEGRITY ASSESSMENT OF ETELEBUO FS ELEVATED WATER TANK | 2017-05-11 | Moderate coating loss on primary support stanchions, diagonal and side bracings. Severe coating loss on handrails. Mild corrosion on grating support frame, fixed vertical ladder, flat bars and braithwaite tank | Remove degraded coating by power brushing, prepare surface and apply 2 coats of Aluminium Epoxy Ester or other approved coating materials on the prepared surface of support stanchions, diagonal and side bracings, handrails, grating support frame, fixed vertical ladder, flat bars and Braithwaite tank, to full film thickness | L | SPDC-2017-06-00000099 | SAP | 22445723 | 2018-10-23 | CORPORATE CIVIL ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 23 | 1Y Structural Assessment of Bridges (Superstructure)
| 24 | 3Y Assessment of Bridges (Substructure)
| 25 | 1 Y Integrity Assesment of Access Roads
| 26 | 2Y Control room buildings
| 28 | Underwater Mtce Services
| 29 | 5 Y Underwater inspection
Underwater insp | 30 | 1 Y Underdeck inspection
31
Asset Engr | 31 | Remedial Works
Cathodic Protection | 32 | 6M CP Mtce
| 33 | 1Yrly CP Survey
Asset Engr | 31 | Remedial Works
Cathodic Protection | 32 | 6M CP Mtce
| 33 | 1Yrly CP Survey
HIGH
MEDIUM
LOW

## Adibawa FS
Action Tracker
|  | HOME | Inspection Report |  |  |  |  | SAP / ORIP / CIMS / FOUNTAIN ENTRY / Engr Work Request EWR
| S/N | Inspection Activity | Date inspected | Findings | Recommended Remedial Action | CMPT/Risk Ranking ( H, M , L) | Report Reference | Close out tracking method e.g. SAP, CIMS, FOUNTAIN, ORIP | Notification / Fountain / WO | LAFD/Target Date | Execution party | Status | Other Remarks
Statutory Inspection | 1 | 2Y Onplot Piping Inspection | 2017-07-01 | 1.Damaged protective wrap on 16'' gas outlet line from flare knockout vessel and inlet lines into the ligament manifold 2.Corroded 1'' gate valve and spool piece on W/24S 3.Faded top coat of the entire facility | 1. Replace damaged protective coating of the affected lines. 2. Replace corroded valve and carry out spot repair coating on spool piece. 3. Carry out coating renovation on areas with deteriorated top coat. | M | ADIF1/VESSTANKPP/06 | SAP | 21824569 | 2017-11-28 |  | OPEN
| 2 | 1Y Lifting Equipment PM Inspections | 2017-09-16 | Misaligned and stiff trolley rollers of PD Meter Skid gantries | Properly align and service the trolley rollers | L | ADIF1.LAP.EU.1609001 | SAP | 22591522 | 2017-04-10 |  | CLOSED
| 3 | 6M Lifting Accessories PM Inspections
| 4 | 30M RV Inspections & Changeout | 2014-03-01 | NIL | NIL | NIL | NIL | NIL | NIL
| 5 | 30M PV Inspection | 2014-03-01 | NIL | NIL | NIL | NIL | NIL | NIL
| 6 | 6M Ligament Valves Inspections
FIMS | 7 | Flowline coating inspection |  | NIL | NIL | NIL | NIL | NIL | NIL
| 8 | 2Y Flowline Inspection |  | NIL | NIL | NIL | NIL | NIL | NIL
CM | 9 | 1M Vibration Analysis | NIL | NIL
| 10 | 1M Lube Oil Sampling | NIL | NIL
Civil / Structural Asset Int. Inspection & Mtce | 11 | 2Y Assessment of Flare & Tank Bundwalls
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF OLD FLARE STRUCTURES | 2017-04-04 | *Moderately corroded handrails, support stanchions, beams, grating frames *Sagged gratings along section of walkway *Degraded sand bags along sections of bundwall *Extremely dirty and torn windsock *Overgrown vegetation in and around the flare bundwall area | *Remove corrosion by power brushing, prepare surface and apply 2 coats of Aluminium Epoxy Ester or other approved coating materials on the prepared surface with dimensions: 35mm dia., CHS, 780m length 150mm dia., CHS, 130m length 100x300mm IPE, 40.5m length *Provide grating support beams(5Nos.) across sagged section, and replace sagged gratings Dimensions: 50x50mm E.A., 5m long Area of gratings=20x1=20m2 *Replace degraded sand bags along sections of bundwall with dimensions: 45m length, 1m height *Replace dirty and torn windsock *Cut overgrown vegetation and ensure good housekeeping | M | SPDC‐2017‐06‐00000070 | SAP | 11600617/22575844 | 2018-10-23 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 12 | 2Y Assessments of Helipad & Helidecks | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 13 | 3Y Assessments of WellHead Platforms | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 14 | 2Y Assessments of Topside Concrete/Steel Structure (Land) | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 15 | 3Y Assessments of Topside Concrete/Steel Structure (Swamp) | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 16 | 3Y Inspection of Telecom Tower/Mast | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF MAST BASE WIDTH | 2017-04-04 | 300mm steel triangular base No concrete support at base of Mast | Prepare ground surface to receive concrete. Cast support base using concrete grade C30. 400mm by 400mm with depth 300mm. | M | SPDC‐2017‐06‐00000070 | SAP | 11600617/22575844 | 2018-10-23 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
| 17 | 5Y Structural Integrity Assessment of Jetty | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 18 | 1Y Asset Integrity Verification | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 19 | 4Y Structural Integrity Assessment of FLBs | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
| 20 | 4Y Structural Integrity Assessment of Buildings | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL |  | NIL
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF DIESEL TANK STORAGE AREA | 2017-04-04 | Missing aluminium roofing sheet | Replace missing aluminium roofing sheet with dimension; 5.8x0.8m | M | SPDC‐2017‐06‐00000070 | SAP | 11598880/22575844 | 2018-10-23
| 21 | 4Y Structural Integrity Assessments of Structural Foundation | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
|  | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF SAVER PIT | 2017-04-04 | Moderately corroded handrails | Remove corrosion by power brushing, prepare surface and apply 2 coats of Aluminium Epoxy Ester or other approved coating materials to the prepared surface. Dimensions: 35mm dia.CHS, 77.4m length | M | SPDC‐2017‐06‐00000070 | SAP | 11600617/22575844 | 2018-10-23 | ASSET ENGINEERING | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
|  | CIVILSTRUCT INTEGRITY ASSESSMENT OF LP, HP SEPARATORS | 2017-04-04 | Missing grating clips/Unstable gratings | Provide missing grating clips to hold unstable gratings in place (10 Nos) | M | SPDC‐2017‐06‐00000070 | SAP | 11600617/22575844 | 2018-10-23
| 22 | Integrity Assessment of Elevated Water tank | NIL | NIL
| 23 | 1Y Structural Assessment of Bridges (Superstructure) | NIL | NIL
| 24 | 3Y Assessment of Bridges (Substructure) | NIL | NIL
| 25 | 1 Y Integrity Assesment of Access Roads | NIL | NIL
| 26 | 2Y Control room buildings | NIL | NIL
| 28 | Underwater Mtce Services | NIL | NIL
| 29 | 5 Y Underwater inspection | NIL | NIL
Underwater insp | 30 | 1 Y Underdeck inspection | NIL | NIL
Asset Engr | 31 | Remedial Works
Cathodic Protection | 32 | 6M CP Mtce
| 33 | 1Yrly CP Survey
| 34 | ADIBW025SFLN |  | No CP cable | Install CP cable and hook up to CP system
HIGH
MEDIUM
LOW

## Ubie FS
Action Tracker
|  | HOME | Inspection Report |  |  |  |  | SAP / ORIP / CIMS / FOUNTAIN ENTRY / Engr Work Request EWR
| S/N | Inspection Activity | Date inspected | Findings | Recommended Remedial Action | CMPT/Risk Ranking ( H, M , L) | Report Reference | Close out tracking method e.g. SAP, CIMS, FOUNTAIN, ORIP | Notification / Fountain / WO | LAFD/Target Date | Status | Other Remarks
Statutory Inspection | 1 | 2Y Onplot Piping Inspection | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 2 | 1Y Lifting Equipment PM Inspections | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 3 | 6M Lifting Accessories PM Inspections | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 4 | 24M RV Inspections & Changeout | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 5 | 30M PV Inspection | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 6 | 6M Ligament Valves Inspections | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
FIMS | 7 | Flowline coating inspection | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 8 | 2Y Flowline Inspection | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
CM | 9 | 1M Vibration Analysis | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 10 | 1M Lube Oil Sampling | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 12 | 2Y Assessments of Helipad & Helidecks | NIL
| 13 | 3Y Assessments of WellHead Platforms | NIL
| 14 | 2Y Assessments of Topside Concrete/Steel Structure (Land) | NIL
| 15 | 3Y Assessments of Topside Concrete/Steel Structure (Swamp) | NIL
| 16 | 3Y Inspection of Telecom Tower/Mast | NIL
| 17 | 5Y Structural Integrity Assessment of Jetty | NIL
| 18 | 1Y Asset Integrity Verification | NIL
| 19 | 4Y Structural Integrity Assessment of FLBs | NIL
| 20 | 4Y Structural Integrity Assessment of Buildings | NIL
| 21 | 4Y Structural Integrity Assessments of Structural Foundation | NIL
| 22 | Integrity Assessment of Elevated Water tank | NIL
| 23 | 1Y Structural Assessment of Bridges (Superstructure) | NIL
| 24 | 3Y Assessment of Bridges (Substructure) | NIL
| 25 | 1 Y Integrity Assesment of Access Roads | NIL
| 26 | 2Y Control room buildings | NIL
| 28 | Underwater Mtce Services | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
Underwater insp | 29 | 5 Y Underwater inspection | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
| 30 | 1 Y Underdeck inspection | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE | SECURITY ISSUE
Asset Engr | 31 | Remedial Works
Cathodic Protection | 32 | 6M CP Mtce
| 33 | 1Yrly CP Survey
HIGH
MEDIUM
LOW

## High Risk For Central Asset
LAND EAST ASSET
S/NO | GBARAN ACTIVITIES | Inspection Date | Description | Remedial Actions | Risk | Report Reference | Close out tracking method e.g. SAP, CIMS, FOUNTAIN, ORIP | Notification / Fountain / WO | LAFD/Target Date | Execution Party | Status
| HEETPILE WALL CLOSE TO MILITARY CHECK POINT | 2022-04-22 | 3 No. large cavities on section of the jetty sheetpile wall at ca 8m below the topside close to the military check point | Option 1  Remove the 400mm concrete slab panel close to the - 400mmx6mx8m  Cut off anchor tie rods across failed section to allow for excavation/access to the openings.  Provide, mix and seal up openings with concrete grade 40  Back fill around the openings using sand bags (1:3 cement/sand mix)  Replace the cut sections of tie rod  Provide, spread and fill and compact area with sharp sand - 18m x 9m x 2.5m  Reconstruct hardstand and reerect ligh | H | SPDC-2022-04-00000161
|  | 2022-04-22 | Severe loss of earth material and collapse of 1 No. lighting pole | Option 2  Remove the 400mm concrete slab panel close to the - 400mmx6mx8m  Cut off anchor failed tie rods across  Weld plates to cover the openings - 0.85m x 3m long x 4Nos.  Provide, spread and fill and compact area with sharp sand - 18m x 9m x 2.5m | H | SPDC-2022-04-00000161
|  | 2022-04-22 | Severe scouring underneath section of concrete hardstand |  | H | SPDC-2022-04-00000161
|  | 2022-04-22 | Severe corrosion and deformation of anchor tie rods |  | H | SPDC-2022-04-00000161
| UBIE FLOW STATION PERIMETER CIDATEL FENCE | 2021-08-25 | Missing bolts and nuts on top rails | Provide and install galvanized citadel fence bolts and nuts on top rails 125Nos. | H | SPDC-2021-12-00000049
| BRIDGE 1 - UBIE MAIN ACCESS STEEL GIRDER BRIDGE. BRIDGE APPROACH SIGNAGE | 2021-08-25 | Not sighted on approach and exit sections | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2021-12-00000049
| BRIDGE 1 - UBIE MAIN ACCESS STEEL GIRDER BRIDGE. GUARD RAILINGS | 2021-08-25 | Missing sections of bridge railings and post | Provide and install galvanized bridge railings and make good. 108m length 70mm CHS 20m Length 70mm CHS Post | H | SPDC-2021-12-00000049
| BRIDGE 2 – UBIE ACCESS STEEL GIRDER BRIDGE. BRIDGE APPROACH SIGNAGE | 2021-08-25 | Not sighted on approach and exit sections | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2021-12-00000049
| BRIDGE 2 – UBIE ACCESS STEEL GIRDER BRIDGE. GUARD RAILINGS | 2021-08-25 | Missing Hand rails/Post | Provide and install galvanized bridge railings and make good. 108m length 70mm CHS 20m Length 70mm CHS Post | H | SPDC-2021-12-00000049
| .BRIDGE ACCESS TO UKPELIEDE MANIFOLD (STEEL GIRDER BRIDGE) BRIDGE APPROACH SIGNAGE | 2021-08-25 | Not sighted on approach and exit sections | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO OTUSIGA (BAILEY BRIDGE) WELL 2. BRIDGE PANELS & RAILS | 2021-08-25 | Missing chord reinforcement pins & bolts 30mm Dia (5 Nos) | Install missing chord reinforcement pins and make good | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO OTUSIGA (BAILEY BRIDGE) WELL 2. SIGNAGE AND REFLECTORS | 2021-08-25 | Bridge carrying capacity and caution signage not installed on the approach and exit | Install signage on both sides of the bridge 2 Nos | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO OTUSIGA (BAILEY BRIDGE) WELL 2 BRIDGE DECK | 2021-08-25 | Bridge deck chequered plate out of alignment & widening the gap between the steel plates 3.15m x 1.05m (1 No) | Re-align misaligned deck plates. 3.15m x 1.05m (1 No) | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO OTUSIGA (BAILEY BRIDGE) WELL 2 TOE BOARD | 2021-08-25 | Warped and misaligned toe boards as a result of mechanical impact and age induced deformation (150x50mm Z-purlins, 3.15m) 4 Nos | Straighten up the warped toe boards, re-install and re-align properly and fasten to bridge deck members to hold plates firmly in place (150x50mm Z-purlins, 3.15m) 4 Nos | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELLS 5 & 28 (BAILEY BRIDGE) Signage and Reflectors | 2021-08-25 | Bridge carrying capacity and caution signage not installed on the approach | Install signage on both sides of the bridge approach 1 No | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELLS 5 & 28 (BAILEY BRIDGE) Toe board | 2021-08-25 | Missing toe boards on both sides of bridge deck, exposing users to possible slip into the water (150x50mm Z-purlins, 3.15m) 14 Nos | Provide and install toe boards at the edges and make good | H | SPDC-2021-12-00000049
| ELEBELE (STEEL GIRDER BRIDGE) WELL 15 Signage and Reflectors | 2021-08-25 | Bridge carrying capacity and caution signage not installed on the approach and exit | Install signage on both sides of the bridge approach 2 Nos | H | SPDC-2021-12-00000049
| ELEBELE (STEEL GIRDER BRIDGE) WELL 15 Bridge deck Chequered plates | 2021-08-25 | Moderate to severe degradation on steel deck plates Fatigue cracks and holes on plates (16.2 x 5.4m) area | Provide steel plates, Prepare surface & recoat with self priming epoxy primer, polyurethane topcoat or any other approved paint and replace the degraded deck plates and make good | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELL 20 (STEEL GIRDER BRIDGE) Signage and Reflectors | 2021-08-25 | Bridge carrying capacity and caution signage not installed on the approach and exit | Install signage on both sides of the bridge approach 2 Nos | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELL 20 (STEEL GIRDER BRIDGE) Bridge deck Chequered plates | 2021-08-25 | Moderate to severe degradation on steel deck plates Fatigue cracks, warped and torned plates 12.5 x 5.5m area | Provide steel plates, Prepare surface & recoat with self priming epoxy primer, polyurethane topcoat or any other approved paint and replace the degraded deck plates and make good | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELL 20 (STEEL GIRDER BRIDGE) Embankment | 2021-08-25 | Severe cracks sighted on the embankment wall 3-5m Cumm. Length, 10-20mm crack width | Prepare surface and seal up cracks with grade C-35 concrete and make good | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELL 20 (STEEL GIRDER BRIDGE) PIERS AND GIRDERS | 2021-08-25 | Moderate to severe corrosion on steel girders 533 x 210mm IPE, 12.5m long (6 Nos) | Prepare surface & recoat with self priming epoxy primer, polyurethane topcoat or any other approved paint | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELL 14 (BAILEY BRIDGE) BRIDGE PANELS & RAILS | 2021-08-25 | Missing chord reinforcement pins & bolts 30mm Dia (8 Nos) | Install missing chord reinforcement pins and make good | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELL 14 (BAILEY BRIDGE) SIGNAGE AND REFLECTORS | 2021-08-25 | Bridge carrying capacity and caution signage not installed on the approach | Install signage on both sides of the bridge approach 2 Nos | H | SPDC-2021-12-00000049
| ACCESS BRIDGE TO WELL 14 (BAILEY BRIDGE) EMBANKMENT | 2021-08-25 | Significant loss of earth-fill materials of the embankment as a result of Slip failure on pre-cast concrete retaining walls at both ends of the bridge (7.0 x 2.5m area) 2 Nos | Carry out earth works to refill the eroded sections Provide and construct stonepitched walls with grade C-35 concrete to hold earth-fill materials firmly in place | H | SPDC-2021-12-00000049
| BAILEY BRIDGE BOLTED CONNECTIONS/JOINTS | 2021-08-25 | 5No. missing chord reinforcement bolts/Nuts | 5No. missing chord reinforcement bolts/Nuts to be replaced | H | SPDC-2021-12-00000049
| BAILEY BRIDGE BRIDGE APPROACH SIGNAGE | 2021-08-25 | Not sighted on approach and exit sections | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2021-12-00000049
| ADIBAWA STEEL GIRDER BRIDGE 1 APPROACHES TO THE BRIDGE (ABUTMENTS) | 2021-08-25 | Severely degraded road section on approach to bridge 6.0 x 4.3 x 0.35m | Carefully cut the degraded road pavement Provide and re-fill gully with sharp sand and compact Source 0 - 50mm crushed granite rock material and compact to 150mm thick Provide, lay and compact 100mm thick hot-rolled asphaltic concrete | H | SPDC-2021-12-00000049
| ADIBAWA STEEL GIRDER BRIDGE 1 SIGNAGE AND REFLECTORS | 2021-08-25 | Bridge carrying capacity and caution signage not installed on both approaches | Install signage on both sides of the bridge approach 2Nos. | H | SPDC-2021-12-00000049
| BISENI STEEL GIRDER BRIDGE 1 SIGNAGE AND REFLECTORS | 2021-08-25 | Bridge carrying capacity and caution signage not installed on both approaches | nstall signage on both sides of the bridge approach 2Nos | H | SPDC-2021-12-00000049
| BISENI STEEL GIRDER BRIDGE 2 SIGNAGE AND REFLECTORS | 2021-08-25 | Bridge carrying capacity and caution signage not installed on both approaches | nstall signage on both sides of the bridge approach 2 Nos | H | SPDC-2021-12-00000049
| BRIDGES ON ACCESS ROAD LINKING ETELEBOU TO THE DUSTBIN ROAD (GBARAN OIL/NAG MANIFOLDSTEEL GIRDER BRIDGE GUARD RAILINGS | 2021-08-26 | Mild to moderate corrosion on Handrails, Knee Rails and Posts Missing sections of Handrails. Tilted sections of Handrails | Remove corrosion on the railings with hand tools and recoat with Epoxy Esters. Dimensions: - 4Nos 18 m length of 60mm diameter CHS , 32 nos post, - 1.3m CHS | H | SPDC-2021-12-00000049
| STEEL GIRDER BRIDGE BRIDGE APPROACH SIGNAGE | 2021-08-26 | Not sighted on approach and exit sections | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2021-12-00000049
| STEEL GIRDER BRIDGE AFTER DXSF2, GOING TO DUSTBIN JUNCTION.STEEL GIRDER BRIDGE BRIDGE APPROACH CONDITION | 2021-08-26 | Pothole on approach to the bridge Length – 5m Width – 3m | Scarify existing bituminous/asphaltic pavement. Pulverize and rec-compact to form grade. Source 0-50mm crushed granite rock material of approved quality and gradation, transport to site, spread, compact and camber to specified profile in layers not exceeding 100mm thick. Sweep surface clean of dust and other deleterious materials. Lay prime coat using MC0 or MC1 cut-back bitumen at 0.9litres/m2 and blind with sharp river sand.Sweep prime surface clean of sand and lay a tack coat of COLAS A spread at the rate of 0.75litres/m2. Provide, lay and compact 50mm thick Hot rolled Asphaltic Wearing course | H | SPDC-2021-12-00000049
| STEEL GIRDER BRIDGE BRIDGE APPROACH SIGNAGE | 2021-08-26 | Not sighted on approach and exit sections | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2021-12-00000049
| STEEL GIRDER BRIDGE GUARD RAILINGS | 2021-08-27 | Mild to moderate corrosion on Handrails, Knee Rails and Posts Missing sections of Handrails. Tilted/unstable sections of Handrails | Remove corrosion on the railings with hand tools and recoat with Epoxy Esters. Dimensions: - 4Nos 18 m length of 60mm diameter CHS , 32 nos post, - 1.3m CHS Replace missing sections 36m length. 60mm CHS | H | SPDC-2021-12-00000049
| KOROAMA BRIDGE 1 ACCESS CONCRETE GIRDER BRIDGE BRIDGE APPROACH SIGNAGE | 2021-08-27 | Not sighted on approach and exit sections | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2021-12-00000049
| KOROAMA BRIDGE 2 ACCESS CONCRETE GIRDER BRIDGE BRIDGE APPROACH SIGNAGE | 2021-08-27 | Not sighted on approach and exit sections | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2021-12-00000049
| BLOCK C16 AIR CONDITIONER | 2021-12-14 | A/C mounted on partition Wall | Consult with HVAC Engineer for relocation of Air Conditioners in the rooms to the rear Door lintel area 16Nos | H | SPDC-2022-01-00000059 |  | 11908914
| BLOCK D16 AIR CONDITIONER | 2021-12-14 | A/C mounted on partition Wall | Consult with HVAC Engineer for relocation of Air Conditioners in the rooms to the rear Door lintel area 16Nos. | H | SPDC-2022-01-00000059 |  | 11908914
| BLOCK E16 AIR CONDITIONER | 2021-12-14 | A/C mounted on partition Wall | Consult with HVAC Engineer for relocation of Air Conditioners in the rooms to the rear Door lintel area 16Nos. | H | SPDC-2022-01-00000059 |  | 11908914
| BLOCK F16 AIR CONDITIONER | 2021-12-14 | A/C mounted on partition Wall | Consult with HVAC Engineer for relocation of Air Conditioners in the rooms to the rear Door lintel area 16Nos. | H | SPDC-2022-01-00000059 |  | 11908914
1 | GBARAN CENTRAL PROCESSING FACILTY KOLO CREEK AND GBARAN OIL PIG RECEIVERS | 2021-03-24 | Severe cracks on Concrete “T” Support Plinths supporting Bulklines | Provide false work to temporarily prop Bulklines at various intervals and demolish degraded supports. Provide, mix and reconstruct support Plinths with IPE Steel Columns embedded in concrete Horizontal: 0.5m x 0.25m x 0.25m x 15Nos. Vertical: 1.1m x 0.25m x 0.25m x 15Nos. | H | SPDC-2021-05-00000048 |  | 11908381
2 | GBARAN CENTRAL PROCESSING FACILTY OIL INLET MANIFOLD | 2021-03-24 | Severe corrosion with perforations on lower bottom plate | Remove corrosion by grit blasting and cut off section with perforations. Provide, cut to size and weld additional Steel plate. Prepare surface and apply selfpriming Epoxy Primer, Epoxy mid coat and Polyurethane top coat or other approved coating materials on the prepared surface Corroded Area: 4m x 1.5m Steel Plate: 1m x 1m | H | SPDC-2021-05-00000048 |  | 11908381
3 | CPF ZARAMA GAS BULK LINE | 2021-03-24 | Severe cracks on concrete column supporting Pipes | See recommendation from SIA report of 20” Gas Inlet Pipe Support Structure…. (Doc. No. SPDC-2017-10-0000057) | H | SPDC-2021-05-00000048 |  | 11908381
4 | CPF GLYCOL SUMP TANKS 1 & 2 | 2021-03-25 | Severely corroded Pile Supports underneath Platform | Remove corrosion by grit blasting. Weld additional Steel Plate to encase the column. Prepare surface and apply self-priming Epoxy Primer, Epoxy mid coat and Polyurethane top coat or other approved coating materials on the prepared surface 350mm dia. CHS, 0.5m long | H | SPDC-2021-05-00000048 |  | 11908381
5 | GBARAN MAIN ACCESS BRIDGE 5 ABUTMENTS/ EMBANKMENTS | 2021-03-26 | Failed section of embankment | Provide, mix and recast failed section using grade C30 concrete Size = 6m x 5m x 2Nos. | H | SPDC-2021-05-00000048 |  | 11908381
6 | GBARAN MAIN ACCESS BRIDGE 5 SHEET PILES WALLS | 2021-03-27 | Loss of soil materials and missing Sheet Pile Walls. Corroded Steel Cased Piles | Remove corrosion by grit blasting. Carry out earthworks to backfill lost soil materials. Provide and install new and approved Sheet Pile Walls to replace missing ones. Prepare surface and apply selfpriming Epoxy Primer, Epoxy mid coat and Polyurethane top coat or other approved coating materials on the prepared surface 300mm dia. CHS, 6m x 24Nos. 15m x 6m x 2Nos. | H | SPDC-2021-05-00000048 |  | 11908381
7 | ZARAMA WELL 7 CITADEL FENCE | 2021-03-27 | Subsidence underneath base of foundation of fence | Carry out earthworks to back fill eroded materials with sharp sand at the base of foundation of fence and compact in layers 18m x 2.5m x 0.15m | H | SPDC-2021-05-00000047 |  | 11908381
8 |  | 2021-03-27 | Severe cracks on Concrete Foundation | Provide, mix and treat cracks with cement-sand mortar 1.5m x 0.2m x 30mm | H | SPDC-2021-05-00000047 |  | 11908381
9 | ZARAMA WELL 7 CONCRETE ROADS & PAVINGS | 2021-03-27 | Failed section of pavement beside Citadel Fence | Provide, spread and compact sharp sand to 50mm thickness to fill failed section. Provide, mix and place grade C30 Concrete over failed section. Ensure concrete pavement is well cambered from foundation of fence to allow for proper run-off of stormwater into drains 25m x 2.5m x 0.7m | H | SPDC-2021-05-00000047 |  | 11908381
10 | MAIN ACCESS BRIDGE 1 AT OKOLOBIRI GUARDRAILS | 2021-03-31 | Missing/severely corroded sections of Handrails with metal loss and perforations | Cut and cart away severely corroded sections of Handrails. Provide and install new Handrails to replace missing/severely corroded sections. Prepare surface and apply self priming Epoxy primer, Epoxy mid coat, and Polyurethane top coat, or other approved coating materials on the prepared surface 65mm dia. CHS, 33.6m long | H | SPDC-2021-05-00000045 |  | 11908381
11 | MAIN ACCESS BRIDGE 2 AT OKOLOBIRI GUARDRAILS | 2021-03-31 | Severely corroded sections of Handrails with metal loss and perforations | Cut and cart away severely corroded sections of Handrails. Provide and install new Handrails to replace severely corroded sections. Prepare surface and apply self priming Epoxy primer, Epoxy mid coat, and Polyurethane top coat, or other approved coating materials on the prepared surface 65mm dia. CHS, 38.4m long | H | SPDC-2021-05-00000045 |  | 11908381
12 | MAIN ACCESS BRIDGE AT OGBOLOMA GUARDRAILS | 2021-03-31 | Vandalized/missing sections of galvanized Steel Handrails | Provide and install missing sections of galvanised Steel Handrails 100mm dia. CHS, 150m long | H | SPDC-2021-05-00000045 |  | 11908381
13 | GBARAN WELLHEAD 6/ACCESS ROAD WELLHEADS PAVEMENT | 2019-04-20 | Severely degraded concrete slabs beside wellhead. | Provide, mix and cast concrete slabs using grade C30 concrete. 3.3m x 0.9m x 0.15m x 3Nos. | H | SPDC-2019-06-00000007 | SAP | 11727758 | 2020-07-06
14 | GBARAN WELLHEADS 4/9 PERIMETER FENCE | 2019-04-20 | Collapsed/failed sections of fence. | Reconstruct perimeter fence with 9’’ hollow blocks. 15m x 3m & 2 x 3m | H | SPDC-2019-06-00000007 | SAP | 11728091 | 2020-07-06
15 | GBARAN WELLHEAD 6/ACCESS ROAD PERIMETER FENCE | 2019-04-21 | Severely degraded section of perimeter fence at entrance gate. | Demolish degraded fence and cart away debris. Reconstruct fence with 9’’ hollow blocks. Cast columns at mid-section of fence 5 x 3m & 3 x 2.5m Columns: 0.25m x 0.25m x 2Nos | H | SPDC-2019-06-00000007 | SAP | 11727758 | 2020-07-06
16 | GBARAN WELLHEAD 10 PERIMETER FENCE | 2019-04-21 | Severe cracks along three sections of perimeter fence. | Provide, mix and treat cracks with cement mortar. Length=15.2m, Crack Width = 30mm | H | SPDC-2019-06-00000007 | SAP | 11728091 | 2020-07-06
17 |  | 2019-04-21 | Missing section of Perimeter Fence. | Reconstruct missing section of fence with 9” vibrated hollow blocks. 10m x 3m | H | SPDC-2019-06-00000007 | SAP | 11728091 | 2020-07-06
18 | GBARAN WELLHEADS 17/19 PERIMETER FENCE | 2019-04-21 | Severe cracks/partially collapsed section of fence on right side of entrance gate. | Demolish partially collapsed section of fence and cart away debris. Provide 9’’ vibrated hollow blocks and reconstruct partially collapsed section of fence. Area = 2.5 x 2m | H | SPDC-2019-06-00000007 | SAP | 11728091 | 2020-07-06
19 | GBARAN WELLHEADS 20/21/ACCESS ROAD PERIMETER FENCE | 2019-04-22 | Severe subsidence/failed asphalt pavement beside perimeter fence. | * Scarify, excavate and cart away any unsuitable material from failed sections. * Lay boulders and coarse aggregates. * Provide, spread and compact sharp sand to 50mm thickness to fill failed section. * Provide, mix and place grade C30 concrete over failed section. Ensure concrete section is well cambered on both sides to allow for proper run-off of storm water into drains. Thickness of concrete: 75mm Failed Area: 47m x 6.4m | H | SPDC-2019-06-00000007 | SAP | 11728091 | 2020-07-06
20 | GBARAN WELLHEAD 25 PERIMETER FENCE | 2019-04-22 | * Collapsed/failed section of the pavement due to severe erosion and subsidence. Collapsed section of perimeter fence. | * Scarify, excavate and cart away any unsuitable material from failed sections. * Lay boulders and coarse aggregates. * Provide, spread and compact sharp sand to 50mm thickness to fill failed section. * Provide, mix and place grade C30 concrete over failed section. Ensure concrete section is well cambered on both sides to allow for proper run-off of storm water into drains. Thickness of sharp sand: 50mm Thickness of concrete: 75mm Failed Area: 19.2m x 6 Reconstruct collapsed Perimeter Fence using 9’’ hollow blocks. 10.2m x 3m 14.5m x 3m | H | SPDC-2019-06-00000007 | SAP | 11728091 | 2020-07-06
21 | GBARAN WELLHEAD 5/ACCESS ROAD | 2019-04-20 | Severe scouring/degraded sections of the Asphaltic Pavement. | * Cut, excavate and cart away unsuitable material from failed road sections. * Provide, spread and compact sharp sand. * Provide, spread, wet and compact 0-50mm mixed granite materials to a thickness of 150mm as base course * Provide and lay prime coat using MC0 or MC1 cut-back bitumen at 0.9 litres/m2 including blinding with sharp sand * Provide and lay a tack coat using Colas A sprayed at 0.75 litres/m2 * Provide, lay and compact HRA wearing course to a compacted thickness of 50mm. Failed area: 55 x 6m & 42 x 2m | H | SPDC-2019-06-00000007 | SAP | 11728091 | 2020-07-06
22 | GBARAN WELLHEAD 6/ACCESS ROAD ENTRANCE GATE | 2019-04-21 | Broken sections with exposed rebar on the Concrete Columns supporting the Entrance Gate. | Demolish columns and cart away debris. Excavate foundation for column and blind with grade 15 concrete. Cut, fabricate and fix reinforcement bars. Install formwork and cast columns with grade C30 concrete. 0.4m x 0.4m x 3m x 2Nos. | M | SPDC-2019-06-00000007 | SAP | 11728091 | 2020-07-06
KOLO CREEK FLOWSTATION ACTIVIES
23 | ADIBAWA ACTIVITY
24 | BAILEY BRIDGE ON JOINKRAMA ROAD 1 BOLTED CONNECTIONS/JOINTS | 2019-07-30 | 5Nos. missing Chord Reinforcement Bolts/Nuts | Provide and replace 5Nos missing Chord Reinforcement Bolts/Nuts | H | SPDC-2019-08-00000149 | SAP
25 | BAILEY BRIDGE ON JOINKRAMA ROAD 1SIGNAGES ON BRIDGE APPROACHES | 2019-07-30 | No signage was seen on the Bridge Approaches | Provide & install 2Nos. approved reflective road signs in accordance with the Federal Highway Code on Bridge Approaches & Exits | H | SPDC-2019-08-00000149
26 | ADIBAWA WELL 19 TIMBER DECK STEEL GIRDER BRIDGE DECK PLATES PANELS | 2019-07-31 | Missing steel Deck Plates. Timber used as Deck Plates. Some Timber logs missing 13 x 5.4m | Replace entire bridge section with steel Deck Plates complete with bolting accessories. 13 x 5.4m | H | SPDC-2019-08-00000149
27 | ADIBAWA WELL 19 TIMBER DECK STEEL GIRDER BRIDGE SIGNAGES ON BRIDGE APPROACHES | 2019-07-31 | No signage on the Bridge Approaches | Provide & Install 2Nos. approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149
28 | ADIB WELL 12 STEEL GIRDER BRIDGE SIGNAGES ON BRIDGE APPROACHES | 2019-07-31 | No signages on the approach and exit of the Bridge | Provide & Install 2Nos. approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149
29 | BISENI WELLS 2 & 3 ACCESS (After ADIBAWA WELL 4) SIGNAGES ON BRIDGE APPROACHES | 2019-08-01 | No signages on the approach and exit of the Bridge | Provide & Install 2Nos. approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149
30 | JK4 (NO LONGER IN USE BAILEY BRIDGE) PRIMARY GIRDER BEAMS TRANSVERSE AND LONGITUDINAL BEAMS | 2019-08-01 | GENERALLY In good condition. No bent or warped sections of the Pan | RAISE A Z6 TO DELETE THIS BRIDGE FROM THE SAP. DECOMMISION THE BRIDGE | H | SPDC-2019-08-00000149
31 | JK4 (NO LONGER IN USE BAILEY BRIDGE)DECK PLATES PANELS | 2019-08-01 | In good condition. Deck Plates have skid resistant threads in place, no missing Deck Plates Sighted. |  | H | SPDC-2019-08-00000149
32 | JK4 (NO LONGER IN USE BAILEY BRIDGE) CHORD REINFORCEMENT BOLTS | 2019-08-02 | 5 No. Bolts/Nuts missing |  | H | SPDC-2019-08-00000149
33 | JK4 (NO LONGER IN USE BAILEY BRIDGE)SIGNAGES ON BRIDGE APPROACHES | 2019-08-02 | No signages on the approach and exit of the Bridge |  | H | SPDC-2019-08-00000149
34 | JK4 (NO LONGER IN USE BAILEY BRIDGE)CONDITION OF BRIDGE APPROACHES | 2019-08-02 | (approach wearing course). NO LONGER IN USE. |  | H | SPDC-2019-08-00000149
35 | BISENI ACCESS BRIDGE AFTER WELL 10 ACCESS SIGNAGES ON BRIDGE APPROACHES | 2019-08-03 | No signages on the approach and exit of the Bridge | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149
36 | STEEEL GIRDER BRIDGE after DXSF2, CLOSE TO DUSTBIN JUNCTION SIGNAGES ON BRIDGE APPROACHES | 2019-08-03 | Not sighted on approach and exit sections | Provide & Install 2 Nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149
| ETELEBUO FLOWSTATION ACTIVITIES |  |  |  | H
| PERIMETER FENCE | 2020-07-11 | Eroded earth-fill materials along and underneath oundation of Perimeter Fence behind Inlet Manifold 8 x 2.3m area, 0.75m deep | Carry out earthworks to back-fill eroded materials with sharp sand at the base of the fence foundation and compact in layers, and make good | H | SPDC-2020-09-00000019
| ETELEBOU WELL 15 GATE & FENCE | 2020-07-11 | Collapsed section of blockwall Fence 18.7 x 3m area | Re-construct the collapsed section of fence with 150mm masonry block laid in stretcher bond. | H | SPDC-2020-09-00000019
37 | TELECOM BUILDING | 2019-02-19 | Severely degraded/termite infested Ceiling Noggin. | Remove degraded Ceiling Noggins. Provide and install treated 2’ x 4” wooden Noggin 4.6m length. 2Nos. | H | SPDC-2019-02-00000261 | SAP
38 |  | 2019-02-19 | Severely degraded Ceiling Boards. 10.95m long, 0.6m wide, 2Nos. | Remove and cart away degraded Ceiling Board. Provide and install PVC Ceiling Board and make good. Area = (10.95 x 0.6)m x 2Nos. | H | SPDC-2019-02-00000261 | SAP
39 | ETELEBOU OIL MANIFOLD DRAINAGE CHANNEL | 2018-09-10 | • Severe erosion at the drain area and Citadel Fence (near Emergency Gate Access). • No outlet/discharge point for the drainage system out of the facility, the drains are filled with storm water run-off from within the facility. • Erosion of base soil materials off the Ground Beam soffit creating a flow path for runoff through the underside of the Beam. | Fill in with approved fine sand and compact in layers of 150mm. then restore finish surface with granite chippings to flush with the top of the citadel Fence concrete ground beam Area of Fill = 8m x 2.5m Depth of Scour = 0.5m Volume = 8 x 2.5 x 0.5m Create an adequate and efficient drain access away from the facility to an approved discharge point | H | SPDC-2018-09-00000114 | SAP
40 | ETELEBOU WELL 15 & ETELEBOU OIL MANIFOLD SANDCRETE BLOCK FENCE. | 2018-09-10 | • Collapsed Fence length due to loss of embankment and supporting base materials. length - 24m • Fence foundation exposed due to washout of the base soil materials. | Reconstruct the Failed Fence Cast a concrete beam at the base of the Fence to serve as concrete footing connecting to the base of the existing Fence length. Provide and Lay 225mm hollow sandcrete blocks and lay in stretcher bond solidly bedded and joined in 1:3 cement mortar Length – 24m Height, not exceeding 3m from finished ground level. | H | SPDC-2018-09-00000114 | SAP | 11728091 | 2020-07-06
41 | ETELEBOU WELL 15 & ETELEBOU OIL MANIFOLD EMBANKMENT BEHIND THE FENCE | 2018-09-10 | • Embankment stability severely threatened by surface run-off from the facility • Embankment terrain is continuously eroded by the water surge which is currently high presently (rainy season) | Restore Embankment Fill the area with lateritic sand tapering towards the swamp, carry out concrete slope protection works to make good | H | SPDC-2018-09-00000114 | SAP | 11728091 | 2020-07-06
MBIAMA MICROWAVE ACTIVITIES
SOKU FS ACTIVITIES
47 | STEEL SUPPORT STRUCTURES AT THE TEST, HP, LP SEPARATORS AREA | 2019-03-02 | Severe corrosion/ coating failure on steel Beams supporting Grating. | Remove corrosion/degraded coating with hand tools. Weld additional steel plate to strengthen web. Prepare surface and apply selfpriming Epoxy primer, Epoxy midcoat and Polyurethane topcoat or other approved coating materials on the prepared surfaces. IPE Sections: 600 x 300mm, 20mm thick, 20m long (23Nos.) 280 x 230mm UA, 12mm thick, 25m long (20Nos.) | H | SPDC-2019-03-00000102 | SAP | 11728115 | 2020-07-06
48 | SURGE VESSEL SUPPORT BEAM/GRATING SUPPORT. | 2019-03-02 | Severe corrosion with metal loss/coating failure on steel beams. | Remove corrosion/degraded coating with hand tools. Weld additional steel plate to strengthen web. Prepare surface and apply selfpriming Epoxy primer, Epoxy midcoat and Polyurethane topcoat or other approved coating materials on the prepared surfaces. 280 x 120mm IPE x 23Nos., 15mm thick, 25m long. 100 x 70mm UA, 6mm thick, 500m long | H | SPDC-2019-03-00000102 | SAP | 11728115 | 2020-07-06
49 | S OKU FLOW STATION FENDER SYSTEMS | 2019-03-02 | Missing, severely degraded and broken wooden Fenders spaced at 0.5m intervals | Provide and fix fit for purpose Composite Rubber Fenders. 120 Nos. | M | SPDC-2019-03-00000102 |  | 11728115 | 2020-07-06
50 | SOKU FLOWSTATION JETTY BOAT LANDING | 2019-03-02 | HANDRAILS: Severe corrosion/metal loss on Handrails. | Cut and replace severely corroded section of Handrails. 35mm dia., 5m long. | H | SPDC-2019-03-00000102 | SAP | 11728115 | 2020-07-06
51 | GENERATOR HOUSE (DIESEL & GAS) | 2019-03-03 | Collapsed/failed cable tray and cable tray steel support | Replace collapsed/failed cable tray and cable tray steel support. Cable Tray: U Section, 4m long. Steel Support: 50 x 50mm EA, 15.5m long | H | SPDC-2019-03-00000102 | SAP | 11728115 | 2020-07-06
52 | PONTOON BOAT LANDING HANDRAILS: | 2019-06-08 | Extreme corrosion with metal loss on Handrails. | Cut off and remove severely corroded section of Handrails. Fabricate and install steel Handrails to approved design on the Bridge. Prepare surface and apply selfpriming Epoxy primer, mid coat and Polyurethane topcoat or other approved coating materials on the prepared surfaces. 35mm dia. CHS, 2.6m x 2Nos. | H | SPDC-2019-06-00000085 |  | 11728115 | 2020-07-06
53 | PONTOON BOAT LANDING STEEL TOE PLATE | 2019-06-08 | Moderate to severe corrosion with metal loss on Toe Plate. | Prepare surface to remove corrosion and apply self-priming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces. 100 x 100 EAS, 4.6m x 2Nos. | H | SPDC-2019-06-00000085 |  | 11728115 | 2020-07-06
54 | PONTOON BOAT LANDING PLATFORM GRATING SUPPORTS | 2019-06-08 | Severe metal loss/coating failure on Fender support. | Prepare surface to remove corrosion and apply self-priming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces. 60 x 150mm channel, 12m long | H | SPDC-2019-06-00000085 |  | 11728115 | 2020-07-06
55 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF KERBS AROUND ROAD SHOULDERS | 2017-03-17 | Failed and broken sections | Replace 72 Nos kerbs measuring 0.3mx0.6mx0.2m | H | SPDC‐2017‐03‐00000003 | SAP | 11603794 | 2018-05-14 |  | Work Order Nos 22625440 and 22655464 canceelled as Helipad is no more in use and to be decommisioned
56 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF WALKWAY | 2017-03-23 | Failed walk-way, separated at several points | Remove degraded concrete, stabilize slope and carefully step the walkway,provide, mix and use grade C30 concrete to reconstruct the concrete surround. | H | SPDC‐2017‐03‐00000003 | SAP | 11603794 | 2018-05-14
57 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF DRAINAGE | 2017-03-22 | Severe cracks and broken drainage channels Degraded drain floor (Invert level) of drainage 20m Length, 0.4m wide, 0.05m deep. | 6Nos shear cracks on drainage; crack width=10mm, 150mm thick and 200mm deep. Supply and use cement slurry to fill the cracks on the sheared section Scarify damaged areas on the floor of drainage & re-cast floor with grade C30 concrete. Slope in order to provide sufficient gradient on the floor to allow free drainage of water. | H | SPDC‐2017‐03‐00000003 | SAP | 11603794 | 2018-05-14
58 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF FENDERS IN WELL 26,5,12,1,11,30,31,20,28,22,35,4,6,27,41,51,52,10,39,33,34,45,53,14,50 | 2017-03-24 | Missing fenders | Replace Fenders (4Nos) Dimensions; 230 x 190mm Remove corrosion by power brushing, prepare surface and apply 2 coats of Aluminum Epoxy Ester or other approved coating materials on the prepared surface | H | SPDC‐2017‐03‐00000003 | SAP | 11603797 | 2018-05-14 |  | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
59 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF WALKWAYS/GRATINGS WELL 5 | 2017-03-29 | Missing gratings on left wing of lower deck | Replace gratings Dimensions: 3.63m2 | H | SPDC‐2017‐03‐00000003 | SAP | 11603797 | 2018-05-14
60 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF HANDRAILS WELL 5 | 2017-03-25 | Missing /broken handrails -Severe coating loss | Replace missing/handrails Dimensions: 35mm dia., 106m long Remove degraded coating by power brushing; prepare surface and apply 2 coats of Aluminum Epoxy Ester or other approved coating materials on the prepared surface. | H | SPDC‐2017‐03‐00000003 | SAP | 11603797 | 2018-05-14
61 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF SURGE VESSEL STEEL BEAM SUPPORTING FRAME SOKU FLOWSTATION | 2017-03-31 | Severely corroded sections with metal loss & extensively coating failures on steel beams | Grit blast first (Sa 2.5) and weld additional web (plate) material on top of existing web. Full coating system to be applied. Install Transverse Stiffeners for Shear at 2m intervals on UB section to prevent web. | H | SPDC‐2017‐03‐00000003 | SAP | 11603797 | 2018-05-14
62 | CIVIL STRUCT ASSET INTEGRITY ASSESSMENT OF STEEL SUPPORT STRUCTURE AT THE TEST SEPARATOR AREA LP& HP | 2017-03-31 | Severely corroded & extensively failed coating steel beams supporting the flowstation | Grit blast first (Sa 2.5) and weld additional web (plate) material on top of existing web. Full coating system to be applied. | H | SPDC‐2017‐03‐00000003 | SAP | 11603797 | 2018-05-14
63 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENTOF JETTY FENDERS | 2017-03-10 | Timber fenders spaced at 0.5m intervals all damaged providing no protection from vessel impact. | Provide fit for purpose fixed rubber fenders system (e.g. Arch, D-Type or Cylindrical Fender Systems). Replace 120 Nos fenders | H | SPDC‐2017‐03‐00000003 | SAP | 11603797 | 2018-05-14
SOKU GP ACTIVITIES
64 | SOKU GAS PLANT FIRE WATER MANIFOLD | 29-11-2017 | 1. Severe subsidence at the river end section of the Fire Water Manifold. 2. Severe cracks on the concrete foundation of Fire Water Manifold. 3. Fire Water outlet close to sheet pile walls causing scouring at sheet pile base. | Demolish severely corroded concrete pavement, remove loose materials, provide sandbags and lay as support for the pavement. Provide and use C30 concrete reinforced with 12mm dia. reinforcements and reconstruct the demolished pavement. Repair cracks by injection of epoxy based crack repair for narrow cracks. Gently open up wide cracks, fix wire mesh across the cracks ass reinforcement and use C30 concrete to fill the opened cracks. Extend the Fire Water discharge line by welding a 2m long pipe to existing pipe to move the discharge point away from the sheet pile wall. | H | SPDC-2017-12-00000008 | SAP | 11623001 | 31/12/2018 |  | Work planned for execution in 2018/2019 as part of SOKU GP Shore Protection Works
65 | CONTROL ROOM AND MAIN SUBSTATION BUILDINGS ENTRANCE | 2018-01-24 | Degraded blast resistant Doors, defective Locks and Handle, missing Overhead Door Closer, missing Elastomeric Strap, coating failure. | Provide, replace and install new blast proof Doors to meet performance standards; -2.15 x 1.5m Single Leaf. -2.15 X 3.2m Duble Leaf (2Nos.) | H | SPDC-2018-03-00000026 | SAP | 11728138 | 2020-07-26
69 | WALKWAY BETWEEN FIRE STATION AND CHEMICAL BUILDING | 2018-01-24 | Failed section along interlocking paved walkway. | Excavate existing unsuitable and unstable subgrade, around affected area, fill up area with mixed granite materials and compact to about thickness of 200mm, fill sharp sand to 200mm and edge restraint to prevent lateral movement of paving stones. Finally, lay paving stones to required level. Size = 7.2 x 0.5m | H | SPDC-2018-03-00000026 | SAP | NA
72 | EFFLUENT PUMP SHED | 2018-01-24 | Severe concrete failure along side of bundwall at Effluent Pump 1. | Provide, mix and place grade C30 concrete over failed section to required finish. Size = 1 x 0.2 x 0.1m | H | SPDC-2018-03-00000026 | SAP | 11728138 | 2020-07-26
73 | FINAL DISCHARGE SCRUBBER UNIT | 2018-01-24 | Severe shear crack on side of bund wall. | Prepare surface and treat crack with cement mortar. Size = 0.2 x 0.1 x 0.015m | H | SPDC-2018-03-00000026 | SAP | 11728138 | 2020-07-26
74 | PIPE RACK A3 | 2019-03-01 | Severe subsidence along sections of drainage underneath Pipe Rack A3. Subsided Sections: 3.7 x 2.8 x 0.7m 2.6 x 1.5 x 0.2m 2.5 x 0.9 x 0.3m 1.7 x 0.6 x 0.2m 1.0 x 1.0 x 0.6m 1.0 x 0.5 x 0.2m | Provide, mix and treat drainage expansion joints with cement mortar to curb loss of sand into drains. Fill up subsided sections with sharp sand and chippings and compact. | H | SPDC-2019-03-00000102 | SAP | 11728138 | 2020-07-26
75 | HEATING MEDIUM SYSTEM | 2018-01-25 | Severe scouring underneath perimeter wall near staircase. | Provide, mix and place grade C30 concrete to treat scouring underneath perimeter wall. Size = 1.9 x 0.2 x 0.45m | H | SPDC-2018-03-00000026 | SAP | 11728569 | 2020-07-29
76 | SECTION OF PERIMETER FENCE OPPOSITE AG TRAIN 2 AND AG TRAIN 3 | 2018-01-25 | Severe scouring along section of foundation. | Provide, mix and place grade C30 concrete to treat scouring underneath foundation. Size = 160 x 0.3 x 0.15m | H | SPDC-2018-03-00000026 | SAP | 11728569 | 2020-07-29
77 | PERIMETER FENCING AROUND FIRE WATER SHED | 2018-01-25 | Severe subsidence underneath concrete foundation caused by differential settlement. | Provide sand bags to act as temporary structural support for the area affected. Size = 2.5 x 0.35 x 0.15m | H | SPDC-2018-03-00000026 | SAP | 11728569 | 2020-07-29
78 |  | 2018-01-25 | Severe scouring underneath concrete foundation. | Provide, mix and place grade C30 concrete to treat scouring underneath foundation. Size = 2.8 x 0.15 x 0.2m | H | SPDC-2018-03-00000026 | SAP | 11728569 | 2020-07-29
79 |  | 2018-01-25 | Missing concrete foundation along section of Citadel Fence. | Provide, mix and cast foundation along fence with grade C30 concrete. Size = 10.5 x 0.2 x 0.15m | H | SPDC-2018-03-00000026 | SAP | 11728569 | 2020-07-29
80 |  | 2018-01-25 | Roof Cladding: Missing sections of Aluminium Cladding. | Replace missing Aluminium Cladiing. Size = 10 x 3m | H | SPDC-2018-03-00000026 | SAP | 11728569 | 2020-07-29
81 | CHAIN LINK FENCE STORAGE | 2018-01-25 | Roof Cladding: Missing sections of Aluminium Cladding. | Replace missing Aluminium Cladiing. Size = 10 x 3m | H | SPDC-2018-03-00000026 | SAP | 11728138 | 2020-07-26
82 | CONDENSATE STORAGE TANK BUNDWALL | 2019-03-01 | Severe fatigue cracks on tank pad. 110m x 3.05m x 50mm | Scarify top surface of pad, provide, mix and resurface pad with grade C20 concrete. | H | SPDC-2019-03-00000102 | SAP | 11728138 | 2020-07-26
83 | HEAVY DUTY PARKING LOT | 2019-03-02 | Severely degraded concrete ramp with exposed rebars. | Break off degraded concrete ramp, prepare formwork and cast grade C20 concrete complete with reinforcement and make good 10.4m x 0.9m x 0.15m | H | SPDC-2019-03-00000102 | SAP | 11728138 | 2020-07-26
84 | MAIN SUBSTATION BUILDING ENTRANCE | 2019-03-03 | Degraded Blast Doors, defective locks and handle, missing overhead door closer, missing elastomeric strap, coating failure. | Provide, replace and install new Blast Doors to meet performance standards. Single Leaf - 2.15x1.5m (1No.) Double Leaf - 2.15 x 3.2m (2Nos.) | H | SPDC-2019-03-00000102 | SAP | 11728138 | 2020-07-26
85 | PLANT ROOM | 2019-03-03 | Severe corrosion on Skid 1 | Remove corrosion with hand tools. Prepare surface and apply self-priming Epoxy primer, Epoxy mid-coat, and Polyurethane topcoat or other approved coating materials on the prepared surface. 100 x 50mm U Channel; 19m long | H | SPDC-2019-03-00000102 | SAP | 11728569 | 2020-07-29
86 |  | 2019-03-03 | Severe corrosion on Skid 2 | Remove corrosion with hand tools. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid-coat, and Polyurethane topcoat or other approved coating materials on the prepared surface. 100mm x 50mm U Channel; 8m long Flat Plate: 3m x 1m | H | SPDC-2019-03-00000102 | SAP | 11728569 | 2020-07-29
87 | FIRE WATER SHED | 2019-03-03 | Severe subsidence/cracks observed around surrounding Pavement | Use sandbags to provide temporary structural support to the affected areas. 15 x 4m Subsidence Level on concrete pavement: 50 – 100mm. (Ref. Report on Integrity Assessment with doc. No: SPDC-2018-03-00000026). | H | SPDC-2019-03-00000102 | SAP | 11728569 | 2020-07-29
88 | CHAIN LINK STORAGE | 2019-03-03 | Roof Cladding: Missing sections of Aluminium cladding. (10 x 3m) | Replace missing Aluminium cladding. (30m2). | H | SPDC-2019-03-00000102 | SAP | 11728569 | 2020-07-29
89 | PROCESS TRAIN 3 (INLET SEPARATOR) | 2019-03-04 | Passive Fire Protection: Severe degradation of concrete. 2.65m dia; 7m height, 35mm thickness. Severe and moderate cracks on Bundwalls and concrete pavement. 0.9m x 0.12m x 5mm x 12Nos. 0.75m x 0.12m x 25mm x 3Nos | Remove degraded firepRoofing material, prepare surface and re-install full layer of concrete coating over the cylindrical surface of Inlet Separator. Prepare surface and treat crack with cement grout. | H | SPDC-2019-03-00000102 | SAP | 11728569 | 2020-07-29
90 | FLARE STACK AREA | 2019-03-04 | EMBANKMENTS A & B: Severe cracks/failed sections on concrete embankments. Existing Area of Concrete Overlay. 27m x 4.8m x 6Nos. | Scarify existing concrete overlay and cart away spoils from site. Source approved laterite and place as directed, compact, shape formation and trim slopes to required cross section. Provide, cut and fix mild steel BRC 65 mesh reinforcement in concrete. Provide, mix, place and compact to 75mm thickness Grade 25 concrete as embankment overlay. Vol. of Laterite: (27m x 3.4m x 4.8m) x 6Nos. (2643.84m3) Area of BRC: 27m x 4.8m x 6Nos. (777.6m2) Vol. of Concrete Overlay: 27m x 4.8m x 0.075m x 6Nos. (58.32m3) | H | SPDC-2019-03-00000102 | SAP | 11728569 | 2020-07-29
BELEMA FS ACTIVITIES
91 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF FLARE CONTROL VALVE ACCESS PLATFORM | 2017-02-28 | Severely corroded HE Sections | Coating renovation - Remove corrosion with hand tools or grit blasting. Spot repairs on existing coating and application of full coating system | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
92 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ACCESS PLATFORM TO FLARE | 2017-03-04 | Severly Corroded Steel Sections | Coating renovation - Remove corrosion with hand tools or grit blasting. Spot repairs on existing coating and application of full coating system to full film thickness. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
93 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF EP 3 & EP 4 PUMP BAYS. | 2017-03-05 | Severely corroded Steel Beams structures | Prepare steel surface to Sa 2.5 and weld steel plate over perforation in steel section before applying full paint coating system (Zinc rich primer, epoxy mid and top coat or any coating as approved by the principal) | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
94 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF AIR RECIEVER AND COMPRESSOR SUPPORT | 2017-03-06 | Severely corroded Steel Beams supporting the air compressor | Coating renovation - Remove corrosion with hand tools or grit blasting. Spot repairs on existing coating and application of full coating system to full film thickness. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
95 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF FRESH WATER TANK ACCESS AREA | 2017-03-07 | Severely Corroded Steel Support Structures. | Renovation is required. Remove corrosion with hand tools (St 3) and/or by means of light grit blasting (Sa 2). Carry out spot repairs first then apply full coating to the entire structural support. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
96 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF PUMP BAY (5BAYS) | 2017-03-08 | Skids in good condition Severe corrosion on primary supports | Renovation is required. Remove corrosion with hand tools (St 3) and/or by means of light grit blasting (Sa 2). Carry out spot repairs first then apply full coating to the entire structural support. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
97 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF ACCESS PLATFORMIN BESIDES LP SEPARATOR | 2017-03-09 | Severely corroded Steel Beams supporting the access platform | Coating renovation - Remove corrosion with hand tools or grit blasting. Spot repairs on existing coating and application of full coating system to full film thickness. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
98 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF SAMPLING POINT/EFFLUENT MONITORING POINT | 2017-03-10 | Severely Corroded Steel Support Structures. | Replace steel sections in sampling point/effluent monitoring point. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
99 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF TEST SEPARATOR ACCESS | 2017-03-11 | Severely corroded structural beams Severely corroded U-pipe supports under the test separator area. | Extend remedial actions of grit blasting to structural beams supporting test separator platform area. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
100 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF SECOND DECK BELOW INLET MANIFOLD | 2017-03-12 | Severely corroded structural support for gratings in lower deck. | Renovation is required. Remove corrosion with hand tools (St 3) and/or by means of light grit blasting (Sa 2). Adjust distorted bracing. Carry out spot repairs first then apply full coating to the entire structural support. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
101 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF SUPPORT BEAMS | 2017-03-18 | Severe corrosion and metal loss on support beams. I-Section (400x180x16mm) Length 38.4m | Cut, remove and replace the severely degraded I-beam sections (400x180x16mm) 38.4m Length. | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
102 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF INLET MANIFOLD | 2017-03-21 | Corroded Steel Sections (Channel supporting inlet 3” line | Prepare steel surface to Sa 2.5 and weld steel plate over perforation in steel section before applying full paint coating system (Zinc rich primer, epoxy mid and top coat or any coating as approved by the principal) | H | SPDC-2017-03-00000043 | SAP | 11603834 | 2018-05-14 |  | Site inaccessible
103 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF RADIO ROOM | 2017-03-28 | Severely corroded steel frame and primary support structure at the telephone /AC area | Replace 2m length of I-section 220 x 110 x 6mm Replace a total of 16.1m Isection 400mm x 180mm x 8.6mm Replace a total of 4.2m length of I-Section 200mm x 100mm x 5.6mm | H | SPDC-2017-03-00000043 | SAP | 11603861 | 2018-05-14 |  | Site inaccessible
104 | CIVIL/STRUCT ASSET INTEGRITY ASSESSMENT OF FRESH WATER TANK ACCESS AREA | 2017-10-02 | Severely Corroded Steel Support Structures. | Renovation is required. Remove corrosion with hand tools (St 3) and/or by means of light grit blasting (Sa 2). Carry out spot repairs first then apply full coating to the entire structural support. | H | SPDC-2017-03-00000043 | SAP | 11603874 | 2018-05-14 |  | Site inaccessible
105 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF FRESH WATER TANK | 2017-04-02 | Severe corrosion on primary and secondary supports with metal loss Moderate corrosion on roof gutter members | Prepare steel surface to Sa 2.5 and weld steel plate over perforation in steel section before applying full paint coating system (Zinc rich primer, epoxy mid and top coat or any coating as approved by the principal) | H | SPDC-2017-03-00000043 | SAP | 11603874 | 2018-05-14 |  | Site inaccessible
OLOMA FS ACTIVITIES
106 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF FENDERS2 IN WELL 2,12,17,18,6,9,11,15,16,24,27,28,29 | 2017-06-17 | Severely corroded Fender bolts and nuts at splash zone | Remove corrosion by power brushing; prepare surface and apply coats of self Replace wooden Fenders with rubber Fenders – 4Nos 4m long 150x150mm | H | SPDC-2017-08-00000039 | SAP | 11604138 | 2018-10-10 |  | Work Planned for execution in 2019 (included in OP18 Budget Plan)
107 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF FIXED VERTICAL LADDERS IN WELL 2,12,17,18,6,11,14,15,23,24,25,27,28,29 | 2017-06-20 | Marine growth/Severely corroded lower rungs below splash zone | Replace severely corroded lower rungs; 4Nos 650mm long 16mm dia rungs @ 250mm centres | H | SPDC-2017-08-00000039 | SAP | 11604138 | 2018-10-10 |  | Work Planned for execution in 2019 (included in OP18 Budget Plan)
108 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF SSTRUCTURAL STEEL FRAME INCLUDING SECONDARY SUPPORT BRACINGS AND BASE PLATES IN WELL 12,16,17,18,2,6,9,11,14,15,1,26,25,28,29 | 2017-06-24 | Severely/Moderately corroded structural steel secondary supports | Remove corrosion by power brushing; prepare surface and apply coats of self priming epoxy, high build epoxy midcoat, high build polyurethane topcoat or other approved coating materials on the prepared surfaces. | H | SPDC-2017-08-00000039 | SAP | 11604138 | 2018-10-10 |  | Work Planned for execution in 2019 (included in OP18 Budget Plan)
BONNY FS ACTIVITIES
109 | BOGT JETTY (BERTH 3) BOLLARD 5 - 6 | 2019-05-29 | 5.7m from Bollard 5 and 2m from top of concrete capping Beam. Torn Sheet Piles walls Circa. (1.2m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
110 | BOGT JETTY (BERTH 3) BOLLARD 6 - 7 | 2019-05-29 | 9.3m from Bollard 6 and 2.75m from top of Concrete Capping Beam. Torn Sheet Piles walls Circa. (1.5m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
111 | BOGT JETTY (BERTH 3) BOLLARD 7 - 8 | 2019-05-29 | 6.8m & 7m from Bollard 7. 2.8m from top of top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.1m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
112 | BOGT JETTY (BERTH 3) BOLLARD 8 - 9 | 2019-05-29 | 4.5 & 5.1m from Bollard 8. 2.8m from top of Concrete Capping Beam. Torn Sheet Piles walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
113 |  | 2019-05-29 | 6m & 6.1m from Bollard 8. 2.68m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.1m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
114 |  | 2019-05-29 | 7.2m from Bollard 8; 3.2m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.25m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
115 | BOGT JETTY (BERTH 3) BOLLARD 9 - 10 | 2019-05-29 | 0.5m from Bollard 9; 2.7m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
116 |  | 2019-05-29 | 2m from Bollard 9; 2.6m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
117 |  | 2019-05-29 | 2.7m from Bollard 9; 2.6m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
118 |  | 2019-05-29 | 5m from Bollard 9; 2.6m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
119 | CIVIL STRUCT ASSET INTEGRITY ASSESSMENT OF TANKS (T-3407 A&B) BUNDWALL | 2017-06-17 | Bundwall perimeter (120 x 70m), 3m long inclined length. Staircase in good condition. Silted drains beside bundwall. 90% degradation of bituminous overlay along sections of the wall and on the Tank pad. | Desilt drainages to allow uninterrupted flow of water Carefully demolish & cart away the failed sections of bituminous/asphaltic overlay. Carry out earthworks to refill degraded sections with minor defects. Supply & lay fresh bitumen/ asphalt on the compacted earth fill to make good. 2660m2 | H | SPDC-2017-08-00000039 | SAP | 11604134 | 2018-10-10 |  | Remedial Works planned for execution in 2019 (included in OP18 Budget Plan)
120 | CIVILSTRUCT ASSET INTEGRITY ASSESSMENT OF JETTY CONCRETE SURFACE | 2017-06-07 | Exposed reinforcement strands, settlement observed. Isolated failed concrete sections sighted as the subgrade underneath the concrete is eroded | Break off degraded pavement, provide, mix and place grade C30 concrete 20mm aggregate min cement content 360kg/m3 and use to reconstruct concrete pavement. | H | SPDC-2017-08-00000039 | SAP | 11604138 | 2018-10-10 |  | Contractor, ZEF NIG. LTD on site, completed breaking/removal of 2no failed concrete bays, progressed fabrication of steel sheet pile sections to close/block slot holes on sheet pile wall.
SOKU FS ACTIVITIES
| GUARD HUT 2 | 2022-05-11 | Broken section of handrail concrete support | Provide, mix and recast reinforced concrete slab covers with grade C30 concrete to repair broken section | H | SPDC-2022-05-00000036
| GUARD HUT 3 |  | Broken sections of concrete beams and concrete spalling of concrete with exposed corroded reinforcements on deck beams and slabs | Provide, mix and recast reinforced concrete slab covers with grade C30 concrete to replace broken/spalled off sections | H | SPDC-2022-05-00000036
|  |  | Severe concrete spalling with exposed corroded reinforcements underneath staircase slab | Carefully expose corroded reinforcements and remove corrosion with handtools. Provide, mix and recast reinforced concrete slab covers with grade C30 concrete to repair underside of the staircase slab | H | SPDC-2022-05-00000036
| SOKU JETTY LIGHT FLIGTH AREA | 2022-02-08 | Broken section of guardrails on pontoon landing | Remove and cart away broken guardrails from site. Provide angle iron of specified dimensions, cut to size and fix including welding 100 x100 EA, 6.5m length | H | SPDC-2022-03-00000002
| FLARE STACK AREA | 2022-02-08 | FLARE CONCRETE EMBARKMENT A & B Failed sections of concrete embankments Existing area of Concrete Overlay = 27m x 4.8m x 12Nos. | Scarify existing concrete overlay and cart away spoils from site. Source sharp sand and place as directed, compact, shape formation and trim slopes to required cross section. Provide, cut and fix mild steel BRC 65 mesh reinforcement in concrete. Provide, mix, place and compact to 100mm thickness Grade 25 concrete as embankment overlay Vol. of sand: (27m x 3.4m x 4.8m) x 6Nos. (15,863.04m3 ) Area of BRC: 27 x 4.8m x 6Nos. (777.6m2 ) Vol. of Concrete Overlay: 27m x 4.8m x 0.1m x 6Nos. (77.76m3 ) | H | SPDC-2022-03-00000002
|  | 2022-02-08 | Failed concrete floor at stack B | Demolish and cart away from site failed section. Provide, spread and compact sharp sand to a depth of 250mm. Provide, mix and place BRC reinforced grade C25 concrete and made good 9m x 2.5m x 0.1m | H | SPDC-2022-03-00000002
|  | 2022-02-08 | Broken section of rigid pavement to flare stack B | Cut off to rectangular shape and cart away spoil from site. Provide, mix and place BRC reinforced grade C30 concrete and made good 4.5m X 0.15m x 0.1m | H | SPDC-2022-03-00000002
| FIRE TENDER BUILDING | 2022-02-08 | Toilet Severely degraded ceiling boards | Carry out Roof spot repair to prevent further leakages. Remove and cart away degraded Ceiling board. Provide and install new Ceiling boards to replace degraded ones Area = 0.6 x 0.6m x 6Nos. | H | SPDC-2022-03-00000002
|  | 2022-02-08 | Service pit Severe corrosion and warped Grating platforms | Remove and cart away Gratings from site. Provide, cut to size and install galvanized Grating platforms 9 x 1m | H | SPDC-2022-03-00000002
| RESTURANT BUILDING | 2022-02-08 | Dry store/Provision store Severely degraded ceiling boards | Carry out Roof spot repair to prevent further leakages. Remove and cart away degraded Ceiling board. Provide and install new Ceiling boards to replace degraded ones Area = 0.6 x 0.6m x 24Nos | H | SPDC-2022-03-00000002
|  | 2022-02-08 | Male cloakroom Severely degraded ceiling boards | Carry out Roof spot repair to prevent further leakages. Remove and cart away degraded Ceiling board. Provide and install new Ceiling boards to replace degraded ones Area = 0.6 x 0.6m x 8Nos | H | SPDC-2022-03-00000002
|  | 2022-02-08 | Technical room Severely degraded ceiling boards | Carry out Roof spot repair to prevent further leakages. Remove and cart away degraded Ceiling board. Provide and install new Ceiling boards to replace degraded ones Area = 0.6 x 0.6m x 6Nos. | H | SPDC-2022-03-00000002
|  | 2022-02-08 | Defective exit door. Broken door hinges | Remove and cart away door from site. Provide and install fit for purpose door and make good 2.1 x 0.9m x 1No. | H | SPDC-2022-03-00000002
| LAUNDARY BUILDING | 2022-02-08 | Broken door hinges | Provide and weld fit for purpose hinges to door 2Nos. | H | SPDC-2022-03-00000002
42 | PIG LAUNCHER | 2021-05-29 | Failed steel shed over instrument valve box. | Remove failed stanchions and base plates. Provide circular hollow steel and base plate of specified dimensions, cut to size and welding.89mm dia. CHS, 2.1m x 2Nos x 6.3mm steel thickness. 300mm x 300mm x 2Nos. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane topcoat or other approved coating materials on the prepared surface 89mm dia. CHS, 2.1m x 2Nos | H | SPDC-2019-03-00000102
43 | SURGE VESSEL | 2021-05-29 | Extremely corroded section of steel beam Grating support underneath walkway Platform by vessel | Remove and cart away extremely corroded section of beam. Provide universal beam of specified dimensions, cut to size and welding.Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane topcoat or other approved coating materials on the prepared surface 305 x 165mm x 54 I-Beam, 2.5m long | H | SPDC-2019-03-00000102
44 | PUMP/ GENERATOR SHED | 2021-05-29 | Extremely corroded section and metal loss on Grating supports and drain pan by Pump Bay 1 facing the river | Cut off corroded section of drain pan and Grating support. Provide channel, equal angle section and mild steel plate of specified dimensions, cut to size, weld as required and install. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane topcoat or other approved coating materials on the prepared surface Grating Support: 230 x 60mm PFC, 1.35m long x 15mm thickness 100 x 70mm UAS, 1.7m long x 6mm steel thickness Drain Pan: = 1.3m x 1.2m | H | SPDC-2019-03-00000102
45 |  | 2021-05-29 | Severe corrosion with metal loss steel beam Grating support by Pump1 | Remove corrosion with hand tools. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane topcoat or other approved coating materials on the prepared surface 250mm x 150mm I-beam, 2.5m long | H | SPDC-2019-03-00000102
46 |  | 2021-05-29 | Extreme corrosion with metal loss on steel pipe support underneath walkway Grating Platform by freshwater tank | Replace corroded steel with new one. Prepare surface and apply self-priming Epoxy primer, Epoxy mid coat and Polyurethane topcoat or other approved coating materials on the prepared surface 80mm x 80mm EAS, 3.5m long | H | SPDC-2019-03-00000102
| LIGHT FLIGTH AREA | 2021-02-08 | Broken section of guardrails on pontoon landing | Remove and cart away broken guardrails from site. Provide angle iron of specified dimensions, cut to size and fix including welding 100 x100 EA, 6.5m length | H | SPDC-2022-03-00000002
47 | FENDER AND FENDER SYSTEM | 2021-05-30 | Severely degraded and missing wooden fenders | Remove and cart away all wooden fenders from site. Provide and install rectangular sharp rubber fenders - 64Nos. Alternatively, Replace all wooden fenders with cylindrical Polyurethane fenders at a spacing of 1.5m from each other - 25Nos. Provide universal beam of specified dimensions a fender supports, cut to size and welding horizontally for anchoring of marine chains. 300 x 150mm I-beam, 60m long Provide galvanized Marine Chains to hold the Fenders in positions and anchored to the Fender supports - 25Nos. |  | SPDC-2019-03-00000102
48 | PONTOON JETTY | 2021-05-30 | Extreme corrosion with metal loss on Guardrails. Severe corrosion with metal loss on Guardrails | Provide circular hollow section of specified dimensions, cut to size and weld as guard rail and posts. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane topcoat or other approved coating materials on the prepared surface 50mm dia. CHS, 60m long |  | SPDC-2019-03-00000102
49 |  | 2021-05-30 | Severely corroded Grating supports | Provide steel sections of specified dimensions, cut to size and weld as required. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane topcoat or other approved coating materials on the prepared surface. Grating supports: 100 x 100mm EAS, 33.6m long. 203 x 133mm I-beam, 32.4m long Pontoon steel connections: 305 x 102mm I-beam, 7.2m long |  | SPDC-2019-03-00000102
50 |  | 2021-05-30 | Missing Fenders | Provide and install Rubberized Wharf Fenders, made up of Polythene Materials with fiber glass reinforcement bars. Size = 0.2 x 0.2 x 12m |  | SPDC-2019-03-00000102
51 | BOAT LANDING WELLHEAD 8 | 2021-05-31 | Missing fenders and steel Fender support | Provide and install Rubberized Wharf Fenders, made up of Polythene materials with fiber glass Reinforcement bars. 0.2 x 0.2 x 3m x 2Nos. Cut off and cart away remains of projected corroded circular hollow steel. Provide circular hollow steel and angle iron of specified dimensions, cut to size and welding to support 120mm dia. CHS, 6m long 100 x 100mm x 15mm EAS, 0.3m x 4Nos. |  | SPDC-2019-03-00000102
52 |  | 2021-05-31 | Moderate - severe corrosion on steel Fender supports | Prepare surface and apply selfpriming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces 100 x 100mm EAS, 0.3m x 8Nos. 120mm dia. CHS, 15m long |  | SPDC-2019-03-00000102
53 | LOWER DECK PLATFORM WELLHEAD 8 | 2021-05-31 | Severe corrosion with metal loss on Grating supports | Remove corrosion with hand tool. Prepare surface and apply self-priming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces Grating supports: 100 x 60mm channel, 15.6m long 100mm dia., 1.3m x 8Nos. |  | SPDC-2019-03-00000102
54 | WELL CASING WELLHEAD 8 | 2021-05-31 | Extremely corroded and broken pipe clamp | Replace Wellhead pipe clamp with new one. |  | SPDC-2019-03-00000102
55 | SOKU WELLHEAD 25 BOAT LANDING | 2021-06-01 | Missing Fender | Provide and install Rubberized Wharf Fenders, made up of Polythene materials with fiber glass Reinforcement bars. 0.2 x 0.2 x 3m x 1Nos |  | SPDC-2019-03-00000102
56 | SOKU WELLHEAD 31 BOAT LANDING | 2021-06-01 | Missing Fenders | Provide and install Rubberized Wharf Fenders, made up of Polythene materials with fiber glass Reinforcement bars. 0.2 x 0.2 x 3m x 4Nos. |  | SPDC-2019-03-00000102
57 |  | 2021-06-01 | Severely corroded Fender supports | Prepare surface and apply selfpriming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces 100 x 100mm EAS, 0.3m x 8Nos. 120mm dia. CHS, 15m long |  | SPDC-2019-03-00000102
58 | SOKU WELLHEAD 27 WELL CASING | 2021-06-01 | Severe corrosion with metal loss on well casing | Prepare surface and apply selfpriming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces. 0.8m dia. CHS, 2.5m length. Provide, mix and cover of steel well case with water repellant mortar 0.8m dia. CHS, 0.5 length. |  | SPDC-2019-03-00000102
59 | SOKU WELLHEAD 49 BOAT LANDING | 2021-06-02 | Severely degraded wooden Fenders | Remove and cart away wooden Fenders. Provide and install Rubberized Wharf Fenders, made up of Polythene materials with fiber glass Reinforcement bars. 0.2 x 0.2 x 3m x 4Nos. |  | SPDC-2019-03-00000102
60 | SOKU WELLHEAD 14 BOAT LANDING | 2021-06-02 | Missing Fenders | Provide and install Rubberized Wharf Fenders, made up of Polythene Materials with fiber glass reinforcement bars. 0.2 x 0.2 x 3m x 4Nos |  | SPDC-2019-03-00000102
61 |  | 2021-06-02 | Severely corroded Fender supports | Prepare surface and apply selfpriming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces 100 x 100mm EAS, 0.3m x 8Nos. |  | SPDC-2019-03-00000102
SOKU GP ACTIVITIES
62 | FLARE STACK AREA | 2020-10-09 | Embankments A & B: Severe cracks/failed sections on concrete embankments Existing area of Concrete Overlay = 27m x 4.8m x 6Nos. | Scarify existing concrete overlay and cart away spoils from site. Source sharp sand and place as directed, compact, shape formation and trim slopes to required cross section. Provide, cut and fix mild steel BRC 65 mesh reinforcement in concrete. Provide, mix, place and compact to 75mm thickness Grade 25 concrete as embankment overlay Vol. of sand: (27m x 3.4m x 4.8m) x 6Nos. (2643.84m3 ) Area of BRC: 27 x 4.8m x 6Nos. (777.6m2 ) Vol. of Concrete Overlay: 27m x 4.8m x 0.075m x 6Nos. (58.32m3 ) | H | SPDC-2020-11-00000080
63 | MAIN SUB-STATION BUILDING HIGH VOLTAGE SWITCH ROOM | 2020-10-09 | Exit Door Defective Blast Resistant Door | Provide and install new BlastResistant Door to meet performance standards Double Leaf – 3.2m x 2.15m | H | SPDC-2020-11-00000080
BELEMA FS ACTIVITIES
64 | BELEMA TELECOM MAST & RADIO ROOM Telecom Radio Room Structural Support Members | 2021-08-27 | Severely corroded perimeter steel frame and primary support members at the telephone /AC area | Replace 3.1m length of I-section 220 x 110 x 6mm Replace a total of 18m I- section 460 x 180 x 8.6mm Replace a total of 4.2m length of ISection 200 x 100 x 5.6mm | H | SPDC-2021-03-00000086
65 | Access Walkway by Radio Room Toe Plates at Access Platform of Telecom Tower | 2021-08-27 | Severely corroded perimeter structural steel supports with some metal losses Moderately corroded toe plates | Replace impacted members with details below. 16m length of I section 460 x 180 x 8.6mm 17m length of I section 400 x 230 x 8.6mm Replace toe plates at the radio room with dimensions: 2(1.3 x 7.6) = 19.76mm | H | SPDC-2021-03-00000086
66 | Chemical Store and Metering Skid Areas | 2021-08-27 | Severely corroded structural beams supporting Gantry and Chemical Shed area | Extend remedial actions of grit blasting to structural beams supporting Chemical Store.3Nos. IPE 450 x 180 x 7mm. Total Length: 26m 7Nos. IPE 280 X 180 x 6mm. Total Length: 26m Toe plate: Total Length: 26m IPE 300 x 180 x 7mm. Total Length: 12m IPE 480 X 180 X 6mm. Total Length: 7.1m | H | SPDC-2021-03-00000086
67 | Access Platform in front of Chemical Injection System | 2021-08-27 | Severely corroded Steel Beams supporting the Platform and Vessels | Coating renovation - Remove corrosion by grit blasting. Spot repairs on existing coating and application of full coating system to full film thickness 3Nos. IPE Section 460 x 180 x 6mm. Total Length = 8m 4Nos. IPE 260 x 160 x 6mm. Total Length = 13m | H | SPDC-2021-03-00000086
68 | Inlet Manifold | 2021-08-27 | Corroded Steel Sections supporting Inlet Manifold. Channel supporting Inlet 3” Line | Prepare steel surface to Sa 2.5 and weld steel plate over perforation in steel section before applying full paint coating system (Zinc rich primer, epoxy mid and topcoat or any coating as approved by the principal) Chanel Section 150mm x 50mm Total Length: 15m | H | SPDC-2021-03-00000086
69 | 2 nd Deck Below Inlet Manifold | 2021-08-27 | Severely corroded structural supports for Gratings in lower deck | Renovation is required. Remove corrosion with hand tools (St 3) and/or by means of light grit blasting (Sa 2). Adjust distorted bracing. Carry out spot repairs first then apply full coating to the entire structural supports. Channel 100 x 50mm. Length = 20m Replace channel at lower deck of Inlet Manifold. Total length -10m | H | SPDC-2021-03-00000086
70 | Test Separator Access Platform | 2021-08-27 | Severely corroded structural beams Severely corroded U-pipe supports under the Test Separator area | Extend remedial actions of grit blasting to structural beams supporting Test Separator Platform area. Channel: 150 x 90mm. Length: 7m | H | SPDC-2021-03-00000086
71 | Sampling Point /Effluent Monitoring Point | 2021-08-27 | Severely corroded Steel Support Structures | Replace steel sections in sampling point/effluent monitoring point. Measured Dimensions: Longitudinal members: Channelsection 150 x 90 x 24mm. Length = 15m 5Nos. I section: 300 x 150 x 7.1mm Length: 10m Secondary member: 10Nos. EA Sections 80 x 80mm. Length 15m | H | SPDC-2021-03-00000086
72 | Access Platform in LP Separator | 2021-08-27 | Severely corroded Steel Beams supporting the Access Platform | Coating renovation - Remove corrosion with hand tools or grit blasting. Spot repairs on existing coating and application of full coating system to full film thickness. Longitudinal Sections: 3Nos. 4m length HE sections 400 x 300mm x 13.5mm Transverse Sections: 4Nos. 8m Length 250 x 240 x 10mm | H | SPDC-2021-03-00000086
73 | Freshwater Tank | 2021-08-27 | Severe corrosion on primary and secondary supports with metal loss | Prepare steel surface to Sa 2.5 and weld steel plate over perforation in steel section before applying full paint coating system (Zinc rich primer, epoxy mid and topcoat or any approved coating paint) HE Beam – 152 x 160mm x 6mm. Length – 14m UA – 100 x 80mm. Length = 100m U-channel (100mm) 1.2m long 12Nos. | H | SPDC-2021-03-00000086
74 | Pump Bay (5 Bays) | 2021-08-27 | Skids in good condition Severe corrosion on primary supports | Renovation is required. Remove corrosion with hand tools (St 3) and/or by means of light grit blasting (Sa 2). Carry out spot repairs first then apply full coating to the entire structural support. I-section 400 x 180 x 9mm. Length = 40m EA 100 x 100 x 6mm. Length – 10m | H | SPDC-2021-03-00000086
75 | Storage Shed by Pump Bay | 2021-08-27 | Severe ponding inside Skid plates | Clean out water from pump bay | H | SPDC-2021-03-00000086
76 | Fresh Water Tank Access Area | 2021-08-27 | Severely Corroded Steel Support Structures | Renovation is required. Remove corrosion with hand tools (St 3) and/or by means of light grit blasting (Sa 2). Carry out spot repairs first then apply full coating to the entire structural support Measured Dimensions: IPE 400 X 180 X 9mm. Length = 14m IPE – 160 x 82 x 5mm. length = 6m IPE - 245 x 118 x 7.5mm. Length = 10m | H | SPDC-2021-03-00000086
77 | Air Receiver and Compressor Support | 2021-08-27 | Severely corroded Steel Beams supporting the air compressor | Coating renovation - Remove corrosion with hand tools or grit blasting. Spot repairs on existing coating and application of full coating system to full film thickness Measured Dimension: IPE Sections: 270 x 135 x 6.6mm. Length = 3m Channel section: 180 x 75 x 20mm Length = 3m IPE Section – 450 x 190 x 9.4mm. Length = 15m | H | SPDC-2021-03-00000086
78 | EP 3 & EP 4 Pump Bays | 2021-08-27 | Severely corroded Steel Beam structures | Prepare steel surface to Sa 2.5 and weld steel plate over perforation in steel section before applying full paint coating system (Zinc rich primer, epoxy mid and topcoat or any coating as approved by the principal) HE -150 x 75 x18mm. Length - 28m IPE - 400 x 180 x 8.6mm. Length = 17m | H | SPDC-2021-03-00000086
79 | Access Platform to Flare | 2021-08-27 | Severely Corroded Steel Sections | Coating renovation - Remove corrosion with hand tools or grit blasting. Spot repairs on existing coating and application of full coating system to full film thickness. Measured Dimension: 240 x 120 x 6.2mm. Total length =10m | H | SPDC-2021-03-00000086
80 | Flare Control Valve Access Platform | 2021-08-27 | Severely corroded HE Sections Missing Grating Clips on flare Platform | Coating renovation - Remove corrosion with hand tools or grit blasting. Spot repairs on existing coating and application of full coating system HE Sections:180 x 180 x 8.5mm; 22m long 150 x 90 x 6.0mm; 10m long Replace 30Nos. Grating Clips | H | SPDC-2021-03-00000086
81 | Fenders | 2021-08-27 | 22Nos. Chipped off and broken timber Fenders. 3 missing Fenders. Timber Fenders susceptible to marine degradation. | Provide fit for purpose fixed rubber Fenders system (e.g. Arch, D-Type or Cylindrical Fender Systems). Spaced (0.15 x Vessel LOA max.) Replace 125 Nos Fenders | H | SPDC-2021-03-00000086
82 | WATER TREATMENT PLANT Ceiling boards | 2021-08-27 | Severely degraded Ceiling boards | Remove and cartaway degraded Ceiling boards. Provide and install new Ceiling boards to replace degraded ones 7m x 0.6m x 2Nos. 6.2m x 0.6m x 2Nos. | H | SPDC-2021-03-00000086
83 | Steel Gates | 2021-08-27 | Severely corroded Steel Gates with metal loss and perforations | Provide and install new Steel Gates to replace severely corroded ones 2.1m x 1.8m 2.1m x 0.8m | H | SPDC-2021-03-00000086
84 | OFFICE BUILDING:PVC Ceiling strips/Ceiling boards | 2021-08-27 | Missing sections of PVC Ceiling strips | Provide and install new PVC Ceiling strips to replace missing ones 0.9m x 0.45m x 3Nos. | H | SPDC-2021-03-00000086
85 |  | 2021-08-27 | Degraded Ceiling board | Provide and install new Ceiling board to replace degraded one 0.6m x 0.6m | H | SPDC-2021-03-00000086
86 | Drainage | 2021-08-27 | Broken and degraded drainage covers | Provide, mix and recast drain covers using grade C30 concrete 29.5m x 0.46m | H | SPDC-2021-03-00000086
87 | Handrails | 2021-08-27 | Missing sections/severe pitting corrosion with metal loss and perforations on Handrails | Provide and install new Handrails to replace missing/severely corroded ones. Prepare surface and apply Zinc Oxide coating and then two coats of approved protective coating on the new Handrails 50mm dia. CHS, 87.5m long | H | SPDC-2021-03-00000086
88 | Kitchens | 2021-08-27 | Missing and degraded Ceiling boards | Provide and install new Ceiling boards to replace missing and degraded ones 2.4m x 2.4m x 2Nos | H | SPDC-2021-03-00000086
89 | OPS2 & OPS3 Rooms | 2021-08-27 | Missing and degraded Ceiling boards | Provide and install new Ceiling boards to replace missing and degraded ones 0.6m x 0.6m x 9Nos | H | SPDC-2021-03-00000086
90 | Telecoms Room | 2021-08-27 | Missing and severely degraded Ceiling boards | Provide and install new Ceiling boards to replace missing and degraded ones 4.8m x 3.6m | H | SPDC-2021-03-00000086
91 | Briefing Room | 2021-08-27 | Missing and severely degraded Ceiling boards | Provide and install new Ceiling boards to replace missing and degraded ones 4.8m x 3.6m | H | SPDC-2021-03-00000086
92 | Bedrooms for Military (2Nos.) | 2021-08-27 | Missing and severely degraded Ceiling boards | Provide and install new Ceiling boards to replace missing and degraded ones 3.6m x 3.6m x 2Nos | H | SPDC-2021-03-00000086
93 |  | 2021-08-27 | Missing sliding Glass Windows | Provide and install new sliding Glass Windows to replace missing ones 1.8m x 1.15m x 2Nos. | H | SPDC-2021-03-00000086
94 | BELEMA WELLHEAD PLATFORM 8T Lower Platform Structural Support | 2021-08-27 | Severe corrosion with metal loss on structural supports | Coating renovation as above. Dimensions: 6Nos. 0.9m Channel: 80 x 40. Total length = 5.4m 12Nos. 0.6m transverse Angle iron: 80 x 40 Total Length = 7.2m 10Nos. 2m 80mm dia. CHS. Total length = 20m | H | SPDC-2021-03-00000086
95 | Conductor Casings and Diagonal Bracings Lower Structural CHS Members, Conductor Anchor, and Fender Support | 2021-08-27 | Severe corrosion with metal loss on conductor casing and diagonal bracing. Diagonal bracings corroded with severe metal loss. Moderate coating failure with marine growth. | Cut and weld new diagonal bracings to conductor. Dimension: Nos IPE 220 x120 x 8mm Total length: 4.8m Coating renovation on conductor casing as described in row 1 above. Coat 6Nos. 1.6m length CHS (120 dia.). Total length: 9.6m Coat 2Nos. 5m length (CHS 120 dia.) Total length: 10m | H | SPDC-2021-03-00000086
96 | BELEMA WELLHEAD PLATFORM 6L/S: Lower Platform Structural Support | 2021-08-27 | Severe corrosion with metal loss on structural supports. | Cut and replace structural members in Lower Deck Platform Dimensions: 6Nos. 0.9m Channel: 80 x 40mm Total length = 5.4m 12Nos. 0.6m transverse UA: 80 x 40mm Total Length = 7.2m 10Nos. 2m long 80mm dia. CHS. Total length = 20m | H | SPDC-2021-03-00000086
97 | Conductor Casings and Diagonal Bracings Lower Structural CHS Members, Conductor Anchors, and Fenders Support | 2021-08-27 | Severe corrosion & coating failure on conductor casing and diagonal bracing. Moderate coating failure with marine growth | Coating renovation for Casing as required Dimension: IPE 220 x120 x 8mm Total length = 4.8m Coating renovation on lower structural CHS members, Conductor Anchor, and Fenders Support Coat 6Nos. 1.6m length CHS (120 dia.). Total length = 9.6m Coat 2Nos. 5m length (CHS 120 dia.) Total length = 10m | H | SPDC-2021-03-00000086
98 | BELEMA WELLHEAD PLATFORM 1L/S: Lower Platform Supports – (seasonally submerged) | 2021-08-27 | Severe corrosion with metal loss on structural supports | Coating as above. Dimensions: 6Nos. 0.9m Channel: 80 x 40mm Total length = 5.4m 12Nos. 0.6m transverse UA: 80 x 40mm Total Length = 7.2m 10Nos. 2m 80mm dia. CHS. Total length = 20m | H | SPDC-2021-03-00000086
99 | Conductor Casings and Diagonal Bracings Lower Structural CHS Members, Conductor Anchors, and Fenders Supports Handrails Gratings/Fenders /Davit. Toe Plates | 2021-08-27 | Severe corrosion & coating failure on Conductor Casing and Structural Supports Moderate coating failure with marine growth. Damaged and severely corroded Severely corroded Grating. 4 Fenders in good condition. Mild coating failure | Cut and weld new diagonal bracings to the Conductor. Dimension: IPE 220 x120 x 8mm Total length: 4.8m Coating renovation on lower structural CHS members, Conductor Anchors, and Fenders Supports Coat 6Nos. 1.6m length CHS (120 dia.). Total length = 9.6m Coat 2Nos. 5m length (CHS 120 dia.) Total length = 10m Repair ladder and restore coating loss. Dimension: 40m length of Handrails requires replacement and coating. Replace Gratings at lower deck Platform.10.6 sq.m Recertify and recalibrate davit 55m length of Toe Plate requires coating | H | SPDC-2021-03-00000086
100 | BELEMA WELLHEAD PLATFORM 10L/S: Handrails Gratings/Fenders /Davit. Toe Plates Access Ladder | 2021-08-27 | Damaged and moderate coating failure 2 missing Fenders. Mild coating failure Damaged Ladder | Repair handrails and restore coating loss. Dimension: 40m length of Handrails requires coating. Replace Fenders with composite Fenders Recertify and recalibrate Davit 55m length of Toe Plate requires coating Replace Access Ladder; 2.5m | H | SPDC-2021-03-00000086
101 | BELEMA WELLHEAD PLATFORM 1T (No access due to siltation: Lower deck and structural suppor | 2021-03-23 | Severe corrosion and damage to structural members | Coating renovation. Dimensions: 6Nos 0.9m Channel: 80 x 40mm Total length = 5.4m 12Nos. 0.6m UA 80 x 40mm Total Length = 7.2m 10Nos. 2m 80mm dia. CHS. Total length = 20m | H | SPDC-2021-03-00000086
102 | Handrails | 2021-03-23 | Severe damage and mechanical impact | Repair and repaint Handrail. Total length = 40m | H | SPDC-2021-03-00000086
103 | Access Channel to Wellhead | 2021-03-23 | Severely silted. No marine access to well | Dredge well access after Geomatics survey | H | SPDC-2021-03-00000086
104 | BELEMA WELLHEAD PLATFORM 5L/S: Conductor Casings and Diagonal Bracing | 2021-03-24 | Severe corrosion with metal loss on Casing and Structural Supports | Cut and replace diagonal bracings Dimension: IPE 220 x120 x 8mm Total length = 4.8m | H | SPDC-2021-03-00000086
105 | Handrails Gratings/Fenders /Davit. Toe Plates and Access Ladder | 2021-03-24 | Damage and moderate coating failures 3 missing Fenders and 1 broken Fender Mild coating failures Damaged Ladder | Repair Handrail and restore coating loss. Dimension: 40m length of Handrails requires coating. Replace Fenders with composite Fenders Recertify and recalibrate davit 55m length of Toe Plate requires coating Replace Access Ladder. 2.5m | H | SPDC-2021-03-00000086
106 | BELEMA WELLHEAD PLATFORM 7L/S: Handrails Gratings/Fenders /Davit. Toe Plates Access Ladde | 2021-03-24 | Severe corrosion at splash zone on Handrails Fenders & Gratings in good condition Mild coating failure Damaged Ladder | Repair Handrails and restore coating loss. Dimension: 40m length of Handrails requires coating. Recertify and recalibrate davit 55m length of Toe Plate requires coating Replace Access Ladder. 2.5m | H | SPDC-2021-03-00000086
107 | BELEMA WELLHEAD PLATFORM 2T Lower Platform Structural Support | 2021-03-24 | Severe corrosion and metal loss on structural supports | Replace lower deck structural supports Dimensions: 6Nos. 0.9m Channel: 80 x 40mm Total length = 5.4m 12Nos. 0.6 transverse UA: 80 x 40mm Total Length = 7.2m 10Nos. 2m 80mm dia. CHS. Total length = 20m | H | SPDC-2021-03-00000086
108 | Conductor Casings and Diagonal Bracings Lower Structural CHS Members, Conductor Anchor and Fender Supports | 2021-03-24 | Severe corrosion and marine growth on conductor casing and structural supports Moderate coating failure with marine growth | Coating renovation: Dimension: IPE 220 x120 x 8mm Total length: 4.8m Coating replacement on lower structural CHS members, Conductor Anchors and Fender Supports Coat 6Nos. 1.6m long CHS (120 dia.). Total length = 9.6m Coat 2Nos. 5m long (CHS 120 dia.) Total length = 10m | H | SPDC-2021-03-00000086
109 | Handrails Gratings/Fenders /Davit Toe Plates Access Ladder | 2021-03-25 | Severe corrosion at splash zone on Handrails Fenders & Gratings in good condition Mild coating failure Damaged Ladder | Repair Handrails and restore coating loss. Dimension: 40m length of Handrails requires coating. Recertify and recalibrate Davit 55m length of Toes Plate requires coating Replace Access Ladder. 2.5m | H | SPDC-2021-03-00000086
110 | BELEMA WELLHEAD PLATFORM 9T:Lower Platform Structural Supports | 2021-03-25 | Severe corrosion and metal loss on structural supports | Replace Lower Deck structural supports Dimensions: 6Nos. 0.9m Channel: 80 x 40mm Total length = 5.4m 12Nos. 0.6 transverse UA: 80 x 40mm Total Length = 7.2m 10Nos. 2m 80mm dia. CHS. Total length = 20m | H | SPDC-2021-03-00000086
111 | Conductor Casings and Diagonal Bracings Lower Structural CHS Members, | 2021-03-25 | Severe corrosion and marine growth on Conductor Casing and Structural Supports | Coating renovation: Dimension: IPE 220 x120 x 8mm Total length: 4.8m | H | SPDC-2021-03-00000086
112 | Handrails Gratings/Fenders /Davit. Toe Plates Access ladder | 2021-03-25 | Severe corrosion at splash zone on Handrails Fenders supports deformed and corroded Mild coating failure Damaged Ladder | Repair Handrails and restore coating loss. Dimension: 40m length of Handrails requires coating. Recertify and recalibrate davit. Replace Fender supports 55m length of Toe Plate requires coating Replace access ladder. 2.5m | H | SPDC-2021-03-00000086
113 | BELEMA WELLHEAD PLATFORM 11T: Conductor Casings and Diagonal Bracings Lower Structural CHS Members, Conductor Anchors and Fender Supports | 2021-03-25 | Severe corrosion and marine growth on Conductor Casing and Structural Supports Moderate coating failure with marine growth | Coating renovation: Dimension: IPE 220 x120 x 8mm Total length: 4.8m Coating replacement on lower structural CHS members, Conductor Anchor and Fender Supports Coat 6Nos. 1.6m length CHS (120 dia.). Total length = 9.6m Coat 2Nos. 5m length (CHS 120 dia.) Total length = 10m | H | SPDC-2021-03-00000086
114 | Handrails Gratings/Fenders /Davit. Toe Plates Access ladder | 2021-03-25 | Severe corrosion at splash zone on Handrails. Fenders supports severely corroded. Mild coating failure Damaged Ladder | Repair Handrails and restore coating loss. Dimension: 40m length of Handrails requires coating. Recertify and recalibrate Davit. Restore Fender Supports. 55m length of Toe Plate requires coating Replace Access Ladder. 2.5m | H | SPDC-2021-03-00000086
115 | BELEMA WELLHEAD PLATFORM 4T:Handrails Gratings/Fenders /Davit. Toe Plates Access Ladder | 2021-03-25 | Severe corrosion at splash zone on Handrails Fenders & Gratings in good condition Mild coating failure | Repair Handrails and restore coating loss. Dimension: 40m length of Handrails requires coating. Recertify and recalibrate davit 55m length of Toe Plate requires coating | H | SPDC-2021-03-00000086
OLOMA FS ACTIVITIES
| PERSONAL ACCESS PLATFORM | 2022-05-04 | Severely corroded handrails | Replace severely corroded sections of hand rails and make good 35mm dia. CHS; 12m | H | SPDC-2022-06-00000004
| JETTY RAMP | 2022-05-05 | Spalled, delaminated and exposed rebars on jetty approach | Recast concrete sections with reinforced concrete of grade 30 and make good | H | SPDC-2022-06-00000004
| OLOMA JETTY TOPSIDE Handrails | 2021-09-18 | Severely corroded section of Handrails on Concrete Staircase | Severely corroded section of Handrails on Concrete Staircase | H | SPDC-2021-12-00000036
|  |  |  | Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials to the prepared surface 45mm dia. CHS, 2.7m long | H
| OLOMA (BONNY) FLOWSTATION MAIN ENTRANCE | 2021-09-18 | Failed section of drain and road opposite Station Office | Remove and cart away failed section. Provide, mix and place grade C30 concrete to re-construct damaged section Drain wall: 2m x 0.1m x 0.4m Road: 1.5m x 1m x 0.3m | H | SPDC-2021-12-00000036
| DIESEL STORAGE TANK | 2021-09-18 | Severe cracks on Concrete Bundwalls | Provide, mix and treat cracks with cement grout, or inject Epoxy Resin 25m x 0.25m x 5mm | H | SPDC-2021-12-00000036
| BONNY NORTH WELL 2 PLATFORM Handrails and Fixed Vertical Access Ladder | 2021-09-18 | Severely corroded and warped Ladder Rungs and Stiles | Replace ladder with new one 18m Length. | H | SPDC-2021-12-00000036
| WELL 10 PLATFORM Gratings, Chequered Plates and Toe Plates | 2021-09-18 | ower Deck – Gratings: Missing Gratings | Provide and install new Gratings to replace the missing ones 3.2m x 1.2m x 2Nos. 1m x 0.3m x 2Nos. | H | SPDC-2021-12-00000036
| WELL 10 PLATFORM Fixed Vertical Access Ladder | 2021-09-18 | Vertical Access Ladder: Moderate to severe corrosion of Ladder Rungs around the splash zone | Provide, cut to size and weld Ladder Rungs to replace severely corroded ones. Remove corrosion with Hand tools. Prepare surface and apply self-priming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials to the prepared surface Ladder Rungs for replacement: 20mm dia., 0.45m x 5Nos. Stiles & Rungs for Recoating: 50mm wide flat bar, 12mm thick, 18m long 20mm dia., 0.45m x 12Nos. placed 250mm c/ | H | SPDC-2021-12-00000036
| WELL 15 PLATFORM Handrails and Fixed Vertical Access Ladder | 2021-09-18 | Handrails: Missing sections and coating failure on Handrails | Replace missing sections of Handrails. Prepare surface and apply self-priming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials to the prepared surface Missing Sections: 35mm dia. CHS, 10m long Sections for recoating: 35mm dia. CHS, 30m long | H | SPDC-2021-12-00000036
| WELL 15 PLATFORM Boat Landing | 2021-09-18 | Bolts and Nuts – Severely corroded | Replace severely corroded Bolts and Nuts 24Nos. |  | SPDC-2021-12-00000036
| WELL 18 PLATFORM Handrails and Fixed Vertical Access Ladde | 2021-09-18 | Vertical Access Ladder: Severely corroded Ladder Rungs | Provide, cut to size and weld Ladder Rungs to replace severely corroded ones. Remove corrosion with Hand tools. Prepare surface and apply self-priming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials to the prepared surface Ladder Rungs for Replacement: 20mm dia., 0.45m x 2Nos. Stiles & Rungs for Recoating: 50mm wide flat bar, 12mm thick, 18m long 20mm dia.,0.45m x 12Nos. placed 250mm c/ | H | SPDC-2021-12-00000036
| WELL 30 PLATFORM Handrails and Fixed Vertical Access Ladder | 2021-09-18 | Handrails: Missing Handrails at the Lower Deck | Provide, cut to size, weld and install new Handrails. Prepare surface and apply self-priming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials to the prepared surface 45mm dia. CHS, 12m long | H | SPDC-2021-12-00000036
| BONNY FS ACTIVITIES |  |  |  |  | SPDC-2022-04-00000172
| Primary support members - Steel columns.200mm E.A sections-16mm | 2022-04-21 | Moderate dirt contamination with minor flaking of protective painting. | Carry out surface preparation to make structural members ready to receive new coat. Apply Self-priming epoxy, epoxy mid-coat, polyurethane topcoat. (2647m2 ) | H | SPDC-2022-04-00000172
| Secondary Support members: Moderate dirt contamination with minor flaking of protective | 2022-04-21 | Last painted date July 2018 Due date:June 2021 |  | H | SPDC-2022-04-00000172
128 | UNIT 13 (GAS HANDLING UNIT) Train D Vessel (P-1402 D | 2021-03-01 | Severe cracks/spalling on Concrete foundation | Provide, mix and treat cracks with cement grout 0.45m x 0.25m x 25mm 0.6m x 0.25m x 0.1m | H | SPDC-2020-03-00000085
129 | BOGT PROCESS AREA(UNIT32) PUMP 3361 | 2021-03-01 | Severe corrosion with metal loss on Skid | Remove corrosion by grit blasting. Prepare surface and apply self priming Epoxy primer, Epoxy mid coat, and Polyurethane top coat, or other approved coating materials to the prepared surface 80 x 40mm PFC, 8.4m long | H | SPDC-2020-03-00000085
130 | PSS 1 BUILDINGS IN PROCESS AREA Main Building Blast-Proof Door | 2021-03-01 | Severely degraded BlastProof Door at entranc | Remove and cart away degraded Door. Provide and install new BlastProof Door 2.3m x 2.1m (Double Leaf) | H | SPDC-2020-03-00000085
131 | PSS 1 Low Voltage Switch Room | 2021-03-01 | Severe cracks on interior Walls | Provide, mix and treat cracks with cement grout, or inject Epoxy Resin 30m x 0.3m x 3mm | H | SPDC-2020-03-00000085
132 | PSS 1 Other sections | 2021-03-01 | Severe cracks on interior Walls | Provide, mix and treat cracks with cement grout, or inject Epoxy Resin 40m x 0.3m x 2mm | H | SPDC-2020-03-00000085
133 | PSS 2 BUILDING Interior Walls | 2021-03-01 | Severe cracks on interior Walls of Low Voltage Switch Room, Battery Room and Generator Control Room | Provide, mix and treat cracks with cement grout, or inject Epoxy Resin 260m x 0.3m x 2mm | H | SPDC-2020-03-00000085
134 | SS 100 BUILDING Exterior Walls | 2021-03-01 | Paint failures on exterior Walls | Prepare surface and apply two coats of approved paint on exterior Walls; L = 30m, W =15m, H = 4m | H | SPDC-2020-03-00000085
| CAPPING BEAM EDGE PROTECTOR STEEL BARS | 2021-04-02 | Missing and Misaligned Capping Beam Edge Protector |  | H | SPDC-2022-04-00000163
| SHEET PILES | 2021-04-02 | Moderate Corrosion on Sheet Piles |  | H | SPDC-2022-04-00000163
| SCOURED AREA UNDERNEATH JETTY TOP SLAB | 2021-04-02 | Progressive Scouring of Backfill Materials and Degraded Concrete Sections at Failed Jetty Section |  | H | SPDC-2022-04-00000163
| SEA WATER PUMP HOUSE | 2021-04-03 | Loosed Roofing Members at the Sea Water Pump House |  | H | SPDC-2022-04-00000163
135 | BOGT JETTY (BERTH 3) BOLLARD 5 - 6 | 2019-05-29 | 5.7m from Bollard 5 and 2m from top of concrete capping Beam. Torn Sheet Piles walls Circa. (1.2m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
136 | BOGT JETTY (BERTH 3) BOLLARD 6 - 7 | 2019-05-29 | 9.3m from Bollard 6 and 2.75m from top of Concrete Capping Beam. Torn Sheet Piles walls Circa. (1.5m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
137 | BOGT JETTY (BERTH 3) BOLLARD 7 - 8 | 2019-05-29 | 6.8m & 7m from Bollard 7. 2.8m from top of top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.1m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
138 | BOGT JETTY (BERTH 3) BOLLARD 8 - 9 | 2019-05-29 | 4.5 & 5.1m from Bollard 8. 2.8m from top of Concrete Capping Beam. Torn Sheet Piles walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
139 |  | 2019-05-29 | 6m & 6.1m from Bollard 8. 2.68m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.1m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
140 |  | 2019-05-29 | 7.2m from Bollard 8; 3.2m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.25m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
141 | BOGT JETTY (BERTH 3) BOLLARD 9 - 10 | 2019-05-29 | 0.5m from Bollard 9; 2.7m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
142 |  | 2019-05-29 | 2m from Bollard 9; 2.6m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
143 |  | 2019-05-29 | 2.7m from Bollard 9; 2.6m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
144 |  | 2019-05-29 | 5m from Bollard 9; 2.6m from top of concrete capping Beam. Torn Sheet Pile walls Circa. (1.0m x 0.67m) | Prepare surface & weld additional plates to cover and close the torn sections. | H | SPDC-2019-06-00000110 |  | 11728570 | 2019-09-09
145 | EQUIPMENT AND PIPING COMPARTMENT SEA WATER PUMP HOUSE AT BONNY JETTY | 2019-07-03 | REAR WALL FACING THE SHORELINE Collapsed section of the infill blockwall, broken corroded steel Beam supporting the blockwall. Severe corrosion with significant metal loss on the exposed sections of the web, flange and base sections of the Structural frame Stanchions initially covered by the infill block wall before the collapse. | Collapsed Section: Carefully demolish the remaining suspended rear infill blockwall and cart away the debris. Dismantle the severely degraded steel sections (Stanchions and Beams) and replacement with new members. Supply and install HE Columns and IPE Beams to replace the degraded sections. Reconstruct the blockwall with 225mm hollow blocks on a stretcher bond of sand-cement mortar. The new support columns should be well encased in concrete for protection against corrosion. - Stanchions - 360 x 300 x 22mm, 6m long - 2 Nos. - Steel Beams - IPE 170 x 90mm x 10mm, 4.8m long -5 Nos Concrete Hollow Blockwall - 4.8m long, 6m high Cathodic protection is advised to further protect the steel members from further deterioration due to corrosion. | H | SPDC-2019-07-00000234 | SAP
146 |  | 2019-07-03 | OTHER WALLS (EXTERNAL & PARTITION) Main Steel Beam Severe corrosion with metal loss on the main Beams of the Structural frame. | Remove corrosion on the Beams with hand tools. Prepare surface and apply self-priming Epoxy primer, Epoxy mid-coat and Polyurethane topcoat, or other approved coating materials to the prepared surface. | H | SPDC-2019-07-00000234 | SAP
147 |  | 2019-07-03 | Blockwall Support Beams Moderate to severe corrosion on the steel | Remove corrosion on the flange surfaces of the steel Beams bearing the sandcrete walls and apply selfpriming Epoxy primer, Epoxy mid-coat and Polyurethane topcoat, or other approved coating materials to the prepared surface. - IPE 170 x 90 x 10mm 4.8m long (4 Nos.) 14.7m length (4 Nos) | H | SPDC-2019-07-00000234
148 |  | 2019-07-03 | Diagonal Bracings Diminished section of diagonal bracing near the connection at base of the Stanchion. | Provide, cut to size and weld 8mm thick plates to the bracings to make up for the diminished sections. Prepare surface and apply selfpriming Epoxy primer, Epoxy midcoat and Polyurethane topcoat, or other approved coating materials to the prepared surface. - 8mm thick Plate; 0.12m wide, 0.3m long | H | SPDC-2019-07-00000234
149 |  | 2019-07-03 | FLOOR Grating Support Beams Severely corroded primary and secondary Beams supporting the floor Gratings. | Remove corrosion on the Beams with hand tools. Prepare surface and apply self-priming Epoxy primer, Epoxy mid-coat and Polyurethane topcoat, or other approved coating materials to the prepared surface. - HE 205 x 205 x 22mm - 1m long, (6 Nos) - U-Channel 100mm x 205mm - 1m length (8 nos). | H | SPDC-2019-07-00000234
150 |  | 2019-07-03 | ROOF Holes observed on the Roofing Sheets. | Carry out spot repairs. 14.7 x 6m | H | SPDC-2019-07-00000234
151 | PUMP COMPARTMENT | 2019-07-03 | Blockwall Support Beams Moderate to severe corrosion on the steel Beams bearing the sandcrete blockwall. | Remove corrosion on the flange surfaces of the steel Beams bearing the sandcrete walls and apply selfpriming Epoxy primer, Epoxy midcoat and Polyurethane topcoat, or other approved coating materials to the prepared surface. - IPE 170 x 90 x 10mm, 4.8m long (4 Nos.) 14.7m long (8 Nos) | H | SPDC-2019-07-00000234
152 | TANK 7 BUNDWALL | 2020-03-03 | Failed asphaltic layer of the entire bund wall perimeter of Tank 7 Area of Bundwalls overlaid with concrete = 12.5% Degraded area to be overlaid = 87.5% | Bundwalls already programmed for concrete surface finish in 2020 | H | SPDC-2020-04-00000077 | SAP
153 | TANK PADS | 2020-03-03 | Fatigue cracks on surface of the asphaltic overlay of the Tank pads (60m radius) Tank under repairs/ renovation | Scarify existing bituminous/ asphaltic surfacing, pulverize, level and compact properly around the Tank Pad Provide & lay the woven polyethylene fabric over the compacted earth Provide, lay & compact grade C25 concrete 100mm thick over the woven fabric | H | SPDC-2020-04-00000077
154 | TANK 10 BUNDWALL | 2020-03-03 | Cavities/large openings on surface of the asphaltic surfaces | Bundwalls already programmed for reconstruction in 2020 with concrete surface finish | H | SPDC-2020-04-00000077
155 | TANKS T-3407 A & B BUNDWALL | 2020-03-03 | Bundwalls extremely degraded | Carry out earth work to excavate the mapped out perimeter & prepare to receive sharp sand Provide, re-fill & compact the loose earth & trim to required profile Set up wooden shuttering at 5m intervals to allow for expansion gaps Install a layer of 6mm thick BRC mesh over the compacted earth ready to receive concrete Provide ,lay & compact grade C-25 concrete 75mm thick over the BRC mesh | H | SPDC-2020-04-00000077
156 | TANK 11 BUNDWALL | 2020-03-03 | Fatigue cracks & cavities on surface of the asphaltic overlay and grassy popouts. | Scarify existing bituminous/ asphaltic surfacing, pulverize, level and compact properly over the entire bunded area Set up wooden shuttering at 5m intervals to allow for expansion gaps Install a layer of 6mm thick BRC mesh over the compacted earth ready to receive concrete Provide, lay & compact grade C25 concrete 75mm thick over the BRC mesh | H | SPDC-2020-04-00000077
157 | WALKWAY & DRAINAGE | 2020-03-03 | Severely degraded section of walkway from the Tank pad (8x1.1x0.3m) Degraded section of drainage (7x0.2x0.4m) | Break up the degraded section & carte away. Reconstruct with grade C-25 concrete & make good | H | SPDC-2020-04-00000077
158 | TANK 12 BUNDWALL: | 2020-03-03 | Severely degraded asphaltic overlay with cavities on surface of the Bundwalls Area of Bundwalls overlaid with concrete = 12.5% Degraded area to be overlaid = 87.5% | Scarify existing bituminous/ asphaltic surfacing, pulverize, level and compact properly over the entire bunded area. Set up wooden shuttering at 5m intervals to allow for expansion gaps Install a layer of 6mm thick BRC mesh over compacted surface and make ready to receive concrete Provide ,lay & compact grade C25 concrete 75mm thick over the BRC mesh | H | SPDC-2020-04-00000077
159 | TANK PADS | 2020-03-03 | Cavities on surface of the asphaltic overlay of the Tank pads (75m radius) | Scarify existing bituminous/ asphaltic surfacing, pulverize, level and compact properly around the Tank Pad Provide & lay the woven polyethylene fabric over the compacted earth Provide ,lay & compact grade C25 concrete 100mm thick over the woven fabric | H | SPDC-2020-04-00000077
160 | TANK 13 BUNDWALL: | 2020-03-03 | Degraded asphaltic overlay with cavities on surface of the Bundwalls Area of Bundwalls overlaid with concrete = 25% Degraded area to be overlaid = 75% | Scarify existing bituminous/ asphaltic surfacing, pulverize, level and compact properly over the entire bunded area Set up wooden shuttering at 5m intervals to allow for expansion gaps Install a layer of 6mm thick BRC mesh over the compacted earth ready to receive concrete Provide ,lay & compact grade C25 concrete 75mm thick over the BRC mesh | H | SPDC-2020-04-00000077
161 | TANK PADS | 2020-03-03 | Severely degraded Tank pad (75m radius) | Scarify existing bituminous/ asphaltic surfacing, pulverize, level and compact properly around the Tank Pad. Provide & lay the woven polyethylene fabric over the compacted eart Provide ,lay & compact grade C25 concrete 100mm thick over the woven fabric | H | SPDC-2020-04-00000077
162 | TANK 16 BUNDWALL DRAINAGE | 2020-03-03 | Severely degraded drain/retaining wall between Tanks 14 7 16 (22X1.4X0.1m) | Provide & re-construct degraded area with grade C-30 concrete | H | SPDC-2020-04-00000077
163 | TANK 20 BUNDWALL | 2020-03-03 | Severely degraded asphaltic overlay with cavities on surface of the Bundwalls | Bundwalls already programmed for reconstruction in 2020 with concrete surface finish | H | SPDC-2020-04-00000077
NUN RIVER FLB ACTIVITY
164 | ACCOMMODATION BUILDINGS IN NUN RIVER FIELD LOGISTICS BASE BLOCK H | 2019-08-20 | ROOM H3: Severely Stained Ceiling Boards | Uninstall stained ceiling boards, wash with detergents and reinstall. 2.4m x 2m | H | SPDC-2019-09-00000063
165 |  | 2019-08-21 | ROOM H4: Severely Stained Ceiling Boards | Uninstall stained ceiling boards, wash with detergents and reinstall. 2.4m x 2 | H | SPDC-2019-09-00000063
166 | TELECOMMUNICATIONS BUILDING EXTERIOR PART OF BUILDING | 2019-08-22 | Severe horizontal cracks alongside of concrete verandah | Provide, mix and treat cracks with cement grout, or inject Epoxy Resin 60 x 0.15m x 3mm | H | SPDC-2019-09-00000063
167 | INCINERATOR SHED | 2019-08-23 | Severe corrosion/metal loss and coating failure on Tank and Steel Supports | No longer in use - No action is required | H | SPDC-2019-09-00000063
NUN RIVER FLOWSTATION ACTIVITY
168 | NUN RIVER WELLHEAD 12 WELLHEAD STEEL GRATING COVER ON CELLAR PIT | 2021-04-23 | Warped steel Grating supports due to improperly laid Grating | Replace all defective Grating and Grating supports as follows: Provide equal angle iron of specified dimensions, cut to size and fix 45 x 45mm x 6mm thickness EA: 30m long. Provide, cut to size and install galvanized steel Grating 2.5m x 2.1m x 2Nos. N/B: Grating Supports, and Gratings should be arranged to safely support personnel weight. | H | SPDC-2021-05-00000097
169 | NUN RIVER WELL 7 WELLHEAD PLATFORM STEEL GRATINGS ON WELLHEAD CELLAR PIT | 2021-04-23 | Missing steel Grating on Cellar pit | Provide galvanized steel Grating, cut to size and install complete with Grating clips 1.2m x 1m x 2Nos. | H | SPDC-2021-05-00000097
170 | NUN RIVER 11 WELLHEAD PLATFORM STEEL GRATINGS ON WELLHEAD CELLAR PIT | 2021-04-23 | nadequate length of Grating load bearing bar resting on Grating support | Provide galvanized steel Grating, cut to size and install complete with Grating clips Area = 1.4m x 1m | H | SPDC-2021-05-00000097
171 | STEEL JETTY LEADING TO WELLHEAD 4 AND 6 STEEL STAIRCASE | 2021-04-23 | Moderately corroded staircase beams | Prepare surface and apply selfpriming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces 250 x 100mm Channel, 16m long | H | SPDC-2021-05-00000097
172 |  | 2021-04-23 | Severely corroded, broken and warped Grating tread/steps | Remove and cart away all staircase Gratings. Provide galvanized steel Grating, cut to size and install/weld to steel thread supports on staircase steel beam 0.8m x 0.4m x 12Nos. | H | SPDC-2021-05-00000097
173 |  | 2021-04-23 | Extremely corroded Grating landing and steel Plate | Remove and cart away Gratings landing and steel Plate. Provide galvanized steel Grating and perforated steel Plate, cut to size and install/weld 1m x 1m each | H | SPDC-2021-05-00000097
174 | STEEL WALKWAY | 2021-04-23 | Missing Bollards | Provide and install/weld Bollards to walkway platform. Prepare surface and apply selfpriming Epoxy primer, Polyurethane topcoat or other approved coating materials on the prepared surfaces 300mm dia. CHS, 0.3m x 2Nos. Tonnage signs - to be inscribed on Bollards | H | SPDC-2021-05-00000097
175 | INLET MANIFOLD | 2019-08-23 | Handrails: Missing Handrails for staircase | Provide missing Handrails. Prepare surface and apply self-priming Epoxy primer, Epoxy mid-coat and Polyurethane topcoat, or other approved coating materials to the prepared surface. 45mm dia. CHS, 4m long | H | SPDC-2019-09-00000060
176 | LP, HP & TEST SEPARATORS | 2019-08-24 | Missing Handrails for staircase | Provide missing Handrails. Prepare surface and apply self-priming Epoxy primer, Epoxy mid-coat and Polyurethane topcoat, or other approved coating materials to the prepared surface. 45mm dia. CHS, 8m long | H | SPDC-2019-09-00000060
177 | SURGE VESSEL | 2019-08-25 | Missing bolts for Grating steel support | Provide and install missing bolts. 16mm dia., 2Nos | H | SPDC-2019-09-00000060
178 | INLET MANIFOLD | 2020-07-01 | Handrails: Missing Handrails for staircase | Provide missing Handrails. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials to the prepared surface 45mm dia. CHS, 4m long | H | SPDC-2020-08-00000030
179 | LP, HP & TEST SEPARATORS | 2020-07-01 | Missing Handrails for staircase | Provide missing handrails. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials to the prepared surface 45mm dia. CHS, 8m long | H | SPDC-2020-08-00000030
NUN RIVER BRIDGE
180 | ONYOMA MAIN ACCESS BRIDGE 1 GUARDRAILS | 2020-07-01 | Severe corrosion, perforations, metal loss and coating failure on sections of railings | Remove degraded Handrails and cart away. Provide, cut to size, install and weld in place new Guardrails. Prepare surface and apply self-priming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials on the prepared surface 65mm dia. CHS, 12.2m x 6Nos. 75 x 75mm EAS, 1.45m x 24Nos. | H | SPDC-2020-08-00000030
DIEBU CREEK ACTIVITY
181 | DIEBU CREEK WELL 10 PLATFORM BOAT LANDING FENDER | 2021-04-22 | Severely degraded wooden Fenders | Provide and install Rubberized Wharf Fenders, made up of Polythene materials with fiber glass reinforcement bars. 0.2 x 0.2 x 3m x 4Nos | H | SPDC-2021-05-00000067
182 | DIEBU CREEK WELL 10 PLATFORM LOWER DECK PLATFORM | 2021-04-22 | Missing Gratings on deck Platform | Provide galvanized steel Grating, cut to size and install. 3.3 x 1m x 2Nos. | H | SPDC-2021-05-00000067
183 | DIEBU CREEK WELL 8 PLATFORM BOAT LANDING | 2021-04-22 | Missing Fenders | Provide and install Rubberized Wharf Fenders, made up of Polythene materials with fiber glass reinforcement bars. 0.2 x 0.2 x 3m x 4Nos. | H | SPDC-2021-05-00000067
184 |  | 2021-04-22 | Tilted Fender steel supports | Straighten Fender steel support by using approved welding technique or using screwing both end of steel supports plates to each other | H | SPDC-2021-05-00000067
194 | METERING SKID | 2020-07-08 | Severe corrosion with metal loss and coating failure on Grating support directly beneath the Handrails | Provide and weld additional steel to reinforce section with metal loss. Remove corrosion with hand tools. Prepare surface and apply selfpriming Epoxy primer, Epoxy mid coat and Polyurethane top coat, or other approved coating materials to the prepared surface 100 x 100mm EAS, 6.1m long | H | SPDC-2020-08-00000039
195 | TELECOMS. TOWER | 2020-07-08 | BASE PLATES Missing hold down bolts | Provide and screw in place missing hold down bolts 16mm dia., 6Nos. | H | SPDC-2020-08-00000039
196 | MASTER SHUT DOWN VALVE | 2020-07-08 | Severe water ponding on Drain Pan | Desilt Drain Pan line to allow flow of fluid/liquid to saver pit 7.5m x 2.5m | H | SPDC-2020-08-00000039
OKOLOMA GAS PLANT ACTIVITIES
197 | CONCRETE POLES: Cracks & Exposed Rebar | 2020-09-18 | P10A – MILD SURFACE CRACK | Replace all defective Poles listed 14Nos. 12m length, 250mm diameter | H | SPDC-2020-09-00000033
198 |  |  | P18 – Moderate crack 3mm crack wide, 1.6m long, 50mm deep
199 |  |  | P18 – Moderate crack 3mm crack wide, 1.6m long, 50mm deep 1 P23 – Exposed Rebar. Continuous linear crack - 3m length, 0.6m wide, 50mm depth
200 |  |  | P24 – Severe crack, multiple crack length and spalled sections - 5m length, 20mm crack width -50mm depth
201 |  |  | Exposed Rebar 2m length, 20mm crack width, 50mm depth
202 |  |  | P28 – Continuous vertical crack 7m length, 20mm crack width, 50mm depth
203 |  |  | P30B – Mild crack at the Pole tip 1.5m crack length, 7mm crack width, 50mm depth
204 |  |  | P34 – Spalled concrete surface, vertical crack, exposed Rebar 3m length, 20mm crack width, 50mm depth
205 |  |  | P141 - Continuous mild crack 2m length, 7mm crack width, 50mm depth.
206 |  |  | Pole 166 – mild vertical crack at the Pole tip 0.8m length, 7mm crack width, 50mm depth
207 |  |  | Pole 167 - Multiple crack length, spalled sections and exposed rebar. -8m length, 10mm crack width, 50mm depth.
208 |  |  | P170A – linear crack at the Pole tip. 1.2m crack length, 7mm crack width, 50mm depth
209 |  |  | P182 - spalled sections and exposed rebar. 2m length, 10mm crack width, 50mm depth
210 |  |  | P183 - spalled sections and exposed rebar. 2.2m length, 10mm crack width, 50mm depth
211 |  |  | P184 - spalled sections and exposed rebar. 2.5m length, 10mm crack width, 50mm depth
| KIDNEY ISLAND ACTIVITIES | [5 empty] | SAP
212 | KIDNEY ISLAND – LIGHT MARINE VESSEL BERTH & THE HOVERCRAFT RAMP. Concrete Section (2.8m Depth - Mudline) | 2018-12-18 | Heavily silted Light Marine Vessel Berths (113.27 x 57.7m) | Dredging to a depth not exceeding 3m. | H | SPDC-2019-02-00000172 | SAP
213 | KIDNEY ISLAND – LIGHT MARINE VESSEL BERTH & THE HOVERCRAFT RAMP.BOLLARD 7-8 (FROM JETTY TRESTLE) | 2018-12-18 | 9.6m – 10m from Bollard 7 & 2.2m from top of Pavement Water ingress into pockets in the Diaphragm Walls during high tide. Accumulated water jets out from the pockets during low tide. (0.2m long, 20mm) | Prepare surface, Provide, mix and close up the openings with injection of Epoxy Resin & patch surface. (0.004m3) | H | SPDC-2019-02-00000172 | SAP
214 | BERTH 3 – BERTH 4 Bollard 1 – 2 (FROM MILITARY SHED BY THE HOVERCRAFT RAMP) | 2018-12-18 | 7m from Bollard 1 & 3m from top of Pavement. Crevice on Diaphragm Wall. Circa. 30mm wide, 0.7m Long | Prepare surface, provide, mix and treat crevice with injection of Epoxy Resin & patch surface. (0.021m3) | H | SPDC-2019-02-00000172 | SAP
215 | BERTH 3 – BERTH 4 Bollard 2 - 3 | 2018-12-21 | 2.5m from Bollard 2 & 2.4m from top of pavement.Exposed reinforcement on Diaphragm Wall. (1.2x1x0.3m) | Remove corrosion with hand tools from the exposed rebar. Carry out concrete patch repairs with grade C35 concrete (0.36m3) | H | SPDC-2019-02-00000172 | SAP
216 | BERTH 3 – BERTH 4 Bollard 3 - 4 | 2018-12-21 | 2.5m from Bollard 3 & 2.5m from top of Pavement. Exposed rebar | Remove corrosion with hand tools from the exposed rebar. Prepare and apply concrete patch repairs with grade C35 concrete (0.32m3) | H | SPDC-2019-02-00000172 | SAP
217 | BERTH 3 – BERTH 4 Bollard 5 - 6 | 2018-12-24 | 0.5m from Bollard 5 & 3.6m from top of pavement. Exposed reinforcement on Diaphragm Wall. Circa 1.2 x 0.9 x 0.3m 3.6m from Bollard 5 & 3.5m from top of pavement. Exposed reinforcement on Diaphragm Wall. 4m from Bollard 5 & 3.5m from top of Pavement. Exposed reinforcement on Diaphragm Wall. | Remove corrosion with hand tools from the exposed rebars. Carry out concrete patch repairs with grade C35 concrete and make good Area = 0.93m3 | H | SPDC-2019-02-00000172 | SAP
218 | KIDNEY ISLAND BERTH 14 (RAMP, BY THE ALMOND TREE)STEEL SHEET PILES | 2019-01-11 | 4.5m from Bollard 1 & 1.5m from the top of Capping Beam Warped/Torn Sheet Piles Circa. 1.0m x 0.9m | Prepare surface & weld additional plates to cover the perforations & make good. (0.9m2) | H | SPDC-2019-02-00000172 | SAP
219 | KIDNEY ISLAND BERTH 15 Bollard 1 – 2 (FROM WORKSHOP & WARE-HOUSE 2) | 2019-01-14 | 10m from Bollard 1& 0.5m from top of Beam. Torn sections of Sheet Pile Circa. 0.2m wide, 0.65m long | Prepare surface & weld additional plates to cover the perforations & make good. (0.13m2) | H | SPDC-2019-02-00000172 | SAP
220 | KIDNEY ISLAND BERTH 15 Bollard 2 – 3 | 2019-01-14 | 15m from Bollard 2 & 1m from top of Beam. Torn sections of Sheet Pile Circa. 0.3m wide, 0.4m long | Prepare surface & weld additional plates to cover the perforations & make good. (0.12m2) | H | SPDC-2019-02-00000172 | SAP
221 | KIDNEY ISLAND BERTH 15 Bollard 4 – 5 | 2019-01-14 | 8m from Bollard 4 & 3m from top of Beam. Delamination of Sheet Pile Circa. 0.55m wide, 1.2m long | Prepare surface & weld additional plates to cover the perforations & make good. (0.66m2) | H | SPDC-2019-02-00000172 | SAP
222 | KIDNEY ISLAND BERTH 15 Bollard 5 – 6 | 2019-01-15 | 0.5m from Bollard 5 & 0.2m from top of Beam. Perforation on Sheet Pile Walls. (0.1mm wide, 0.1m) | Prepare surface & weld additional plates to cover the perforations & make good. (0.01m2) | H | SPDC-2019-02-00000172 | SAP
223 | KIDNEY ISLAND BERTH 15 Bollard 6 – 7 | 2019-01-15 | 6.2m from Bollard 2 & 3.2m from top of beam. Torn sections of Sheet Pile Circa. 0.2m wide, 0.35m long | Prepare surface & weld additional plates to cover the perforations & make good. (0.07m2) | H | SPDC-2019-02-00000172 | SAP
224 | KIDNEY ISLAND BERTH 15B Bollard 1 – 2 | 2019-01-16 | 1 m from Bollard 1 & 3m from top of Beam. Torn sections of Sheet Pile Circa. 0.2m wide, 0.45m long | Prepare surface & weld additional plates to cover the perforations & make good. (0.09m2) | H | SPDC-2019-02-00000172 | SAP
225 | KIDNEY ISLAND BERTH 15B Bollard 2 – 3 | 2019-01-17 | 8.2m from Bollard 2 & 1m from top of Beam. Severe perforation on Sheet Pile allowing for penetration of water into the foundation at high tide. Circa. 0.2 x 0.25m | Prepare surface & weld additional plates to cover the perforations & make good. (0.05m2) | H | SPDC-2019-02-00000172 | SAP
226 | KIDNEY ISLAND BERTH 15B Bollard 3 – 4 | 2019-01-18 | 1.5m from Bollard 3 & 1m from top of Beam. Severe perforation on Sheet Pile Circa. 0.2 x 0.15m 14m from Bollard 3 & 2.5m from top of Beam. Severe perforation on Sheet Pile Circa. 0.2 x 0.25m | Prepare surface & weld additional plates to cover the perforations & make good. (0.03m2) Prepare surface & weld additional plates to cover the perforations & make good. (0.05m2) | H | SPDC-2019-02-00000172 | SAP
227 | KIDNEY ISLAND BERTH 15B Bollard 4 – 5 | 2019-01-19 | 3m from Bollard 4 & 2.8m from top of Beam. Delamination of Sheet Pile Circa. 0.6mm wide, 1.2m long 0.5m from Bollard 4 & 2m from top of Beam. Delamination of Sheet Pile Circa. 0.5m wide, 0.7m long Corrosion on Sheet Pile Circa. (75 x 2.5m) | Prepare surface & weld additional plates to cover the perforations & make good. (0.05m2) Prepare surface & weld additional plates to cover the perforations & make good. (0.35m2) Remove marine growth with hand tools, recoat entire surface & make good. (187.5m2 area) | H | SPDC-2019-02-00000172 | SAP
228 | PERIMETER FENCE | 2020-06-11 | Failed/collapsed section of the perimeter fence at the waterfront | Reconstruct the fence with 450 x 225 x 220mm hollow blocks Size = 64.8m long, 2.5m high |  | SPDC-2020-06-000000129 | SAP
229 | BOAT LANDINGS 1,2,3,4,5 & 6 | 2020-06-11 | Spalled concrete cover with exposed rebar between Apron pavement and Boat landing | Seal up the spalled section with grade C-30 concrete and make good Size = 12Nos. of 0.5 x 0.4m |  | SPDC-2020-06-000000129 | SAP
230 |  |  | Severe corrosion with metal loss on Handrails around splash zone 70mm dia. CHS 42.6m cumulative length | Cut off the severely degraded sections, provide and weld to existing ones and make good Prepare surface & recoat with self priming Epoxy primer, Epoxy mid coat and Polyurethane top coat or other approved coating materials on the prepared surface | H | SPDC-2020-06-000000129 | SAP
231 | GUARD RAILS | 2020-06-11 | Severely corroded Handrails & Toe board 70mm dia. CHS, 35m long 90 x 40mm RHS, 38.6m lon | Cut off the severely degraded sections, provide and weld to existing and recoat | H | SPDC-2020-06-000000129 | SAP
232 | MILITARY POST | 2020-06-11 | SANDBAG SHED: Severely degraded sand bags Area = 12m x 1.5m | Provide and replace degraded sandbags with steel drums 1000mm dia. CHS with sand infill - 13Nos. |  | SPDC-2020-06-000000129 | SAP
233 |  |  | Damaged/missing aluminium roofing sheets Area = 3.5m x 3.3m | Replace degraded aluminium roofing sheets and make good |  | SPDC-2020-06-000000129 | SAP
234 |  |  | REST SHED: Moderate pitting corrosion on steel members Roof: Area = 8.9m x 2m 60mm dia. CHS, 46.8m long | Prepare surface & recoat with self priming Epoxy primer, Epoxy mid coat and Polyurethane topcoat or other approved coating materials on prepared surface |  | SPDC-2020-06-000000129 | SAP
| ADIBAWA ACTIVITIES | [5 empty] | SAP
235 | JK 1 Bailey Bridge Bolted Connections/ Joints | 2019-07-29 | 5Nos. missing Chord Reinforcement Bolts/Nuts | Provide and replace 5Nos. missing Chord Reinforcement Bolts/Nuts | H | SPDC-2019-08-00000149 | SAP
236 | JK 1 Bailey Bridge Signages on Bridge Approaches | 2019-07-30 | No signage was seen on the Bridge Approaches | Provide & Install 2Nos approved reflective road signs in accordance with the Federal Highway Code on Bridge Approaches & Exits | H | SPDC-2019-08-00000149 | SAP
237 | Deck Plates Panels ADIB Well 19 Bridge Access | 2019-07-31 | Missing steel Deck Plates. Timber used as Deck Plates. Some Timber logs missing 13 x 5.4m | Replace entire Bridge section with steel Deck Plates complete with bolting accessories. 13 x 5.4m | H | SPDC-2019-08-00000149 | SAP
238 | ADIB Well 19 Bridge Access Signages on Bridge Approaches | 2019-08-01 | No signage on the Bridge Approaches | Provide & Install 2Nos. approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149 | SAP
239 | ADIB WELL 12 STEEL GIRDER BRIDGE Signages on Bridge Approaches | 2019-08-02 | No signages on the approach and exit of the Bridge | Provide & Install 2Nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149 | SAP
240 | STEEL GIRDER BRIDGE AFTER ADIB WELL 4 Signages on Bridge Approaches | 2019-08-03 | No signages on the approach and exit of the Bridge | Provide & Install 2Nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149 | SAP
241 | BISENI ACCESS BRIDGE AFTER WELL 10 ACCESS:Signages on Bridge Approaches | 2019-08-04 | No signages on the approach and exit of the Bridge | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149 | SAP
242 | STEEEL GIRDER BRIDGE after DXSF2, CLOSE TO DUSTBIN JUNCTION :Bridge approach Signage | 2019-08-04 | Not sighted on approach and exit sections | Provide & Install 2Nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approach & Exit | H | SPDC-2019-08-00000149 | SAP
| AHIA ACTIVITIES | [5 empty] | SAP
| AHIA FLOWSTATION TELECOMS TOWER | 2022-03-03 | Tower Painting Painted:08-02-2018 Due: 08-02–2021 Algae deposits and coating loss on Structural Steel Members | Remove degraded coating with hand tools. Prepare surface and apply self priming Epoxy primer, Epoxy mid coat, and Polyurethane top coat, or other approved coating materials on the prepared surface Height of tower – 120m. A = 2,250m2 | H | SPDC-2022-03-00000083
| IMO RIVER 1 AGG CONROL ROOM | [5 empty] | SAP
245 | IMO RIVER III FLOWSTATION SUCTION DRUM SHED | 2021-03-22 | Missing Grating on Personnel Access Platform | Provide and install galvanized Gratings 2.5m x 3m x 2Nos. | H | SPDC-2021-05-00000029
246 | IMO RIVER II FLOWSTATION FLARE WALKWAY | 2021-03-22 | Missing Grating panel on walkway | Provide and install galvanized Grating complete with accessories 1.8m x 0.9m | H | SPDC-2021-05-00000029
247 | IMO RIVER III FLOWSTATION CHEMICAL INJECTION SHED | 2021-03-22 | Missing Aluminum Roofing sheets | Provide and install Aluminum Roofing sheets Area = 7m x 0.9m | H | SPDC-2021-04-00000074
248 | ELEVATED TANK | 2021-03-22 | Severe metal loss on secondary beam supporting Tank | Prepare surface and apply selfpriming Epoxy primer, Epoxy midcoat and Polyurethane topcoat or other approved coating materials to the prepared surfaces 150mm x 80mm I-beam, 15m long | H | SPDC-2021-04-00000074
249 | WALKWAY TO FLARE | 2021-03-22 | Missing Guardrails | Provide circular hollow section steel of specified dimensions, cut to size, weld as required and fix/ install. 40mm dia. CHS, 32m long | H | SPDC-2021-04-00000074
250 | BACK PRESSURE | 2021-03-22 | Steel Grating support resting on flow pipe | Reposition Grating support to rest on concrete floor. | H
251 | SUCTION DRUM SHED | 2021-03-22 | Missing Roofing Sheets | Provide and install Aluminum Roofing Sheet on Shed Size = 4.5m x 7m | H
252 |  | 2021-03-22 | Broken E-14 earth cover slab near Suction Drum Shed | Provide and place grade 30 reinforced cover slab 0.6m x 0.6m x 0.15m
253 | STATION ATTENDANT HUT | 2021-03-22 | Severely degraded Ceiling boards | Provide and install new Ceiling boards to replace degraded ones 0.6m x 0.6m x 3Nos
254 | TELECOM. HOUSE | 2021-03-22 | Severely degraded fascia board | Remove degraded Fascia board & cart away. Provide and install new and treated Fascia board 7m x 0.3m
255 | IMO RIVER 1 FLOWSTATIONFLARE WALKWAY | 2021-03-22 | Missing Grating panel on walkway | Provide and install galvanized Grating complete with accessories Area = 1.8m x 0.9m
256 | EXTERNAL PART OF BUILDING | 2020-01-23 | Moderate cracks sighted on wallS 3mm crack width, 3m long (3 Nos.) | Open up the cracks to 50mm, Provide, mix and treat with Grade C30 concrete at the affected sections. Prepare the surface of the treated sections, & apply 2 coats of Emulsion paint or any SPDC approved paint & make good | H | SPDC-2020-01-00000090 | SAP
257 |  |  | CHAMBER PIT MANHOLE COVER PLATE: Degraded steel cover plate | Prepare, mix and provide concrete grade 30 to replace the degraded steel plated chamber cover. 1No. – 0.6 x 0.6m x 0.1m thick slab | H |  | SAP
258 |  |  | DOWNSPOUTS Downspouts provided, not extended to the perimeter drain. | Open up the concrete floor to accommodate the extra PVC length Extend all downspouts in the building to the perimeter drain & seal up the buried pipes. 10Nos. – 1.3m length, SHS -100 x 100mm, PVC. | H |  | SAP
259 | INSIDE THE BUILDING | 2020-01-23 | MAIN ENTRANCE BLAST DOOR: Hinges: 4Nos – OK. Door Panel – impacted sections significant Defective lever arm door opener No overhead door rail closer to keep the door self-shut at all times. | Remove blast door and install fit for purpose blast door complete with all accessories. 1No. – 2.45 x 0.9 | H | SPDC-2020-01-00000090 | SAP
260 | MECHANICAL OFFICE | 2020-01-23 | Defective door handle and mortise lock | Replace door handle. 1No | H |  | SAP
261 |  |  | Severe structural crack at the corner edge of the office, appeared at the tools room (same wall separating the offices) and cracks running from the window base level to the floor. 4.4m length structural crack, width - 2mm | Open up the cracks to 20mm & 150mm deep, Provide, mix and treat with Grade C30 concrete at the affected sections. | H | SPDC-2020-01-00000090 | SAP
262 |  |  | Broken/impacted tiles | Break the existing ceramic floor tiles & cart away. Provide & install laminated PVC floor tile (600 x 600mm) 4.2 x 3m | H |  | SAP
263 | PANTRY (KITCHEN) 3.9 x 2.8m | 2020-01-23 | Severe structural crack near the entrance door, 4.7m length, 4mm | Open up the cracks to 20mm & 150mm deep, Provide, mix and treat with Grade C30 concrete at the affected sections. | H | SPDC-2020-01-00000090 | SAP
264 |  |  | Impacted door panel sections and impacted frame. Defective door handle, missing overhead door rail closer, no mortise lock, by extension, no spring/dead bolt latch | Replace defective blast door and frame complete with all blast door accessories. 2.1m x 0.87m | H |  | SAP
265 | ELECTRICAL & INSTRUMNENT ROOM (E & I) |  | BLAST DOOR: Defective spring bolt, impacted sections on door panels, missing overhead door rail closer, | Replace defective blast door and frame complete with all blast door accessories. 2.1m by 0.87m | H | SPDC-2020-01-00000090 | SAP
266 | BATTERY ROOM | 2020-01-23 | TILES: Suspended floor tiles, poorly aligned panel tiles | Realigned the props suspending the floor tiles and make good, change all defective props. 20Nos.1 | H | SPDC-2020-01-00000090 | SAP
267 | MOTOR CONTROL CENTRE (MCC) | 2020-01-23 | Shaky wooden floor tile panels, not aligned, uneven at some areas. | Realigned the props suspending the floor tiles and make good, change all defective props. 20Nos | H | SPDC-2020-01-00000090 | SAP
268 |  |  | Severe structural vertical cracks | Open up the cracks to 20mm & 150mm deep, Provide, mix and treat with Grade C30 concrete at the affected sections. 15 x 0.15m x 20mm | H |  | SAP
269 |  |  | Degraded insulated floor skirting at the entire room perimeter. | Provide insulated floor skirting at the room perimeter base 33m length by 100mm | H |  | SAP
270 |  |  | Insulation Mat on Floor Inadequate for the Floor Area | Provide approved thick insulation mat 14m x 5.5m floor area. | H |  | SAP
271 |  |  | Degraded ceiling boards at the AC Vent points | Replace all the ceiling boards in the MCC room with white Aluminium ceiling panels, complete with accessories,Panels must have durable coating, waterproof and sound proof features. 14m length by 5.5m | H |  | SAP
| OBELE FLOWSTATION |  |  |  | H |  | SAP
| OBELE FLOWSTATION OIL SPIL RESPONSE MATERIA STORE /CHEMICAL SHED | 2022-03-02 | Blown off roof section | Replace blown out roof section 7m by 3m | H | SPDC-2022-03-00000083
|  | 2022-03-02 | Severely warped Grating and Grating support due to insufficient Grating supports for Chemical Drum Storage Platform. | Provide angle iron of specified dimensions, cut to size and fix including welding and bolting to provide additional support for the Grating platform. 60 x 60mm EAS, 0.9m x 17Nos. Provide galvanized steel Grating, cut to size and install on the Grating support.Grating platform: 2.4m x 0.9m x 2Nos | H | SPDC-2022-03-00000083
| GENERATOR HOUSE/DISEL STORAGE SHED | 2022-03-02 | Detached section of Aluminium cladding at rear side of Shed | Provide Aluminium screw nails and refix detached Aluminium cladding to cladding supports. 12mm dia. 6Nos. | H | SPDC-2022-03-00000083
| FLOOD LIGHT | 2022-03-02 | Tilted flood light pole. Ground heave | Realign flood light and make good. 2 Nos | H | SPDC-2022-03-00000083
| TELECOM MAST | 2022-03-02 | Slacked and moderately corroded Guy Wires/ Guy lines | Carry out three monthly condition monitoring of Telecom Mast Guy Wires for further slacking of Wires | H | SPDC-2022-03-00000083
| CATHODIC PROTECTION – PULSE GENERATION AND MONITORING BOX SHED | 2022-03-02 | Blown off Roof section | Replace blown off Roof Section and replace with new one. 3.5m by 1m. | H | SPDC-2022-03-00000083
| HORIZONTAL FLARE STRUCTURE | 2022-03-02 | Missing section of knee rail close to the flare tip | Replace missing section of rails. 35m length – 50mm dia, CHS | H | SPDC-2022-03-00000083
OGUTA FIELD
| OGUTA FLOWSTATION STATION OFFICE | 2022-02-27 | Broken drainage slab covers Slabs with exposed rebar | Provide, mix and cast drainage cover Slabs with grade C30 concrete to replace degraded ones Size = 0.8m x 0.35m x 0.15m x 10Nos. | H | SPDC-2022-03-00000083
278 | SAVER PIT | 2022-02-27 | Severe crack on concrete walkway close to Citadel Fence | Cut open section along crack, fill up with sharp sand, compact and recast with grade C30 concrete Size = 1.6m x 0.12m x 0.15m | H | SPDC-2022-03-00000083
| BACK PRESSURE MF/CITADEL FENCE AREA | 2022-02-27 | Subsidence/Loss of fill Material at the fence area | Fill the affected area with laterite sand, compact in layers of 150mm and make good. Total Height of fill – 500mm by 7m by 1m Provide, mix and lay concrete grade 25 as finished concrete surface and make good 7m by 1m by 0.15m | H | SPDC-2022-03-00000083
279 | FIRE HYDRANT | 2022-02-27 | Severe cracks on concrete slab. | Prepare surface and treat cracks with cement grout or inject Epoxy Resin. Size = 3.6 x 0.15m x 50mm | H | SPDC-2022-03-00000083
280 |  | 2022-02-27 | Severe scouring underneath concrete slab. | Prepare surface and treat scouring with cement mortar. 1.2 x 0.3 x 0.1m | H | SPDC-2022-03-00000083
| INLET MANIFOLD | 2022-02-27 | Personnel Access Staircase Warped tread on Access Staircase | Straighten out warped section of tread with hand tools 1No. | H | SPDC-2022-03-00000083
|  | 2022-02-27 | Shaky Handrails on Access staircase | Provide bracing for shaky Handrails 2Nos | H | SPDC-2022-03-00000083
|  | 2022-02-27 | Loose/Slack bolts and nuts on Access staircase | Tighten slack bolts 2Nos | H | SPDC-2022-03-00000083
|  | 2022-02-27 | Grating Platform Unstable Grating Platforms | Provide and install hold down clips for unstable Grating Platforms 10Nos | H | SPDC-2022-03-00000083
282 | TELECOM. MAST | 2022-02-27 | Slack Guy cables. | Tighten slack cables to make them taut. 6Nos. | H | SPDC-2022-03-00000083
| CHEMICAL SHED/OIL SPILL RESPONSE MATERIALS STORE | 2022-02-27 | Broken drainage slab cover slab opposite Chemical Shed | Provide, mix and cast drainage concrete cover slab with grade C30 concrete to replace degraded one Size = 0.6m x 0.3m x 0.2m | H | SPDC-2022-03-00000083
| FLARE STRUCTURES | 2022-02-27 | Broken section of handrail near flare tip | Replace broken section of handrail 20m length, 80mm dia | H | SPDC-2022-03-00000083
| BAILEY BRIDGE CONNECTING EPC AND OGUTA FLOWSTATION BRIDGE APPROACHES | 2022-02-28 | Signages & Reflectors No Bridge capacity and caution signs such as “slow down, bridge ahead”, etc, installed | Install approved reflective Bridge capacity and caution signages in accordance with Federal Highway Code on both sides of approaches – 2Nos | H | SPDC-2022-03-00000083
| BRIDGE HANDRAILS | 2022-02-28 | Missing sections of galvanized Hand and Knee railings on Pedestrian Walkway | Replace missing sections of galvanized Handrails 50mm dia. CHS, 50m long | H | SPDC-2022-03-00000083
| CONCRETE BRIDGE LOCATED CLOSE TO THE WATER TREATMENT PLANT BRIDGE APPROACHES | 2022-02-28 | Signages & Reflectors No Bridge capacity and caution signs such as “slow down, bridge ahead”, etc, installed | Install approved reflective Bridge capacity and caution signages in accordance with Federal Highway Code on both sides of approaches – 2Nos. | H | SPDC-2022-03-00000083
| ABUTMENTS/EMBA NKMENTS | 2022-02-28 | Erosion and loss of backfill materials | Carry out earthworks to back fill eroded soil materials with laterite, and compact in layers. Provide and place 50 - 100mm stone pitching set in 150mm thick Grade C20 concrete around the abutments and embankments 8m x 5m x 0.15m x 2Nos | H | SPDC-2022-03-00000083
| OGUTA WELL 4 ACCESS BAILEY BRIDGE LOCATED ~100M FROM OGUTA FLOWSTATION BRIDGE APPROACHES | 2022-02-28 | Signages & Reflectors No Bridge capacity and caution signs such as “slow down, bridge ahead”, etc, installed | Install approved reflective Bridge capacity and caution signages in accordance with Federal Highway Code on both sides of approaches – 2Nos. | H | SPDC-2022-03-00000083
| BOLTED CONNECTIONS/JOI NTS | 2022-02-28 | Missing Chord Reinforcement Pins/Bolts | Provide and install new Chord Reinforcement Pins to replace missing ones 30mm dia., 2Nos | H | SPDC-2022-03-00000083
| OGUTA WELLS 17, 20, 26 & 30 ACCESS BAILEY BRIDGE BRIDGE APPROACHES | 2022-02-28 | Signages & Reflectors Missing signage on one side of approach | Install approved reflective Bridge capacity and caution signage in accordance with Federal Highway Code on one side of approach – 1No. | H | SPDC-2022-03-00000083
|  | 2022-02-28 | Signage obscured by overgrown vegetation | Remove overgrown vegetation and cart away | H | SPDC-2022-03-00000083
| ABUTMENTS | 2022-02-28 | Exposed Rebar on Abutment Headwall on Bridge Approach | Provide, mix and recast concrete abutment headwall with grade C30 concrete 6. x 0.3m x 0.15m | H | SPDC-2022-03-00000083
| EZIORSU MAIN ACCESS BRIDGE BRIDGE APPROACHES | 2022-02-28 | Signages & Reflectors No Bridge capacity and caution signs such as “slow down, bridge ahead”, etc, installed | Install approved reflective Bridge capacity and caution signages in accordance with Federal Highway Code on both sides of approaches – 2Nos. | H | SPDC-2022-03-00000083
|  | 2022-02-28 | Roadway Failed and degraded sections of asphalt pavement, clustered and isolated potholes on both approaches | 1. Scarify and cart away all unsuitable materials 2. Provide, spread and compact sharp sand properly to fill degraded sections 3. Provide, spread and compact 0- 50mm mixed granite aggregates to 150mm thickness 4. Apply prime coat using MCI cut back bitumen @ 1.33itres/m2 , including blinding with sharp sand 5. Provide and lay asphaltic concrete wearing course to a compacted thickness of 50mm over new base Length = 120m, Width = 6m | H | SPDC-2022-03-00000083
| WALKWAY | 2022-02-28 | Damaged/degraded section of concrete Walkway with exposed rebar | Provide, mix and repair damaged/degraded section with grade C30 concrete 0.9m x 0.5m x 50-100mm | H | SPDC-2022-03-00000083
283 | OGUTA FLOWSTATION MAIN ACCESS BRIDGE 1 BRIDGE APPROACH SIGNAGES | 2022-02-28 | None sighted on approach and exit of the Bridge | Provide & Install 2 nos approved reflective road sign in accordance with the Federal Highway Code on Bridge Approaches | H | SPDC-2022-03-00000083
| BRIDGE APPROACHES (Approaches Wearing Course) | 2022-02-28 | Failed road shoulder on exit from Bridge. | Fill up the failed embankment with laterite, compact in layers of 150mm and make good. 5m by 2m by 0.85m Provide, mix and place grade C25/30 concrete to serve as finish Road shoulder Surface slab to the bridge. 5m by 2m by 0.25m thickness | H | SPDC-2022-03-00000083
| ABUTMENT EMBANKMENT | 2022-02-28 | Exit: Loss of backfill materials at the Abutment embankment | Clear Medium bush. The works shall include felling, cutting and stumping of all growths, shrubs and disposal of spoils. Provide and place 50 - 100mm stone pitching set in 150mm thick Grade 20 concrete around the abutments and embankments 17m long x 2.8m wide x 0.15m thick | H | SPDC-2022-03-00000083
| EGBEMA EPC - FLB PERIMETER CITADEL FENCE AND MAIN GATE CITADEL FENCE POST | 2022-03-01 | Warped and Bent Post. 6 Nos. | Replace bent post. 6 Nos. | H | SPDC-2022-03-00000083
| TOP RAILS | 2022-03-01 | Missing bolts & nuts for the connection of the top rails to the citadel fence/post. (10mm bolts) | Provide and install (10mm) bolts nuts & washers on top rails. (4000 Nos) -Entire Fence Perimeter | H | SPDC-2022-03-00000083
|  | 2022-03-01 | 8 Nos Bent top rail bar | Replace bent top rail with new ones. 8 nos - 50mm by 50mm EAS – 3m length | H | SPDC-2022-03-00000083
|  | 2022-03-01 | 6 nos missing top rail bar | Replace missing top rail with new ones. 6 Nos - 50mm by 50mm EAS – 3m length | H | SPDC-2022-03-00000083
| CITADEL WELDED MESH | 2022-03-01 | Torn sections of citadel Mesh dotted along the fence line from the Fire Station Building to the Helipad Reject area. | Fully replace sections with torn mesh. 3m by 3m – 20 Nos. | H | SPDC-2022-03-00000083
| RAZOR WIRE & COILS | 2022-03-01 | Loose sections of Razor wire & coils on top of the lintel bar rocker arms 6 Nos rockerarm bent.(13.75m) | Carefully re-arrange loose/collapse razor wire coils and rocker arm & hold in place with clips. | H | SPDC-2022-03-00000083
|  | 2022-03-01 | Citadel fence/razor wire covered by overhanging vegetation. | Carefully cut off overhanging vegetation on the citadel fence/razor wire. | H | SPDC-2022-03-00000083
| EGBEMA EPC - FLB OFFICE AREA TOWER members - Steel columns. 200mm E.A sections-16mm Secondary Support members: Moderate dirt contamination with minor flaking of protective | 2022-03-01 | Moderate dirt contamination with minor flaking of protective painting. Overdue painting: Last painted date - 25th December 2017 Due date – 25th December 2020 | Carry out surface preparation to make structural members ready to receive new coat. Apply Self-priming epoxy, epoxy mid-coat, polyurethane topcoat. (2647m2 ) | H | SPDC-2022-03-00000083
| RA PORT-HARCOURT AKUKWA STREET (18 NOS. OF LIGHTING POLES) | 2022-01-19 | Perforated section of lighting pole | Provide, replace and install perforated pole 170 mm dia. X 7 m length of single arm octagonal pole | H | SPDC-2022-03-00000083 | SPDC-2022-02-00000022