## Rigless
| FIELDS | Well Code | Themes | Detailed Scope | Gather FTHPs of all Flowing Strings |  |  | Analyse Well and Determine Strings for Re-alignement |  |  | Field Implementation |  |  | Carry Out Post-Job Analysis
[5 empty] | Start | End | Action Party | Start | End | Action Party | Start | End | Action Party | Start | End | Action Party
1 | OTUMARA | Several | Rigless | Optimize well aligmentment in Otumara field to minimize impact of back-pressure thereby unlocking additional production | 2019-05-15 | 2019-05-30 | Oyebode Oyedele | 2019-06-01 | 2019-06-05 | Erasmus Nnanna | 2019-06-30 | 2019-06-30 | Oyedele Oyebode | 2019-07-15 | 2019-07-17 | Erasmus Nnanna