## Slide 1: Project Title: HUMAN PERFORMANCE & CARE :OKGP & IMOR 2019. RESILIENCE.
Project Scope/Actions :
Develop a training plan approved.(SOU)
Training plan approved and implemented.
Nominate facilitators
Train facilitators
Deliver the modules.
High-level Timeline:
L0-L1:01/04/19
L2: 15/05/19
L3: 15 JUN 2019
L4: JULY 2019
L5: SEPTEMBER 2019
Critical Success Factors:
Ownership By Asset leadership
Buy-in from personnel
Potential Benefits & Measurement:
Strong problem solving skills
Improved Health
Strong social connection
Improved productivity.
Power of positive thinking.
Measurement details
DRS 15 Survey. (PRE & POST)
Charter Template
Project Sponsor: Oladimeji B.
Onyeka Ike, OHNs, and other Resilience facilitators
Business Case/Objectives:
Achieve goals through perceivierance
Develop right attitude when performing under pressure
Understand organization change
Optimize life work/ balance
helping people to develop the ability to cope/bounce back in the midst of challenges.
Maintain positive outlook in challenging circumstances.
Understand how to maintain hopeful outlook.
Keep Things In Perspective
Take Care Of Yourself
Look For Opportunities For Self-discovery
Others not listed
Threat:
Time management
Non GID Users
Transfer/relocation of a trained facilitator

## Slide 2: Project Cadence Commitment Template
No. | Action | Action Party | Threat | Due Date | Status
1-1.1 | Develop Draft Cadence Charter and share with Team | OHN |  | 01/04/19 | 
1-1.2 | Develop Resilience SOU Training Plan for ImoR/Okoloma, approved for implementation | OHN |  | 01/04/19 | 
1-1.3 | Launch Awareness | OHN |  | 01/04/19 | 
1-1.4 | Deliver module 1 | Resilience Facilitators/OHNs |  | 15/05/19 | 
1-1.5 | Module 2 | Resilience Facilitators/OHNs |  | 18/05/19 | 
1.1.6 | Module 3 | Resilience Facilitators/OHNs |  | 20/07/2019 | 
1.1.7 | Module 4 | Resilience Facilitators/OHNs |  | 10/09/2019 | 
1.18 | Module 5 | Resilience Facilitators/OHNs |  | 12/10/2019 | 
1.19 | Module 6 | Resilience Facilitators/OHNs |  | 11/11/2019 | 
2.0 | Module 7 |  |  |  | 
No. | Action | Action Party | Threat | Due Date | Status
1-1.1 | Develop Draft Cadence Charter and share with Team | OHN |  | 01/04/19 | 
1-1.2 | Develop Resilience SOU Training Plan for ImoR/Okoloma, approved for implementation | OHN |  | 01/04/19 | 
1-1.3 | Launch Awareness | OHN |  | 01/04/19 | 
1-1.4 | Deliver module 1 | Resilience Facilitators/OHNs |  | 15/05/19 | 
1-1.5 | Module 2 | Resilience Facilitators/OHNs |  | 18/05/19 | 
1.1.6 | Module 3 | Resilience Facilitators/OHNs |  | 20/07/2019 | 
1.1.7 | Module 4 | Resilience Facilitators/OHNs |  | 10/09/2019 | 
1.18 | Module 5 | Resilience Facilitators/OHNs |  | 12/10/2019 | 
1.19 | Module 6 | Resilience Facilitators/OHNs |  | 11/11/2019 | 
2.0 | Module 7 | Resilience Facilitators/OHNs |  | 5/12/2019 | 

## Slide 3
3
Date Month 2019