## Sheet1
Project : Afam W25T Sectional Replacement Project Schedule
Client: Shell Petroleum Development Company
Prepared By: Vagan Oil and Gas Limited
Project Scope: DEWATERING/EXCAVATION/CUTTING OF SECTION/WELDING & FITTING OF THE SECTION/RADIOGRAPHY/SLEEVING/FLUSHING & HYDROTEST
Date: 19/06/2017
PROJECT SCHEDULE |  |  |  | 2017-06-01 |  |  | 2017-07-01 | [30 empty] | 2017-08-01 | [30 empty] | 2017-09-01 | [29 empty] | 2017-10-01
S/N | DESCRIPTION OF WORK | ACTION | Duration | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Mobilization | VOGL/WBIL | 1
2 | Induction of Personnel | VOGL/WBIL | 1
3 | Facility Entry(Work Permit) | VOGL/WBIL | 1
4 | Spading, Blind Flanging, and Flanging at Launcher and receiver (at Okoloma) | WBIL | 1
5 | Equipment Spotting / Rig up at launcher and receiver (at Okoloma) | WBIL | 1
6 | Flushing | WBIL | 3
7 | Dewatering | WBIL | 3
8 | Excavation | VOGL | 10 | [13 empty] | COMMUNITY STAND OFF
9 | Cutting of section | VOGL | 3
10 | Welding and fitting of the section | VOGL | 4
11 | Radiography | VOGL | 2
12 | Equipment Movement to W27T |  | 0
13 | Line Filling | WBIL | 4
14 | Hydrotesting | WBIL | 4
15 | Line Depresurization/Dewatering | WBIL | 2
16 | Sleeving | VOGL | 1
17 | Back Fill | VOGL | 2
18 | Rig Down | WBIL | 2
19 | Clean up/Demob | VOGL/WBIL | 2
| TOTAL |  | 47
| Work is Planned for One Month |  | 30
| Float (For Rain/No Access/Late PTW opening) |  | -17
| LECD |  | 2017-10-14
Project : Afam W27T Sectional Replacement Project Schedule
Client: Shell Petroleum Development Company
Prepared By: Vagan Oil and Gas Limited
Project Scope:PIGGING/DEWATERING/EXCAVATION/CUTTING OF SECTION/WELDING & FITTING OF THE SECTION/RADIOGRAPHY/SLEEVING/FLUSHING & HYDROTEST
Date: 19/06/2017
PROJECT SCHEDULE |  |  |  | 2017-06-01 |  |  | 2017-07-01 | [30 empty] | 2017-08-01 | [30 empty] | 2017-09-01 | [29 empty] | 2017-10-01
S/N | DESCRIPTION OF WORK | ACTION | Duration | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Mobilization | VOGL/WBIL | 1
2 | Induction of Personnel | VOGL/WBIL | 1
3 | Facility Entry(Work Permit) | VOGL/WBIL | 1
4 | Spading, Blind Flanging, and Flanging at Launcher and receiver (at Okoloma) | WBIL | 7
5 | Excavation | VOGL | 10
6 | Equipment Spotting / Rig up at launcher and receiver (at Okoloma) | WBIL | 11
7 | De-oiling (Pigging) | WBIL | 4
8 | Flushing | WBIL | 4
9 | Dewatering | WBIL | 4 | [13 empty] | COMMUNITY STAND OFF | [61 empty] | FAULTY CLOSED DRAIN LEVEL SWITCH & TNP OUTAGE
10 | Cutting of section | VOGL | 2
11 | Welding and fitting of the section | VOGL | 3
12 | Radiography | VOGL | 2
13 | Line Filling | WBIL | 4
14 | Hydrotesting | WBIL | 2
15 | Line Depresurization/Dewatering | WBIL | 3
16 | Sleeving | VOGL | 2
17 | Back Fill | VOGL | 2
18 | Rig Down | WBIL | 2
19 | Clean up/Demob | VOGL/WBIL | 2
| TOTAL |  | 67
| Work is Planned for One Month |  | 30
| Float (For Rain/No Access/Late PTW opening) |  | -37
| LECD |  | 2017-10-21