## Weekly Commitments
FUNCTIONS | INITIATIVE | COMMITMENTS | STATUS
East Asset | Deploy foam lift on NAG wells in East Asset to unlock 120MMscf/d and 3.0kbopd | Execute Foam Injection and Unloading of KOMA 6T. | 1
East Asset | Deploy foam lift on NAG wells in East Asset to unlock 120MMscf/d and 3.0kbopd | Continue Monitoring of Pressure on the Foam-injected Soku Wells 38T, 50T & 53T and open-up wells if pressure improves. Ongoing - continued to monitor wells for buildup. | 1
East Asset | OMl 20 Re-entry (Egbema Main, Egbema West and Ugada Fields) to Increase production by circa 14,000bbl/d | Complete Sign-off of Handover Agreement | 1
East Asset | OMl 20 Re-entry (Egbema Main, Egbema West and Ugada Fields) to Increase production by circa 14,000bbl/d | Site handover of facilities 1st of July 2025 and demob of NEPL personnel from site | 1
East Asset | OMl 20 Re-entry (Egbema Main, Egbema West and Ugada Fields) to Increase production by circa 14,000bbl/d | Progress with Security exercise at EGBW | 0
West Asset | OPUK 13L/S (0.5Kbbls).LEC: 30/06 | Achieved 99% completion: 98% of hook up arm & comingle spool | 1
West Asset | Opuk 32T (0.6Kbbls) LEC 31/07 | Achieved 90% completion: 100% Fabrication of Hook up arm | 1
West Asset | Tunu 15 L.S (2.3Kbbls) LEC – 12/07 | Xmas tree installation completed | 1
NOV Onshore | OPEX optimization ($) | Engage with operators and agree at least 2 cost saving initiatives by end June 2025. Operators have been engaged but asked for more time to work the initiatives internally and revert. | 0
NOV Onshore | Monetization of AG from NAOC-Operated unitized fields to realize ca. $2M (Ogbainbiri-Afuo: $1,102,982 & Akri-Oguta: $995,725) | Follow through with Oando for the IDD outcome to enable execution of Agreements. Followed through, Oando informed that the IDD process takes time but currently conducting checks on documents submitted by Renaissance. To revert if additional information is required. | 1
NOV Onshore | Grow NOV production by additional 2.67Kbopd above OP24 plan by Q4. | Work with NEPL to identify Q1 delivery recovery plans to meet Uzere-East 2025 promise – end Jun ’25. Received revised forecast from June connect with NEPL. | 1
Pipelines | Liquidate 20 RBSL Sites | Carryout visit to 2no RBSL site | 1
Pipelines | 24hrs Operations at Rumuekpe | Bank gains (FCF: $147.44K – YTD FCF :$429.89K) associated with incremental oil production(10/6 – 29/6) | 1
Pipelines | All Terrain Vehicle - ATV | Check bid for compliance with requirements and specifications | 1
Production Services | SPDC Material Re-Use (O) - 2025 | Support Asset & Project Teams with requested materials from grey stock. - Achieved This week’s savings: $68,518.18 (FCF: $4,111.09) | 1
Production Services | SPDC Material Re-Use (O) - 2025 | Progress validation and inventorization; PHIA PHASE II in PORT HARCOURT Warehouse from 57% to 60%. | 1
Production Services | SPDC Material Re-Use (O) - 2025 | Progress validation and inventorization; FYIP Project Surplus Spares in North Bank CPF from 87% to 90% | 1
Production Services | SPDC Material Re-Use (O) - 2025 | Upload all validated Forcados Terminal Surplus Materials on CMMTS and commence write-off process for Obsolete and damaged Materials. – Achieved | 1
Production Services | SPDC Material Re-Use (O) - 2025 | Kick-off Material validation and Inventorization exercise for NGC Surplus Materials at I.A Ogunu Warehouse | 1
Production Services | Improve Availability by Improving Facility and Compressor Uptime (OTUMARA IVD). | Finalise close out dates of the implementation actions with action parties and fix a weekly/bi-weekly cadence for tracking – Achieved | 1